SIXTH FRAMEWORK PROGRAMME

Project no.: PL012002

Project acronym: GMS application

Project title:

“Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century”

Specific Support Action

Priority D.1. Environmental Protection

D5. FINAL   REPORT

Period covered: 1 August, 2005 to 31 July, 2006

Date of preparation: 1 September, 2006

Start date of project: 1 August, 2005				         Duration: 12 months

Project coordinator name: Dr. Leonid P. Bobylev

Project coordinator organisation name: Scientific Foundation “Nansen International Environmental and Remote Sensing Centre”, St. Petersburg

Revision: 1.0

St. Petersburg 2006

Summary

Within the INCO2 RADARC project (ICA2-CT-2000-10037, 2001 - 2003) a Generic Model System (GMS) for the first time was created for simulations of global change scenarios in the 21st Century for potential spreading of radioactive contaminants in the Arctic Ocean from European and land-based sources in Siberia.

This SSA will demonstrate and extend the GMS applications for the management of environmental risks associated with man-made changes and industrial waste in the Arctic regions. The development of methods for risk assessment using mathematical simulation models are extremely important, especially for the anthropogenic waste concerned with persistent organic pollutants (POPs), industrial chemicals (PCP´s) and heavy metals.

Accordingly, the overall objective was to demonstrate and promote the use of an existing GMS for simulations of industrial pollution spreading in the marine Arctic environment in order to support the management of environmental risks associated with man-made changes.

One of the main results of this project was preparation of book manuscript – “Radioactivity and Pollution Spreading in the Arctic Ocean: Observations, Modelling and Simulations” with detailed GMS description and its applications on wide range of contaminant including persistent organic pollutants, heavy metals and petroleum hydrocarbons in the Arctic marine environment. Moreover, during the GMS Thematic expert Workshop a potential users group was formed and preliminary topics for new proposals for FP7 integrated projects was formulated.

A dynamic GMS project web-site with links to the CORDIS and partner’s websites for the project characterization and progress of realization was established to maintain an information flow to the potential user community.

Table of Contents

1.	Summary description of project objectives	3

2.	Contractors involved and external experts	4

Discription of the consortium	4

Management	7

The repartition of tasks between the partners will be as follows:	8

3.	Work performed and end results	9

4.	Conclusion. Impact on research or research-based policy development at regional, national or European level. using and disseminating knowledge	14

Appendix 1. Agenda and Protocol of the GMS application project Kick-off Meeting	15

Appendix 2. Agenda and Protocol of the GMS application Progress Meeting	22

Appendix 3. Draft of the monograph Contents. Version 5, 26 October 2005	25

Appendix 4. Agenda of the GMS application Thematic Expert Workshop	35

Appendix 5. Agenda of the GMS application Final Meeting	39

- Summary description of project objectives

Within the INCO2 RADARC project (ICA2-CT-2000-10037, 2001 - 2003) a Generic Model System (GMS) for the first time was created for simulations of global change scenarios in the 21st Century for potential spreading of radioactive contaminants in the Arctic Ocean from European and land-based sources in Siberia.

This SSA will demonstrate and extend the GMS applications for the management of environmental risks associated with man-made changes and industrial waste in the Arctic regions. The development of methods for risk assessment using mathematical simulation models are extremely important, especially for the anthropogenic waste concerned with persistent organic pollutants (POPs), industrial chemicals (PCP´s) and heavy metals.

Accordingly, the overall objective is to demonstrate and promote the use of an existing GMS for simulations of industrial pollution spreading in the marine Arctic environment in order to support the management of environmental risks associated with man-made changes.

This objective will be implemented through:

- Assessment and demonstration of the extended GMS applications for simulations of the spreading and distribution and fate of major pollutants in the marine Arctic environment;

- Organisation and holding of thematic expert workshop for demonstration and promotion of GMS use for monitoring of different pollutants in the Arctic;

- Reporting, publication and dissemination of project results, including one book manuscript - “Simulation of a Radioactive Spreading in the Arctic“ with detailed GMS description and its applications on wide range of contaminant spreading in the Arctic region.

The project seeks to increase the efficiency of future environmental monitoring and scientific research and to support the management of environmental risks associated with man-made changes and industrial pollution in the Arctic marine environment.

- Contractors involved and external experts

The three institutions from Russia, Norway and Ukraine will carried out the project:

- Scientific Foundation “Nansen International Environmental and Remote Sensing Centre”, St. Petersburg, Russia (Participants 1);

- Nansen Environmental and Remote Sensing Center”, Bergen, Norway (Participants 2);

- Ukrainian Center of Environmental and Water Projects, Kiev, Ukraine (Participants 3).

Moreover external scientists from leading European and Russian institutes was involved as guiding experts to the project through thematic expert workshop. It was, for example:

Arctic and Antarctic Research Institute (AARI), St.Petersburg, Russia; Marine Hydrophisical Institute,  Sebastopol, Ukraine; Murmansk Marine Biological Institute (MMBI), Murmansk, Russia; Khlopin Radium Institute (KRI), St. Petersburg, Russia; SPA ”Tayphoon”, Roshydromet, Obninsk, Russia; St. Petersburg Department of the State Oceanographical Institute (SPbSOI) Roshydromet, St.Petersburg, Russia; St. Petersburg State University (SPbSU), Department of geography and geoecology, St.Petersburg, Russia; Northern Water Problem Institute (NWPI), Petrozavodsk, Russia; Shelf Geological Environment Centre of the Russian Federal State Enterprise ”Sevmorgeo”, St.Petersburg, Russia; Scientific Research Center of Ecological Safety of Russia Academy of Sciences (SRCES RAS), St. Petersburg, Russia and others.

Having been involved in realization of a many national and international projects, during the project implementation the participant institutions disseminated the information about project among some European scientific centres and institutions located in other countries beyond Europe.

### Discription of the consortium

The Scientific Foundation “Nansen International Environmental and Remote Sensing Centre” (NIERSC) was founded in 1992 as a non-profit research centre. NIERSC addresses such areas of its scientific activities as climate change and environment deterioration in high northern latitudes. Within the NIERSC sphere of interests are aquatic ecology, sea ice dynamics, North Atlantic and Arctic oscillations, environmental pollution and radioactivity. The staff members of the Centre incorporate core scientists (including two Professors, three D.Sc. and ten Ph.D.), associated staff, Ph.D. students and administrative personnel totally about 40 employees. NIERSC enjoys an internationally recognized expertise in environmental monitoring from satellites, marine environments inclusive. Creation of advanced algorithms for inferring the desired environmental data from visible to microwave space images, development of numerical models simulating the optical properties of marine and land environments are salient but not sole specialties of NIERSC. NIERSC is among the leading scientific teams focused upon a) observations and simulations of global climate change, b) investigations of alterations to the ice regime in marine environments, c) modelling of aquatic ecosystems, etc. NIERSC has also an extensive experience in coordination of activities of Russian partners both in national and international projects, convocation of associated seminars, workshops and progress meetings.

The Nansen Environmental and Remote Sensing Center (NERSC) in Bergen, Norway was established in 1986 and is a non-profit environmental and climate research institute, affiliated with the University of Bergen. NERSC strategy of the research and application development is based on an integrated approach using information from various sources combined with numerical model simulation through advanced data assimilation techniques. The NERSC staff members consist of 44 persons, including scientific personnel, 8 PhD Candidates. The scientific personnel have professional background in remote sensing, oceanography, climatology, mathematics, physics, informatics/computer science, geology and biology. NERSC has extensive experience in co-ordinating large international research projects in oceanography and remote sensing, particularly in Arctic regions. Several major Arctic experiments such as NORSEX, MIZEX, SIZEX, CARDEEP in the GIN Sea, ICEWATCH in the Russian Arctic, COASTWATCH and AOSGE Pilot project in 1996 has been co-ordinated by NERSC. In addition NERSC was co-ordinator of several completed and ongoing INTAS Projects as well as being the coordinator for two completed FP5 INCO-2 projects (RADARC and WHITESEA) as well as partner in another INCO-2 project (AMETHYST). Under FP5 NERSC has participated (some still not completed) in 23 projects, of which co-ordinating 14 of these.

The personnel involved have expertise in complementary fields of project studies: Prof. Ola M. JOHANNESSEN is the founding Director of NERSC. He has been the chief scientist of more than 30 large marine experiments and expeditions. He is the author/co-authorof more than 400 publications. Mr. Lasse H. PETTERSSON, leading scientist, has more than 20 years experience in oceanographic environmental research at NERSC. He is and has been the project leader for several large EC, ESA and national funded research projects, including the deputy project leader for RADARC. He will be the deputy responsible for co-ordination and management for these SSA activities. Prof. Helge DRANGE, applied mathematician, has wide experience in use of global scale ocean models and coupled physical-biogeochemical models for climate research, process studies and industry.

Ukrainian Center of Environmental and Water Projects (UCEWP) Ltd is consulting and software development company (SME), specializing in environmental risk assessment, radiation safety, environmental and water management, environmental hydrothermodynamics, river and marine computational hydraulics, physical oceanography, coastal engineering and development of environmental modelling software and data bases (see http://www.ucewp.kiev.ua). Within the Fourth, Fifth and now Sixth Framework Programs, this group participates in the development of the “EU Real time, On-line, Decision Support (RODOS) system for the off-site management of nuclear emergencies” as well as customisation of this system in the Ukraine and other European countries. The group is participating in Fifth and Sixth Framework Program, INTAS, INCO-COPERNICUS Programs, TACIS and in a set of bilateral projects concerning pollutant transport in rivers, lakes and coastal seas, flood risk assessment and management. From 1996 it actively participates in the EU projects on the radionuclide contamination of the Arctic seas, large Siberian Rivers and estuaries. Team leader of UCEWP group, Dr. Vladimir Maderich is a physical oceanographer. Dr. Mark Zheleznyak is an expert in environmental risk assessment and contamination of inland waters.

In recent years the partners of this composite team were jointly involved in the implementation of a number of projects solicited and sponsored by EC:

- “Sustainable management of the marine ecosystem and living resources of the White Sea” – WHITESEA, INCO-COPERNICUS-II (NIERSC, NERSC etc.), 2000-2002;

- “The water quality in the coastal zone of the Gulf of Finland: measurements, remote sensing, computer modelling - development of a strategic tool for sustainable management” - INTAS FinGulf (NIERSC, NERSC etc.), 2000-2002;

- “Simulation scenarios for potential radioactive spreading in the 21st century from rivers and external sources in the Russian Arctic coastal zone” – RADARC, INCO-COPERNICUS-II (NIERSC, NERSC, UCEWP team as a part of IMMSP), 2000-2003

and some others.

Moreover, scientists from NIERSC and NERSC recently published three books:

- Volkov, V.A., O.M. Johannessen, V.E. Borodachev, G.N. Voinov, L.H. Pettersson, L.P. Bobylev, A.V. Kouraev: Polar Seas Oceanography: An Integrated Case Study of the Kara Sea. Springer/Praxis, Chichester, UK, 2002, 495 pp.

- Bobylev L.P., Kondratyev K.Ya. and Johannessen O.M.: Arctic Environment Variability in the Context of Global Change. Springer/Praxis, Chichester, UK, 2004, 500 pp.

- O.M. Johannessen, Vitali Yu. Alexandrov, Ivan Ye. Frolov, Stein Sandven, L.H. Pettersson, L.P. Bobylev, Kjell Kloster, Vladimir G. Smirnov, Yeugeny U. Mironov and Nikolay G. Babich. Remote Sensing of Sea Ice in the Northern Sea Route: Studies and Applications. Springer/Praxis, Chichester, UK, 2006, 472 pp.

All three institutions to be involved in the proposed project possess sufficient manpower including some experts with a worldwide reputation.

### Management

Overall project co-ordination and scientific supervision was the responsibility of the Director of NIERSC Dr. Leonid P. Bobylev.

A consortium agreement was signed between all partners before the kick-off meeting, which will deal with all aspects of the relationships between partners, including legal aspects, intellectual property rights and further exploitation of the project results.

The project co-ordinator was the liaison person for communication with the European Commission and the point of contact for delivery of all project deliverables to the EU. A project Management Group was established with one partner from each participant, namely Dr. Vladimir A. Volkov (NIERSC), Dr. Mark I. Zheleznya(UCEWP) and Mr. L:asse H. Pettersson (NERSC), with the project co-ordinator as the Chair. The Management Group communicated on a regular basis using telephone meetings, e-mail for monthly progress reports and during project meetings and visits. The management group worked closely together with each work package leaders.

### The repartition of tasks between the partners will be as follows:

Participant No. 1 is the Scientific Foundation “Nansen Centre” (NIERSC), St. Petersburg, Russia, the principal coordinator of the project. NIERSC’s responsibilities covered not only assessment of research aspects but also logistic and financial issues. NIERSC also organised two working meetings and was responsible for the project reporting and deliverables. NIERSC also holds thematic workshop on the assessment of resources of GMS for its extended application, and the preparation of the demonstration of extended GMS for non-nuclear application in the Arctic region, instead of UCEWP. But UCEWP preparation to this workshop was by participation of the UCEWP.

Participant No. 2; NERSC, Bergen, Norway, is among the leading scientific teams focused upon a) observations and simulations of global climate change, b) investigations of alterations to the ice regime in marine environment, c) modelling of aquatic ecosystems, etc. Within the framework of the project, NERSC was responsible on contacts with EU institutions, expert and potential users groups formation, final version of book.

Participant No. 3; The Ukrainian Center for Environmental and Water Projects (UCEWP), Kiev, took pert in preparation of the thematic workshop on the assessment of resources of GMS for its extended application, and the preparation of the demonstration of extended GMS for non-nuclear application in the Arctic region. UCEWP was responsible also for the GMS extension with components relating to the process oriented modelling of rivers, estuaries and regional seas. and tasked with the preparation of the WEB-site.

- Work performed and end results

The Project fulfillment began with holding the Kick-off Meeting at the Nansen International Environmental and Remote Sensing Centre, St. Petersburg, Russia on 22 August, 2005. Representatives of all Project Partners were attending the Meeting including the invited participant Dr. Andrey V. Stepanov from the Khlopin Radium Institute (KRI), St. Petersburg, Russia, who is one of the main authors of the monograph “Radioactivity and Pollution Spreading in the Arctic Ocean: Observations, Modelling and Simulations”, which is being prepared for publication in the Project framework. The technical session of the meeting (Appendix 1) discussed the formal issues connected with the terms and requirements of fulfilling the SSA Projects. In addition, the problems of the status of the individual blocks of a complex model of pollution spreading in the Arctic Ocean were discussed, the draft structure of the monograph was developed, the list of potential invited new co-authors was determined, the Action Plan under the Project was corrected and adopted for the entire period of its fulfillment, the data provision/delivery scheme and principles of its logistic implementation were defined and the  financial management issues were considered.

The partners have agreed that the Thematic Expert Workshop should become the main event of the Project and the monograph manuscript – the main outcome of the Project. The Protocol of the Kick-off Meeting was prepared and it was decided that the monograph will be published at the PRAXIS – Springer Publishing House in the end of 2006 or at the beginning of 2007.

The next planned events of the project were the Progress meeting and the Thematic Expert Workshop: “Demonstration and promotion of GMS use for monitoring of different pollutants in the Arctic” in the Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev. However in preparation of the Thematic Expert Workshop it has become clear that coordination of the issues of participation of experts from different countries would require more time. Therefore only the Progress meeting was held in Kiev on 26 October, 2005, its main aim being consideration of the Status of the RADARC Monograph preparation and development of the new version of the monograph contents and the work plan for finalizing the work on the manuscript. A number of independent experts on the Artic environmental modeling and investigation were invited from the leading institutes of Russia: Dr. Alexey L. Karsakov, Knipovich Polar Research Institute of Marine Fisheries and Oceanography (PINRO) Murmansk, Russia; Prof. Vladimir V. Denisov and Dr. Valery A. Golubev, Murmansk Marine Biological Institute (MMBI), Murmansk, Russia; Dr. Vladimir M. Kattsov, Voeikov Main Geophysical Observatory (VMGO), St. Petersburg, Russia, who were at that time in Kiev.

A new corrected version appeared as a result of discussing the contents of the monograph (Appendix 3). Proposals for inviting additional new co-authors to participate in preparation of Chapter 5 were also considered and the responsible persons and the dates of submitting the sections of the monographs by the authors were determined.

This working meeting has also made a decision to meet at a later date (possibly to May 2006) and transfer the place of holding the Thematic Expert Workshop to St. Petersburg, where there are numerous institutes involved in the ecology problems and development of the methods for environmental pollution monitoring. It was simpler to provide participation of lead experts in St. Petersburg at the minimal costs of the visits. The Workshop also aimed at attempting to formulate the topic and form a consortium for preparation of application to Frame Program 7. The GMS development and assessment of the possibilities of adapting this system for different regions of Europe and Russia where there is a problem of estimating the transfer of different polluting components by large rivers to seas was to be the main idea of the new application. For example, the GMS could be adapted for the water systems: “Lena River-Laptev Sea-Arctic Ocean”, “Kolyma River-East-Siberian Sea –Arctic Ocean”, “Volga and Ural Rivers-Caspian Sea”, etc.

During the period prior to the Thematic Expert Workshop at the UCEWP leadership, the work on preparing the Demonstration of an extended GMS applications for the management of environmental risks associated with the industrial anthropogenic non-radioactive waste: persistent organic pollutants (POPs), industrial chemicals (PCP´s) and heavy metals in the Arctic regions was continued, the list of experts invited to this event was determined, their participation in the workshop was coordinated and the work on writing and editing the monograph section was continued.

In the framework of this work a number of specialists from the partner-institutes, invited experts and new co-authors traveled to other research centers for joint work on the monograph sections and for consultations, which is reflected in the fiscal and management reports. For example, Dr. Volkov, NIERSC, one of the main authors of the monograph has been working with monograph materials in Bergen together with the colleagues from the Bergen Nansen-Center. In addition, there were organized a one-week scientific visit to Marine Hydrophisical Institute, Sevastopol, Ukraine (Prof. V. Koudryavtsev, NIERSC) to carry out research within GMS project goals and discuss participation in the monograph as a co-author of chapter 5 of Dr. Sergey KONOVALOV from Marine Hydrophisical Institute; a three-day business trip to NPO “Taifun” Roshydromet, Moscow (Obninsk), Russia in June 2006 (Dr. V. Volkov, NIERSC) to work with the monograph together with Dr. Alexey KONOPLEV, SPA ”Tayphoon”, a two-week visit to NERSC, Bergen, Norway (Prof. V. Koudryavtsev) to demonstrate the General Model System to monitor pollution in the Arctic; a one-week visit to NERSC, Bergen, Norway (Dr. L. Bobylev) to work on the Monograph in June 2006.

The GMS Thematic Expert Workshop was held on 30 May, 2006 at NIERSC in St. Petersburg. The agenda (Appendix 4) included presentations of the project participants – authors of separate GMS blocks, reviews on pollution of water bodies and the main presentation: Demonstration of an extended the GMS applications for the management of environmental risks associated with the industrial anthropogenic non-radioactive waste: persistent organic pollutants (POPs), industrial chemicals (PCP´s) and heavy metals in the Arctic regions.

A key point of the agenda was the Round Table: GMS application for the management of environmental risks associated with man-made changes and industrial wastes in the Arctic region.

Twenty people participated in the workshop, from 13 research centers of Russia, Norway and the Ukraine, including six official project participants and visiting experts: Dr. G.Il’in, MMBI, Murmansk, Russia; Dr. Sergey KONOVALOV Marine Hydrophysical Institute,  Sebastopol, Ukraine; Dr. Alexey KONOPLEV, SPA ”Tayphoon”, Roshydromet, Obninsk, Russia. In addition to the enumerated persons, post-graduates in the corresponding fields from the St. Petersburg State University, Arctic and Antarctic Research Institute, Russian State hydrometeorological University attended the meeting.

All presentations made at the workshop were posted to the project site.

The discussion was prolonged and quite interesting. The proposals were made (Prof. V.Fouks) for improving the GMS with application of modern satellite remote sensing data on chlorophyll concentration and estimates of temporal and spatial derivatives of this value, and using satellite altimeter information for estimating the speeds of currents by the sea level tilts. The topics were formulated, which could serve as a basis for new applications for FP7. We do not give these formulations due to copyright considerations, however when the FP7 competitions will be declared it is planned to hold a new meeting with the main topic of preparing the application.

After holding the Thematic Expert Workshop a group of scientists (Prof. V.Troyan and Prof. V.Dmitriev St. Petersburg State University, St. Petersburg, Russia and Prof. G. Menzhoulin, Russian Academy of Science, St. Petersburg, Russia) headed by Dr. Bobylev traveled to Bergen in June to take part in the working meeting on the GMS Application Project as invited experts to discuss the structure and content of the monograph sections connected with the problem of observations and modeling global climatic changes and marine ecosystems and assessment of spreading non-radioactive pollution in the Arctic under the global climate warming conditions (objectives 3 and 5).

The Final Meeting took place in St. Petersburg after the official deadline of the Project, because it was impossible to organize the final meeting on term in summer, 2006 due to the of vacations and trips. All expenses were covered by partners’ organizations.

The agenda (Appendix 5) included consideration of the reporting documents including the fiscal and management reports.

The change of the reporting date was coordinated with the administration of European commission.

Fig. 1. Graphical presentation of work packages

- Conclusion. Impact on research or research-based policy development at regional, national or European level. using and disseminating knowledge

So, the objectives of the Work Program can be considered achieved and the work plan as fully fulfilled. The project has made a significant contribution to research or research-based policy development at the regional and national level in Russia, Norway and the Ukraine through the implementation of assessment and demonstration of the extended GMS applications for simulations of the spreading and distribution and fate of major pollutants in the marine Arctic environment. As a result of the main event of the project, namely the Thematic Expert Workshop in St. Petersburg, the new scientific consortium in the area of the contaminant spreading study in the Arctic region was established. This international group plans to prepare some proposals for the FP7 in early 2007.

The project promoted international cooperation between Russian, Ukrainian, Norwegian and other European scientists.

The other very important result of the project was preparation of the monograph manuscript for submitting to the Publishers with detailed GMS description and its applications on a wide range of contaminant spreading in the Arctic region: “Radioactivity and Pollution Spreading in the Arctic Ocean: Observations, Modelling and Simulations”. The contract with the Springer/Praxis publishing house for publishing the book in the Springer/Praxis series “POLAR SEAS OCEANOGRAPHY” in 2007 was signed. The deadline is 1 May 2007 and the monograph is 90 % ready.

The information was disseminated through a special project web-site on the Internet and will be made available by selling the book. When published, it will be circulated to participants of activities conducted in the framework of this SSA project. The project web-site was established early in the project to maintain an information flow to the potential user community and will develop after finishing the project.

The results of the project will be also published in the international peer-reviewed journals and presented at international conferences, in the related scientific/technical literature dedicated to such fields as environmental management, nuclear energy, marine ecology, etc. In this respect the application potential of the project will be communicated to a very wide potential user community.

Information about the project is disseminated using the EC and partners’ mailing lists.

### Appendix 1. Agenda and Protocol of the GMS application project Kick-off Meeting

Meeting Agenda

Project full title: Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century

Project acronym: GMS application

Proposal/Contract no.: PL012002

Kick-off Meeting

Venue:	Nansen International Environmental and Remote Sensing Centre, St. Petersburg, Russia

Date:	Monday, 22 August 2005

Time:	10:00 – 17:00

| 10:00 – 10:05 | Opening and welcome |
| --- | --- |
|  | Dr. Leonid P.Bobylev, NIERSC |
| 10:05 – 10:30 | ###### Introduction. Meeting objectives ###### Presentation of the host organization, NIERSC |
|  | Dr. Leonid P.Bobylev, NIERSC |
| 10:30 – 11:00 | ###### Presentation of the partner organizations: |
|  | ###### Nansen Environmental and Remote Sensing Centre - NERSC, Bergen, Norway |
|  | Mr. Lasse H. Pettersson |
|  | ###### Ukrainian Center of Environmental and Water Projects - UCEWP , Kiev, Ukraine |
|  | Dr. Mark I. Zheleznyak |
| 11:00 – 11:20 | Hystory of the proposal (review of the Kara Sea and RADARC projects) |
|  | Dr. Leonid P.Bobylev and Dr. Vladimir A. Volkov, NIERSC |
| 11:20 – 11:40 | Coffee Break |
| 11:40 – 12:10 | Review of Commission requirements |
|  | Mr. Lasse H. Pettersson, NERSC |
| 12:10 – 12:30 | Review of the management structure and decision making mechanisms, administrative and financial procedures |
|  | Dr. Leonid P.Bobylev and Mr. Lasse H. Pettersson, NERSC |
| 12:30 – 14:00 | Lunch |
|  | Technical session |
| 14:00 – 14:20 | Project programme. Objectives, deliverables, timescales |
|  | Dr. Leonid P.Bobylev, NIERSC |
| 14:20 – 14:40 | Status of the river modelling |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| 14:40 – 15:00 | Status of NIERSC Kara Sea modeling |
|  | Dr. Ivan A. Neelov, NIERSC |
| 15:00 – 15:20 | Status of NERSC Arctic Ocean modeling |
|  | Mr.Lasse H. Pettersson, NERSC |
| 15:20 – 15:40 | Coffee Break |
| 15:40 – 16:00 | Status of the RADARC Monograph preparation |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 16:00 – 16:30 | Project management |
|  | Mr.Lasse H. Pettersson, NERSC |
|  | - Data provision/delivery scheme and principles of its logistic implementation - Financial management - Action plan for the coming period |
| 17:00 | Adjourn |

LIST OF PARTICIPANTS

Nansen International Environmental and Remote Sensing Centre (NIERSC), St.Petersburg, Russia

Dr. Leonid P. BOBYLEV

Dr. Ivan A. NEELOV

Dr. Vladimir A. VOLKOV

Nansen Environmental and Remote Sensing Centre (NERSC), Bergen, Norway

Mr. Lasse H. PETTERSSON

Ukrainian Center of Environmental and Water Projects, Kiev, Ukraine

Dr. Mark J. ZHELEZNYAK

INVITED PERSON

Khlopin Radium Institute (KRI), St. Petersburg, Russia

Dr. Andrey V. STEPANOV

PROTOCOL No. 1

of the

GMS application Kick-off Meeting

Project full title: Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century

Project acronym: GMS application

Proposal/Contract no.: PL012002

Venue:	Nansen International Environmental and Remote Sensing Centre, St. Petersburg, Russia

Date:	Monday, 22 August 2005

#### Participation in Kick-off Meeting:

Nansen International Environmental and Remote Sensing Centre (NIERSC), St.Petersburg, Russia

Dr. Leonid P. BOBYLEV

Dr. Ivan A. NEELOV

Dr. Vladimir A. VOLKOV

Nansen Environmental and Remote Sensing Centre (NERSC), Bergen, Norway

Mr. Lasse H. PETTERSSON

Ukrainian Center of Environmental and Water Projects, Kiev, Ukraine

Dr. Mark J. ZHELEZNYAK

#### Invited person:

Khlopin Radium Institute (KRI), St. Petersburg, Russia

Dr. Andrey V. STEPANOV

# Opening and Welcome

Dr. Leonid P.Bobylev welcomed the General Meeting members and opened “GMS application” project Kick-off Meeting

# Approval of Agenda

Decision and Vote: The Agenda was approved.

###### Introduction. Meeting objectives.

Dr. Leonid P.Bobylev, Director of NIERSC, reviewed the status of the GMS application contract and formulated the meeting objectives.

Decision and Vote: The Meeting took the report as information.

###### Presentation of the host organization, NIERSC

Dr. Leonid P.Bobylev made a short presentation of NIERSC and informed about past and current NIERSC projects that concern to the objectives of “GMS application” project.

Decision and Vote: The Meeting took the presentation as information.

###### Presentation of the partner organizations

Mr. Lasse H. Pettersson: Nansen  Environmental and Remote Sensing Centre - NERSC, Bergen, Norway

Dr. Mark I. Zheleznyak: Ukrainian Center of Environmental and Water Projects - UCEWP , Kiev, Ukraine

Decision and Vote: The Meeting took the presentations as information.

###### Hystory of the proposal (review of the Kara Sea and RADARC projects

Dr. Vladimir A. Volkov, NIERSC performed shortly information about INTAS Kara Sea and INCO-2 RADARC projects that were preceded GMS application project.

Decision and Vote: The Meeting took the report as information.

###### Review of Commission requirements

###### Mr. Lasse H. Pettersson, NERSC informed about EU commission requirements for SSA projects.

Decision and Vote: The Meeting took the report as guiding principle.

###### Review of the management structure and decision making mechanisms, administrative and financial procedures

Dr. Leonid P. Bobylev presented information about financial procedures and other administrative mechanisms. NIERSC is main contractor; all payments will be made via NIERSC to partners.

Decision and Vote: The Meeting took the report as guiding principle.

Technical session

###### Project programme. Objectives, deliverables, time scales

Dr. Leonid P. Bobylev presented detail information about time profile.

Decision and Vote: The Meeting took the report as guiding principle. The work program was accepted.

###### Status of the modelling

Speaker underlined that the main components of GMS are in working conditions, all partners will prepared a additional proposal for development of the model component for extend the GMS applications for the management of environmental risks associated with man-made changes and industrial waste in the Arctic regions.

Decision and Vote: The Meeting took the report as guiding principle.

| Action 10.1 | To prepare a proposals for development of the model component for extend the GMS applications for the management of environmental risks associated with man-made changes and industrial waste in the Arctic regions. Due date: October, 2005 | Mark I. Zheleznyak Ivan A. Neelov Lasse H. Pettersson |
| --- | --- | --- |

###### Status of the RADARC Monograph preparation

Dr. Vladimir A. Volkov, NIERSC, presented information about last version of Contents and status of the Monograph preparation.

Dr. Mark I. Zheleznyak suggested to include in the Contents additional Chapter  5 “Methodology of GMS application for simulation of non-radioactive pollutants spreading in the Arctic environment”.

Decision and Vote: The Meeting accepted a concept of the Monograph..

| Action 11.1 | To prepare a structure and contend of the Chapter 5. To mail this proposal to all authors for discussion and agreement. Due date: September, 2005 | Mark I. Zheleznyak |
| --- | --- | --- |
| Action 11.2 | To prepare a corrected draft of Chapter 1 (1.1, 1.2.2, 1.3.1) and Chapter 2. Due date: December, 2005 | Andrey V. Stepanov |

###### Project management

Lasse H. Pettersson, NERSC

| Action 11.1 | To organise a next GMS application progress meeting in Kiev in October, 2005 | Mark I. Zheleznyak |
| --- | --- | --- |
| Action 11.2 | To prepare suggestions on involving of some experts in area of industrial waste in the Arctic regions for preparation of Chapter number 5. | Mark I. Zheleznyak, Vladimir A. Volkov |
| Action 11.3 | To plan a two months work of Dr. Volkov in Bergen for preparation of the next version of the monograph text | Lasse H. Pettersson, Vladimir A. Volkov |

Decision and Vote: Action plan for the coming period was accepted.

Dr. Leonid P.Bobylev, NIERSC

St. Petersburg, 22 August, 2005

### Appendix 2. Agenda and Protocol of the GMS application Progress Meeting

Meeting Agenda

Project full title: Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century

Project acronym: GMS application

Proposal/Contract no.: PL012002

Progress meeting

Venue:	Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev

Date:	Thursday, 26 October 2005

Time:	10:00 – 15:30

Agenda

| 10:00 – 10:05 | Opening and welcome |
| --- | --- |
|  | Dr. Mark Zheleznyak, Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev |
| 10:05 – 10:40 | ###### Introduction. Meeting objectives ###### Presentation of the host organization, UCEWP |
|  | Dr. Mark Zheleznyak, UCEWP |
| 10:40 – 11:00 | Coffee Break |
|  | Technical session. Status of the monograph preparation |
|  | Chairman: Prof. Ola M. Johannessen |
| 11:00 – 11:30 | ###### LIST of ACTIONS of the GMS application Kick-off Meeting |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 11:30 – 11:50 | Status of the river modelling |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| 11:50 – 12:10 | Status of NIERSC Kara Sea modeling |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 12:10 – 12:30 | Status of NERSC Arctic Ocean modeling |
|  | Mr.Lasse H. Pettersson, NERSC |
| 12:30 – 13:30 | Lunch |
| 13:30 – 13:50 | Status of the RADARC Monograph preparation in general |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 13:50 – 14:10 | ## Project management (Lasse H. Pettersson, NERSC) |
|  | - Data provision/delivery scheme and principles of its logistic implementation - Financial management - Action plan for the coming period |
| 14:10 – 16:00 | Round Table. New version of the monograph contents and working plan |
|  | Chairman: Prof. Ola M. Johannessen |
| 16:00 | Adjourn |

LIST OF PARTICIPANTS

Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev, Ukraine:

Mr. Igor BROVCHENKO

Dr. Vladimir I. KOSHEBUTSKY

Dr. Kateryna TERLETSKA

Dr. Mark I. ZHELEZNYAK

Nansen Environmental and Remote Sensing Center (NERSC), Bergen, Norway:

Prof. Ola M. JOHANNESSEN

Mr. Lasse H. PETTERSSON

Nansen International Environmental and Remote Sensing Center (NIERSC), St.Petersburg, Russia:

Dr. Vladimir A. VOLKOV

Mr. Vladimir V. IONOV

Invited persons

Knipovich Polar Research Institute of Marine Fisheries and Oceanography (PINRO):

Dr. Alexey L. KARSAKOV

Murmansk Marine Biological Institute (MMBI), Murmansk, Russia:

Prof. Vladimir V. DENISOV

Dr. Valery A. GOLUBEV

Voeikov Main Geophysical Observatory, St.Petersburg, Russia:

Dr. Vladimir M. KATTSOV

### Appendix 3. Draft of the monograph Contents. Version 5, 26 October 2005

Ola M. Johannessen1), Vladimir A. Volkov3), Lasse H. Pettersson1), Helge Drange1),

Vladimir S. Maderich4), Ivan A. Neelov3/5), Sven P. Nielsen6), Leonid P. Bobylev3),

Andrey V. Stepanov7) Mark J. Zheleznyak4), Youngi Gao1) and Viktor P. Tishkov7)

Radioactivity and Pollution Spreading in the Arctic Ocean:

Observations, Modelling and Simulations

First Draft 1 June 2006

Final Manuscript 31 December 2006

PRAXIS – Springer  2007

Ola M. Johannessen1), Vladimir A. Volkov3), Lasse H. Pettersson1), Helge Drange1),

Vladimir S. Maderich4), Ivan A. Neelov3/5), Sven P. Nielsen6), Leonid P. Bobylev3),

Andrey V. Stepanov7) Mark J. Zheleznyak4), Youngi Gao1) and Viktor P. Tishkov7)

Radioactivity and Pollution Spreading in the Arctic Ocean:

Observations, Modelling and Simulations

1)Mohn Svendrup Center and Nansen Environmental and Remote Sensing Center,

Edvard Griegsvei, 3a, N-5059 Bergen, Norway;

2)Geophysical Institute University of Bergen,

Edvard Griegsvei, 3a, N-5059 Bergen, Norway;

3)Nansen International Environmental and Remote Sensing Centre,

26/28 Bolshaya Monetnaya Str., 197061 St. Petersburg, Russia;

4)Institute of Mathematical Machines and System Problems,

42 Glushkov Pr., 03187 Kiev, Ukraine

5)Arctic and Antarctic Research Institute,

38 Beringa Str., 199397 St. Petersburg, Russia

6)RISØ National Laboratory,

Frederiksborgvej 399, Postboks 49, 4000 Roskilde, Denmark;

7)V.G.Khlopin Radium Institute,

2-nd Murinski Av., 28, 194021 St. Petersburg, Russia;

PRAXIS – Shpringer  2007

# Contributing authors

| Kirill L.Bobylev | V.G.Khlopin Radium Institute, 2-nd Murinski Av., 28, 194021 St. Petersburg, Russia; |
| --- | --- |
| Natalya N.Dziuba | Institute of Mathematical Machines and System Problems, 42 Glushkov Pr., 03187 Kiev, Ukraine; |
| Vladimir I.Koshebutsky | Institute of Mathematical Machines and System Problems, 42 Glushkov Pr., 03187 Kiev, Ukraine; |
| Vadim Plekhov | V.G.Khlopin Radium Institute, 2-nd Murinski Av., 28, 194021 St. Petersburg, Russia; |
| Lars Otto Reiersen (TBD) | Arctic Monitoring And Assessment Program (AMAP) Secretariat, Strømsveien 96, P.O. Box 8100 Dep. 0032 Oslo Norway; |
| Per Strand or Morten Sickel (TBD) | Norwegian Radiation Protection Authority, Postboks 55, 1332 Østeraas, Norway; |
| Dr. G. Ilyin | MMBI, Murmansk, Russia |
| Dr. Konoplev Alexey | SPA TAYPHOON Russian Hydromet, Obninsk, Russia |

CONTENTS

First Draft 1 June 2006

Final Manuscript 31 December 2006

Draft

# Preface (Responsible - Ola M. Johannessen, Vladimir A. Volkov)                        1.06.

# Acknowledgment (Responsible - Ola M. Johannessen, Vladimir A. Volkov)    1.06

# List of figures

# List of tables

# List of plates

# Acronyms and abbreviations

# Introduction (Responsible - Ola M. Johannessen, Vladimir A. Volkov)            1.06

# The problem of the radionuclide contamination in the Arctic and methodology of study (Responsible -Vladimir A. Volkov)                  1.04

# 1.1. Sources of the artificial radionuclides contamination in the Arctic

# (AndreyV. Stepanov,  Viktor P. Tishkov et al,  Lars Otto Reiersen)      rough draft 20.10.05,      Volkov to send to LOR 1.01.2006

# read and edited by LOR 15.2.2006

# Introduction

# 1.1.1. Primary and secondary sources of radionuclides contamination of the ecosystems

# 1.1.2. Main sources, composition and a transfer pathways of the artificial radionuclides in the Arctic

# 1.2. Geographical description of the region of study            rough draft 1.04.06

# (Vladimir A. Volkov, Ola M. Johannessen)                                                                           ,

# 1.2.1. General description, division into districts   VV&OMJ

# 1.2.2. Ob’ & Yenisey river basin       AS                                       rough draft 31.12.05

# 1.2.3. Kara Sea region           VV

# 1.2.4. North Atlantic and Arctic Ocean  VV & OMJ

# 1.3. Radioecological monitoring and modelling             rough draft 31.12.05

# (Vladimir A. Volkov, Andrey V. Stepanov, Mark J. Zheleznyak)

# 1.3.1. Main principles of a radioecological monitoring  AS

# 1.3.2. Modelling of a radioactive contamination      MZ

# 1.3.3. Need for integrating Geographical Information System – GIS   AS&VV

# 1.4. Generic Model System (GMS) as a new tool for an assessment of radioactive spreading (Vladimir S. Maderich, Vladimir A. Volkov, Helge Drange)

# rough draft VM to be send to HD  31.12.05

# HD read and edit 1.02.06

# 1.4.1. Need for a GMS

# 1.4.2. Concept of the GMS

# Geographical Information System (GIS) as a basis for the radioactivity study

# (Responsible – Andrey V. Stepanov, Vladimir A. Volkov)                              1.04

# VV read and edit to send to SN    1.03.06

# SN edit                                          1.04.06

# Introduction

# 2.1. RADARC GIS description

# (Andrey V. Stepanov)                                                                                               31.12.05

# 2.1.1. GIS basics and tools

# 2.1.2. Base cartographic data sets

# 2.2. Data description and analysis using GIS

# (Andrey V. Stepanov)                                                                                             31.12.05

# 2.2.1. Environmental data

# (Vladimir A. Volkov, Andrey V. Stepanov, Vadim Plekhov)                                  31.12.05

# 2.2.2. Environmental data for radionuclide sources

# (Andrey V. Stepanov, Sven P. Nielsen)                                                                 31.12.05

# 2.2.3. Radiation pollution data

# (Andrey V. Stepanov, Viktor P. Tishkov, Sven P. Nielsen)                                   31.12.05

# Descriptions of Generic Model System (GMS)

# (Responsible - Mark J. Zheleznyak, Helge Drange)                                   1.04

# MZ read and edit to send to HD    1.03.06

# HD edit                                          1.04.06

# Introduction

# 3.1. River and estuary of Ob’ & Yenisey modelling

# (Responsible – Mark J. Zheleznyak)                                             1.02.06

# Introduction

# 3.1.1. One-dimensional model for the simulation of the transport of radionuclides in the river system – RIVTOX

# (Mark J. Zheleznyak et al.)

# 3.1.2. Numerical model for three-dimensional dispersion simulation of radionuclides in stratified water bodies – THREETOX

# (Vladimir S. Maderich et al.)

3.1.2. Models validation results

(Vladimir S. Maderich, Mark J. Zheleznyak et al.)

# Conclusion

# 3.2. Shelf Sea modelling of the Kara Sea                                      1.03.06

# (Responsible – Ivan A. Neelov)

# Introduction

# (Vladimir A. Volkov, Ivan A. Neelov)                                                         1.02.06

# 3.2.1. General model description

# (Ivan A. Neelov)                                                                                        1.02.06

# 3.2.2. Radionuclide tracer module

# (Ivan A. Neelov)                                                                                       1.02.06

# 3.2.3. Model validation results

# (Vladimir A. Volkov, Ivan A. Neelov)                                                        1.03.06

# Conclusion

# 3.3. Open Ocean / North Atlantic modelling                                1.03.06

# (Responsible – Lasse H. Pettersson)

# 3.3.1. General model description

# (Helge Drange, Youngi Gao)

# 3.3.2. Radionuclide tracer module (Helge Drange, Youngi Gao)

# 3.3.3. Model validation results (Helge Drange, Youngi Gao)

# 3.4. Architecture of the Generic Modelling System                                      1.03.06

# (Responsible – Helge Drange, Vladimir S. Maderich, Ivan A. Neelov)

# 3.3.1. GMS structure and data streams

# 3.3.2. Modelling management

# Study of the potential radioactive spreading in the Arctic using GMS (Responsible - Vladimir S. Maderich, )

# VM read and edit to send to SN    1.04.06

# SN edit                                          1.05.06

Introduction

4.1. Reconstruction of past contamination of Arctic by nuclear plants       1.03.06.

# 4.1.1. River & estuary transport and dilution of radioactive waste and dissolved pollutants from the rivers to the Kara Sea (Vladimir S. Maderich)

# 4.1.2. Transport and dilution of radioactive waste and dissolved pollutants in the Kara Sea (Ivan Neelov)

# 4.1.3. Transport and dilution of radioactive waste and dissolved pollutants from the Sellafield (Helge Drange, Youngi Gao)

# 4.1.4. Total transport and dilution of radioactive waste and dissolved pollutants from all sources include atmospheric fallout (Helge Drange, Youngi Gao)

# 4.2. Scenario for potential radioactive releases                                              1.03.06

# Introduction (Mark J. Zheleznyak, Sven Nielsen, Andrey Stepanov)

# 4.2.1. “Mayak” scenario (Mark J. Zheleznyak, Sven Nielsen, Andrey Stepanov)

# 4.2.2. “Kraznoyarsk” scenario (Mark J. Zheleznyak, Sven Nielsen, Andrey Stepanov)

# 4.2.3. “Tomsk” scenario (Mark J. Zheleznyak, Sven Nielsen, Andrey Stepanov)

# 4.2.4. “Sellafield” scenario (Sven Nielsen)

# 4.2.5. “Atmospheric fallout” scenario (Sven Nielsen)

# 4.2.6. “CO2 doubling” scenario (Helge Drange)

# 4.3. Assessments of potential accidental releases for the 21st century    1.03.06

# 4.3.1. Potential radioactive contamination from the rivers to the Kara Sea (Vladimir S. Maderich, Mark J. Zheleznyak)

# 4.3.2. Potential radioactive contamination in the Kara Sea (Ivan Neelov)

# 4.3.3. Potential radioactive contamination from the Sellafield (Helge Drange, Youngi Gao)

# 4.3.4. Total potential influence of all radioactive sources including atmospheric fallout (Helge Drange, Youngi Gao)

# 4.4. Transport of radioactivity in the Arctic and possible impact of climate change (Helge Drange, Youngi Gao)                                                          1.03.06

# 4.4.1. Accidental scenarios under present climatology (period 1970-2000)

# (Helge Drange, Youngi Gao)

# 4.4.2. Accidental scenarios under the global warming (2´CO2) (period 2084-2114) (Helge Drange, Youngi Gao)

# 4.5. Potential transport of radioactivity from submarine accidents

# (Vladimir S. Maderich, Helge Drange, Youngi Gao)                                  1.03.06

# Methodology of GMS application for simulation of non-radioactive pollutants spreading in the Arctic environment

# (Responsible – Mark Zhelesnyak)

# MZ read and edit to send to LOR    1.05.06

# LOR edit                                          1.06.06

5.1 Overview of aquatic marine environment pollution by the non-radioactive contaminants

LOR, Ilyin, Konoplev,  MZ                                                                         15.04.06

# 5.1.1. Siberian rivers pollution (only Ob’ and Yenisey, AARI publications, NIERSC)

# 5.1.2. Russian Arctic coastal areas pollution

# 5.1.3. Pollution of the European Arctic Coastal Areas

# 5.1.4. Polar Ocean pollution

# 5.1.4. Main sources of the marine Arctic environment pollution

# (AMAP input, Access to the existing DB and reports on Arctic and Siberian river pollution via NIERSC and NERSC)

5.2 Basic approaches for the simulations of the pollutants in the river and marine environment

Mark Zhelesnyak, Vladimir Maderich                                               15.04.06

# 5.2.1. Basic equations

# 5.2.2. POP modelling

# 5.2.3. Petroleum hydrocarbons modelling

# 5.2.4 PCB modelling

# 5.2.5 A brief overview of the existing models/codes

5.3 Application of River and Estuary models of GMS                           15.04.06

# 5.3.1. Application of the river model RIVTOX    MZ

# 5.3.2. . Application of the estuary model THREETOX    VM

5.4 Application of the Kara Sea model

Ivan Neelov                                                                                            15.04.06

5.5 Extension of the Arctic / North Atlantic model                          15.04.06

Youngi Gao

5.6. Example of the GSM applications for the non-radioactive pollutants in Arctic environment

Youngi Gao, Helge Drange,  Vladimir Maderich,                                15.04.06

# Assessment – input to risk management

# (Responsible – Sven Nielsen)                    SN write and send to Viktor Tishkov    1.04.06

# VT comments& adds                             1.05.06

6.1 Introduction

# 6.1.1. Assessment purpose, end points and philosophy

# 6.1.2. Source term characteristics

# 6.1.3. Environmental characteristics

# 6.1.4. Time frames and societal assumptions

6.2 Source terms and environmental systems

# 6.2.1. Source terms

# 6.2.2. Geosphere

# 6.2.3. Biosphere

6.3 Development and justification of scenarios

# 6.3.1. Source term scenarios

# 6.3.2. Climate scenarios

6.4 Formulation and implementation of dose models

# 6.4.1. Model features and processes

# 6.4.2. Model validation

6.5 Results

# 6.5.1. Doses along rivers

# 6.5.2. Doses in coastal regions

6.6 Conclusions

# Conclusion

# (Ola M. Johannessen, Vladimir A. Volkov)                                                     1.06

# Appendix A Units of a radioactivity

# Appendix B (TBD)

# Appendix C (TBD)

# References

# Index

# Glossary

Radioactivity and Pollution Spreading in the Arctic Ocean:

Observations, Modelling and Simulations

# Volume of manuscript

| Preface (incl.: List of figures, List of tables, List of plates, Acronyms and abbreviations) | 5 pp. = 1% |
| --- | --- |
| Introduction | 10 pp. = 2% |
| - The problem of the radionuclide contamination in the Arctic and methodology of study | 60 pp. = 11% |
| 1.1. Sources of the artificial radionuclides contamination in the Arctic | 20 |
| 1.2. Geographical description of the region of study | 20 |
| 1.3. Radioecological monitoring and modelling | 10 |
| 1.4. Generic Modelling System (GMS) as a new tool for an assessment of radioactive spreading | 10 |
| - Geographical Information System (GIS) as a basis for the radioactivity distribution study | 60 pp. = 11% |
| Introduction | 10 |
| 2.1. RADARC GIS description | 25 |
| 2.2. Data description and analysis using GIS | 25 |
| - Descriptions of Generic Model System (GMS) | 120 pp. = 23% |
| 3.1. Descriptions of Generic Model System (GMS) | 40 |
| 3.2. Shelf Sea modelling of the Kara Sea | 30 |
| 3.3. Open Ocean / North Atlantic modelling | 35 |
| 3.4. Architecture of the Generic Modelling System | 15 |
| - Study of the potential radioactive spreading in the Arctic using GMS | 135 pp.= 25% |
| Introduction | 5 |
| 4.1. Reconstruction of past contamination of Arctic by nuclear plants | 25 |
| 4.2. Scenario for potential radioactive releases | 25 |
| 4.3. Assessments of potential accidental releases for the 21st century | 25 |
| 4.4. Transport of radioactivity in the Arctic and possible impact of climate change | 40 |
| 4.5. Potential transport of radioactivity from sunken submarines – a case study | 15 |
| - Methodology of GMS application for simulation of non-radioactive pollutants spreading in the Arctic environment | 30 pp.= 6% |
| 5.1 Overview of aquatic marine environment pollution by the non-radioactive contaminants | 8 |
| 5.2 Basic approaches for the simulations of the pollutants in the river and marine environment | 6 |
| 5.3 Extension of River and Estuary models of GMS | 9 |
| 5.4 Extension of the Kara Sea model | 8 |
| 5.5 Extension of the Arctic / North Atlantic model | 9 |
| 5.6. Example of the GSM applications for the non-radioactive pollutants in Arctic environment | 15 |
| - Assessment – input to risk management | 55 pp. = 10% |
| 6.1 Introduction | 5 |
| 6.2 Source terms and environmental systems | 10 |
| 6.3 Development and justification of scenarios | 10 |
| 6.4 Formulation and implementation of dose models | 10 |
| 6.5 Results | 15 |
| 6.6 Conclusions | 5 |
| Conclusion | 10 pp. = 2% |
| Appendix A Appendix B Appendix C | 20 pp. = 4% |
| References | 10 pp. = 2% |
| Index | 5 pp. = 1% |
| Glossary | 10 pp. = 2% |
| TOTAL | 530 pp.= 100% |

### Appendix 4. Agenda of the GMS application Thematic Expert Workshop

Meeting Agenda

Project full title: Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century

Project acronym: GMS application

Proposal/Contract no: PL012002

:

“Demonstration and promotion of GMS use for monitoring of different pollutants in the Arctic”

Venue:	Nansen International Environmental and Remote Sensing Centre (NIERSC), St. Petersburg, Russia

Date:	Thursday, 30 May 2006

Time:	10:00 – 18:00

Agenda

| 10:00 – 10:05 | Opening and welcome |
| --- | --- |
|  | Dr. Leonid P. Bobylev, NIERSC |
| 10:05 – 10:20 | Introduction. Meeting objectives |
|  | Dr. Vladimir A. Volkov, NIERSC |
|  | Scientific session: Generic Model System (GMS) as a new tool for an assessment of a pollutants spreading in the Arctic environment. |
|  | Chairman: Dr. Vladimir A. Volkov, NIERSC |
| 10:20 – 11:20 | Architecture of the Generic Modelling System. River and estuary of Ob’ & Yenisey modelling |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| 11:20 – 11:40 | Shelf Sea modelling of the Kara Sea |
|  | Dr. Ivan A. Neelov, AARI |
| 11:40 – 12:20 | Open Ocean / North Atlantic modelling |
|  | Mr. Lasse H. Pettersson, NERSC |
| 12:20 – 12:50 | Coffee Break |
| 12:50 – 13:30 | Overview of aquatic marine environment pollution by the non-radioactive contaminants |
|  | Dr. Gennady V. Ilyin, MMBI |
| 13:30 – 14:00 | Persistent toxic substances (POPs+heavy metals) in Arctic ecosystems |
|  | Dr. Alexey Konoplev, ”Tayphoon” |
| 14:00 – 14:40 | Demonstration of an extended the GMS applications for the management of environmental risks associated with the industrial anthropogenic non-radioactive waste: persistent organic pollutants (POPs), industrial chemicals (PCP´s) and heavy metals in the Arctic regions |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| 14:40 – 15:300 | Lunch |
| 15:30 – 18:00 | Round Table: GMS application for the management of environmental risks associated with man-made changes and industrial wastes in the Arctic region |
|  | Chairman: Dr. Mark I. Zheleznyak, UCEWP |
|  | Numerical modelling of the water quality and biogeochemical properties of the Black Sea |
|  | Dr. Sergey KONOVALOV, MHI |
|  | Establishment and maintenance of the project web site |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| (16:30 – 17:00) | Coffee Break |
| 18:00 | The End |

LIST OF PARTICIPANTS

Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev, Ukraine:

Dr. Mark I. ZHELEZNYAK

Nansen Environmental and Remote Sensing Center (NERSC), Bergen, Norway:

Prof. Ola M. JOHANNESSEN

Mr. Lasse H. PETTERSSON

Nansen International Environmental and Remote Sensing Centre (NIERSC), St. Petersburg, Russia:

Dr. Leonid P. BOBYLEV

Dr. Vladimir A. VOLKOV

Dr. Ivan A. NEELOV

Invited persons

Arctic and Antarctic Research Institute (AARI), St.Petersburg, Russia:

Dr. Vitaly M. SMAGIN

Marine Hydrophisical Institute,  Sebastopol, Ukraine

Dr. Sergey KONOVALOV

Murmansk Marine Biological Institute (MMBI), Murmansk, Russia:

Dr. Gennady V. ILYIN

Khlopin Radium Institute (KRI), St. Petersburg, Russia:

Mr. Andrey I. STEPANOV

Ms. Irina M. SAVELIEVA

SPA ”Tayphoon”, Roshydromet, Obninsk, Russia:

Dr. Alexey KONOPLEV

St. Petersburg Department of the State Oceanographical Institute (SPbSOI) Roshydromet, St.Petersburg, Russia

Dr. Eugeny A. ZAKHARCHUK

Mr. Konstantin G. SMIRNOV

Ms. Natalya A. TIKHONOVA

St. Petersburg State University (SPbSU), Department of geography and geoecology, St.Petersburg, Russia

Prof. Viktor R. FOUKS

Mr. Alexei  KOLDUNOV

Northern Water Problem Institute (NWPI), Petrozavodsk, Russia:

Prof. Nikolay N. FILATOV

Shelf Geological Environment Centre of the Russian Federal State Enterprise ”Sevmorgeo”, St.Petersburg, Russia

Dr. Alexander D. KRASNIUK

Scientific Research Center of Ecological Safety of Russia Academy of Sciences (SRCES RAS), St. Petersburg, Russia

Dr. Viktor M. PITULKO

### Appendix 5. Agenda of the GMS application Final Meeting

Meeting Agenda

Project full title: Generic Model Simulations (GMS) of spreading of marine pollutants in the Arctic environment during the 21st Century

Project acronym: GMS application

Proposal/Contract no.: PL012002

Final meeting

Venue:	Nansen International Environmental and Remote Sensing Centre (NIERSC), St. Petersburg, Russia

Date:	Thursday, 26 October 2006

Time:	10:00 – 15:00

| 10:00 – 10:05 | Opening and welcome |
| --- | --- |
|  | Dr. Leonid P.Bobylev, NIERSC |
| 10:05 – 10:30 | ###### Introduction. Meeting objectives |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 10:30 – 11:00 | Technical session: Preparation of the reporting materials |
| 11:00 – 11:40 | Status of the project web-site and Technical Report on assessment and demonstration of the extended GMS applications |
|  | Dr. Mark I. Zheleznyak, UCEWP |
| 11:00 – 11:40 | ###### Status of the RADARC Monograph and preparation of the Final Report |
|  | Dr. Vladimir A. Volkov, NIERSC |
| 11:40 – 12:10 | Coffee Break |
| 12:10 – 13:30 | ###### Project management, financial reporting |
|  | Mr. Lasse H. Pettersson, NERSC |
| 13:30 – 14:30 | Lunch |
| 14:30 – 15:30 | Round Table: perspectives of the development of the “GMS application for the management of environmental risks associated with man-made changes and industrial wastes in the Arctic region” under FP7 |
|  | Chairman: Dr. Leonid P.Bobylev |
| 15:30 | Adjourn |

LIST OF PARTICIPANTS

Ukrainian Center of Environmental and Water Projects (UCEWP), Kiev, Ukraine:

Dr. Mark I. ZHELEZNYAK

Nansen Environmental and Remote Sensing Center (NERSC), Bergen, Norway:

Prof. Ola M. JOHANNESSEN

Mr. Lasse H. PETTERSSON

Nansen International Environmental and Remote Sensing Centre (NIERSC), St. Petersburg, Russia:

Dr. Leonid P. BOBYLEV

Dr. Vladimir A. VOLKOV