NETSSAF

Deliverable 68

PUBLISHABLE EXECUTIVE SUMMARY

Project Summary

Without a sharp acceleration in the rate of progress, the world will miss the Millennium

Development Goals (MDG) sanitation target by half a billion people. For instance, in sub-Saharan

Africa almost two-thirds of the population (64%) lack adequate access to excreta disposal facilities.

In African countries the sanitation coverage varies from 84% in urban areas to 45% in rural areas.

To achieve the year 2015 goal for urban water supply coverage an additional 210 million (194 in

rural areas) people over the next 15 years will have to be provided with service.

NETSSAF aims to bring together the most relevant stakeholders in the field of sustainable

sanitation in Sub-Saharan African and Europe, and to promote international cooperation

between research organisations, associations, universities, and social and governmental

stakeholders in a European and Sub-Saharan African context, focussed in particular in the West

African countries.

A sustainable sanitation expert and research co-ordination platform, and an expertise network, will

be established in order to co-ordinate, assess and guide suitable research and strategic activities

with the aim of identifying best practices, gaps in knowledge and barriers to further execution, and

to propose directions for futures research.

The main aim of NETSSAF is to develop a variety of innovative, adaptable and replicable

approaches to sustainable sanitation, integrating appropriate low-cost technologies with

community-based management and their relevant governance, institutional frameworks and socioeconomic

constraints. The main outcome will be the development of a Participative Multistakeholder

Sanitation Management Support Tool aimed for the end-users to be able to apply

large-scale sanitation concepts and technologies adapted to the different conditions prevailing in

Africa.

Project objectives

The specific strategic objectives of the NETSSAF are:

1.

To prepare the technical, social and policy bases for the future large-scale implementation of

low cost technologies for sustainable sanitation in West Africa.

2.

To encourage the establishment of permanent communication links between key

actors/stakeholders in West Africa, promoting the know-how exchange and expertise in relation

to innovative sanitation approaches for large-scale implementation.

3.

To co-ordinate current R&D activities in West Africa in order to promote cooperation and avoid

duplication of efforts, taking into account traditional knowledge and innovation technologies.

4.

To define, initiate and guide future R&D activities on West African level by mapping current

research and forming research clusters in order to fulfil the scientific and technological needs

for the further large-scale implementation of innovative and feasible sanitation concepts.

5.

To identify a variety of innovative, adaptable and replicable approaches to sustainable

sanitation in Africa, aiming at integrating appropriate low cost technologies in the context of

community based management.

6.

To disseminate the results, through a Sustainable Sanitation Extension Programme, designed

specially to reach the local communities and to build capacity of authorities for future

implementation and dissemination, developing institutional mechanisms for deployment of

extension strategy.

The scientific and technological objectives of the NETSSAF Co-ordination Action are:

1.

To evaluate and classify a group of existent rural and peri-urban settlements with no access to

improved sanitation in West Africa, selecting a set of typical cases.

2.

To review and discuss different sanitation technologies, by using experiences of

implementation in West Africa and other developing regions.

Page 3of 15

NETSSAF

Deliverable 68

3.

To identify suitable sanitation technologies for each typical case, according to the

characteristics and needs identified regarding technical, social, economical, environmental,

institutional and legal aspects.

4.

To identify the technical requirements (sourcing, logistics, installation, operation and

maintenance) and non-technical requirements (human, financial, economical, environmental,

legal and institutional aspects) of each technology selected for large-scale implementation.

5.

To identify, map and contact the existent regional suppliers of the technological requirements

of each sanitation technology selected, in order to prepare a West African database of

Sanitation Supply.

6.

To identify and map the current sanitation implementation activities and their actors in West

African, in order to prepare a West African database of potential technology transfer

associations and groups, which will participate in a future massive implementation.

7.

To propose and design an Adapted Sustainable Sanitation Management System, to support

decision makers and beneficiaries in identifying feasible sanitation alternatives for large-scale

implementation by using low-cost technologies adapted to the different physical and socioeconomic

conditions prevailing in West Africa.

8.

To develop adequate strategies for large-scale implementation of low-cost sanitation

technologies in peri-urban and rural areas, focusing on their relevant governance, institutional

frameworks and socio-economical aspects in the African context.

Contractors list

The contractors involved in the project are shown in the following list:

Table 1: Contractors list

Partic.

Role*

Partic.

number

Participant organisation name Participant

short name

Country Month

project

Month

project

CO 1 Technologie Transfer Zentrum Bremerhaven TTZ Germany 1 30

CR 2 Technische Universität Hamburg-Harburg TUHH Germany 1 30

CR 3 Le Centre Régional pour l'Eau Potable et

l'Assainissement

CREPA Burkina Faso 1 30

CR 4 BioAzul BIOAZUL Spain 1 30

CR 5 Bureau Ouest-Afraicain d´Appui Organisationnel et

de Technologies Appropriées

BOATA Mali 1 30

CR 6 International Ecological Engineering Society IEES Switzerland 1 30

CR 8 International Water Association IWA United

Kingdom

1 30

CR 9 Université Abobo-Adjamé UAA Côte d’Ivoire 1 30

CR 10 Sveriges Lantbruksuniversitet SLU Sweden 1 30

CR 11 Maire de Matam MTM Senegal 1 30

CR 12 Eidgenössische Anstalt für Wasserversorgung,

Abwasserreinigung und Gewässerschutz

EAWAG Switzerland 1 30

CR 13 Commune de Bobo Diolasso Ville-de-SYA Burkina Faso 1 30

CR 14 EcoSan Club Austria ESCA Austria 1 30

CR 15 Kwame Nkrumah University of Science and

Technology

KNUST Ghana 1 30

CR 16 University of Leeds ULeeds United

Kingdom

1 30

CR 17 Université de Ouagadougou-CEPAPE CEPAPE Burkina Faso 1 30

CR 18 Stockholm Environment Institute SEI Sweden 1 30

CR 19 Deutsche Gesellschaft für Technische

Zusammenarbeit

GTZ Germany 1 30

CR 20 Tampere University of Technology TUT Finland 1 30

*CO = Coordinator / CR = Contractor

Page 4of 15

NETSSAF Deliverable 68

The contact details of the co-ordinator

Mirko Hänel

Verein zur Foerderung des Technologietransfers and der Hochschule Bremerhaven E.V

UMWELT Institut -TTZ

An der Karlstadt 6

Bremerhaven, 27568, Germany

Phone: +49-(0)471-4832-180

Fax: +49-(0)471-4832-129

e-mail: mhaenel@ttz-bremerhaven.de

Work performed, results achieved so far and expected end results

The main aims of the coordination action NETSSAF are: to develop a variety of innovative,

adaptable and replicable approaches to sustainable sanitation, integrating appropriate low cost

technologies with community based management and their relevant governance, institutional

frameworks and socio economic constrains, and to coordinate and integrate the current scientific

research, technological innovation and execution activities, creating synergies to support large-

scale implementation of sustainable sanitation systems in peri-urban and rural areas, in order to

propose feasible solutions for the achievement of the Sanitation MDG in Africa.

In order to achieve the above mentioned objectives, the work has been organised in the following

work packages (WP):

·

WP1: Definition of evaluation criteria

·

WP2: Regional evaluation and classification in typical settlements

·

WP3: Sanitation technologies Assessment

·

WP4: Identification of potential sustainable sanitation technologies

·

WP5: Regional identification of possible sanitation providers and actors

·

WP6: Adapted sustainable sanitation management system

·

WP7: Coordination of research, technology, development and cooperation

·

WP8: Sustainable sanitation extension and dissemination programme

·

WP9: Project management

During the 30 months of the project duration, reporting from the 1st June 2006 until the 30th

November 2008, all project tasks foreseen in the DoW have been performed by project partners.

As a first step it was defined the necessary evaluation criteria for the activities to be performed

during the whole project. The three tasks of WP1 run the four first months to define: criteria for the

identification of key actors (D02), criteria for the evaluation and classification of peri-urban and

rural settlements with no access to improved sanitation (D03) and criteria for the evaluation and

classification of conventional and innovative low cost sanitation technologies (D 04). In parallel

within task 2.1 of WP2, 66 typical settlements with no access to appropriate sanitation facilities

were identified across the West African region, as potential study cases where further NETSSAF

activities are recommended (D05).

Based on task 1.3 and task 2.1 results, a data base compiling key actors and external stakeholders

in the West African region (D13) and the regional assessment of rural and peri-urban settlements

(D15) were developed in task 2.2. Following the work, the typical settlements with lack of improved

sanitation identified were screened and organised into three regions (D17) within task 2.3. Finally,

11 sites located in six NETSSAF targeted countries were selected as showing typical

characteristics, relevant for the designing and planning of sustainable sanitation systems in task

2.4: Molodo, Macina, Vy, Loumbila, Matam, Anyama, Songon, Ashakoko, Eduaden, Dedesua and

Rosso. Four rural and seven peri-urban sites were chosen to reflect and represent the range of

variable categories, with clear distinctions in geophysical, economical, social and administrative

factors. The work carried out within WP2 set the grounds for WP4, especially the mentioned D24.

The work of WP3 was devoted to the systematization, characterization, and assessment of

sanitation systems and technology configurations. Seven main sanitation systems were developed

Page 5of 15

NETSSAF Deliverable 68

by project partners, using wet/dry as main key criteria for subdividing the systems as well as

various degrees of separating waste flow streams. A description of feasible technology

components and configurations were established according to these sanitation systems and

described with regard to their key features and characteristics. The individual technologies were

then comparatively assessed using criteria defined in WP1 (D22&23).

The major objective of WP4 was the development of a conceptual approach for supporting

decisions in the field of sanitation on a large scale, identifying at the same time the needed

technical and non-technical requirements for the large scale implementation in West Africa of

sustainable sanitation systems. Since the meeting in Bamako, the work within WP4 was focused

on the development of guidelines and principles of the decision making process, providing the

conceptual basis for the decision making tool, as an objective in WP 6. The work in the three tasks

belonging to WP4 was rearranged leading in the merging of task 4.2 and 4.3, as well as the

merging of some deliverables. Deliverables 33, 36, and 39 were submitted as one deliverable as

the tasks go hand in hand and do not merit from being separated out and delivered separately.

Within task 4.2&4.3, a compilation of universally valid technical and non-technical requirements for

the large-scale implementation of sustainable sanitation concepts in West Africa was carried out.

Those requirements have given a feed back to task 4.1 for the selection of suitable sanitation

concepts (D33&36&39).

Within WP5, two questionnaires were prepared for gathering the data regarding the suppliers of

technical components and services in the wastewater and sanitation field, as well as the

organizations which provide support in different fields, and the organizations were mapped during

October and November 2007. Within task 5.3 (WP5), the Yellow Pages of Sanitation and

Wastewater Treatment Solutions for West Africa (D48) was developed and made available in

internet at http://www.yellowpagesofsanitation.com/, whose main aim is to encourage and promote

small and medium enterprises in the business of sanitation in Africa, improving their market

performance thus generating extra profits and empowering the local economies. This data base of

key capacities for Africa is available for the sanitation planners, authorities and individuals involved

in sanitation planning and implementation. It includes information on 160 companies offering

sanitation products and services (D44) and on 198 organizations offering sanitation services and

generally specialized in the non-technical aspects of sanitation in West Africa (D45). The data base

offers the users the possibility to: register as a company/organisation/expert and to search for

companies and organisations involved in sanitation related activities in all countries located in

Africa.

WP6 aims to design and produce two valuable tools for authority and institutional capacity building

in the West African countries, by making use of the information already gathered since the

beginning of the project. These two tools are planed to guide the stakeholders from the decision

making and planning to the installation, operation, monitoring, management and exploitation of the

most the appropriate sanitation technologies/systems. Within task 6.1, a software presenting the

“Sanitation Participative Planning Approach” (SPPA) elaborated within WP4, was developed and is

freely available in the NETSSAF web page. An Alpha version was submitted in April 2008 (D43)

and a beta version (D55) in September 2008. This tutorial for sustainable sanitation planning is a

ready source of information for decision makers and individuals involved in setting up municipal

wastewater systems and concepts for management of excreta in communities in West Africa.

Within task 6.2, a guideline, condensing the NETSSAF SPPA, has been prepared to reach those

stakeholders without access to internet (D46). This manual is aimed at planners, engineers,

decision-makers and medical practitioners concerned with sanitation, with two main objectives:

provide them with guidelines on how to carry out sanitation planning, and convince them of the

benefits of adopting a participatory approach in the planning process.

Within task 7.1, which runs from the first month of the project, a review of current research

activities within (D06) and outside (D10) the NETSSAF consortium in the field of sustainable

sanitation was carried out. D06 showed the deep involvement of the members in multiple activities

in pure and applied research as well as implementation and networking actions in the field of

sustainable sanitation and related fields. D10 results enabled the identification of any duplication

Page 6of 15

NETSSAF Deliverable 68

of research activities in the West African region outside the consortium. Two updates of D10 on

current research outside the NETSSAF consortium (D29 and D47) were prepared.

In task 7.2, research activities performed by West African and European research institutions

working on sustainable sanitation in West Africa were clustered based on the processes being

under research and their characteristics. The information was compiled in two reports, the first

formation of research cluster report (D16) and the Research Cluster Report (D53), which included

more information about recent additions to research cluster. The inclusion of new members in the

clusters will enhance and support the coordination efforts in sustainable sanitation in West Africa.

In addition, the Public Library was developed within task 7.3, whose main objective was to provide

information on Sustainable Sanitation in order to facilitate its implementation in West Africa. It

contains relevant articles, papers and reports that have been written under NETSSAF framework,

as well as a compilation of relevant literature of members of the consortium and external

researchers and a section of useful links. The library has been updated during the whole duration

of the project.

The work carried out in task 7.1 and 7.2 fed task 7.4, which has yielded reports on Network

solidification (D51) and Recommendations for future research, technology development and

cooperation (D52). The major conclusion of D52 was that existing knowledge on low-cost

sanitation needed to be disseminated much more widely in the NETSSAF countries (and beyond).

The report identified the need for local West African R&D to adapt proven low-cost sanitation

systems to the local context at pilot/demonstration-scale prior to large-scale implementation. The

principal research area identified for research for beyond 2015 is the development of affordable

low-cost EcoSan systems for high-density peri-urban areas.

The specific results derived from the work performed in the whole project duration are presented in

the following table.

Table 2. Workpackages of the NETSSAF project

WP no. Workpackage

title contractor

Short name

IEES

Lead

Start month

1

End month

4

Deliverable

number

D02, D03, D04

Status

üWP1

Definition of

evaluation

criteria

WP2

Regional

evaluation and

classification in

typical

settlements

BOATA 1 12 D05, D13, D15

D17, D24

ü

WP3

Sanitation

technologies

Assessment

EAWAG 3 12 D22&D23 ü

WP4

Identification of

potential

sustainable

sanitation

technologies

SEI 13 18 D27, D28, D32

D33&36&39

ü

WP5

Regional

identification of

possible

suppliers/actors

TTZ 15 21 D44, D45, D48 ü

WP6

Adapted

Sustainable

Sanitation

Management

System

TTZ 7 24 D43, D46, D55 ü

Page 7of 15

NETSSAF Deliverable 68

WP7

Coordination of

research,

technology,

development

and cooperation

IWA 1 30

D06, D10, D16

D29, D47, D51

D52 D53

ü

WP8

Sustainable

sanitation

extension and

dissemination

programme

CREPA 1 30

D07, D11, D12

D14, D25, D26

D31, D34, D35

D40, D49, D50

D59, D60, D61

D62, D63, D65

D66, D67, D70

D74, D75

ü

WP9 Project

management TTZ 1 30

D01, D08, D09

D18, D19, D20

D21, D30, D37

D38, D41, D42

D54, D56, D57

D58, D64, D68

D69, D71, D73

D76, D77

ü

Strong dissemination activities have been carried out within WP8 since the beginning of the project

in order to widespread to a major public the main outcomes of the project.

One of the main tools for the wide dissemination of the project and its results is the official project

website www.netssaf.net, corresponding to D07, launched in July 2006. It consists of a public

access site containing a description of the project, information about the objectives, partnership

and progress of the NETSSAF project, and a restricted area for the consortium in which all

important information, project deliverables and other documents are hung down. The website has

been updated during the whole duration of the project (D11, D26 and D40). After finalizing the

project, a special feature in the welcome page with a link to each WP has been included with the

chairman’s expectation, a summary of each session and a link to each presentation, all together

gathered in Minutes of the conference. The news and event section of the web page was removed,

a new section called NETSSAF in public was included, in which all the articles and publications

referred to NETSSAF are published.

In addition, an official logo of the project was developed and included in the webpage and all

dissemination materials produced in the NETSSAF project:

Fig. 1: NETSSAF Logo

A series of workshops took place to first capacitate local governments in sustainable sanitation

(task 8.2, D67) and introduce the necessity of sanitation system choice. In a next step

representatives of the local governments (task 8.1, D60), played an active role in the end-user

workshops. In both tasks, 14 workshops were organised by five partners in seven West African

countries as follows: BOATA (1 in Niger and 2 in Mali), CREPA (2 in Mauritania), Ville de Sya (2 in

Burkina Faso), UAA (2 in Côte d’Ivoire), MTM (2 in Senegal) and KNUST (3 in Ghana). This

strategy places local government as the key actors and moves away from the traditional way of

doing things, where local governments were more often seen as an institution that needs to be

informed and invited than as the primary responsible. Within task 8.1, the assessment of channels

of communication of local key actors and end users was analysed through the results of interviews

performed. The results were presented in the D25. In addition, a set of materials sensitive to end

users (awareness kit, D49) were prepared for the local workshops focused on rural communities

Page 8of 15

NETSSAF Deliverable 68

and end-users held in targeted regions across Africa, as well as the report on the Strategy of

dissemination and extension for end-users: bringing sustainable.

The educational programmes on Sustainable Sanitation at the West African Universities partners

of NETSSAF was reviewed and the ideas to strength these programmes were compiled in the

report on new specialised training activities within NETSSAF (D14) within task 8.3. In addition, the

reports Results of the strategies of cooperation in order to link and empower new and existing

specialised training activities (D34) which includes the results of three workshops organized in

Ivory Coast, Burkina Faso and Ghana, was successfully finished. The report Strategies of

cooperation in order to link and empower new and existing specialised training activities (D35),

presented activities needed in the short-term as well as longer term that could contribute to fulfilling

the aim of linking and empowering specialised training activities in West Africa.

Regarding the tools and activities for mass dissemination (task 8.4), the most important event

related to mass dissemination held in NETSSAF framework was the Final Conference “Pathways

towards Sustainable Sanitation in Africa” that took place from 24th to 27th September 2008 in

Ouagadougou, Burkina Faso. A special feature of the web page was created for the final

conference in French and English in order to present the event, giving the possibility of registering

participants, exhibitors and side events online, as well as the submission of papers.

Two promotional leaflets were developed in English and French (D12 and D62) mainly focus in the

final conference. 2000 exemplars in English and 1500 in French of the first leaflet were distributed.

The second included most relevant information on the Conference. 1500 hard copies in each

language were distributed amongst project partners. Downloadable versions are available in the

web of the project. In addition, a promotional poster has been developed for the wider promotion of

the Conference (D31). The poster is available in the web in English and French.

In addition, some NETSSAF results have been used for the production of different articles

published in conferences and specialised journals (D65 and D66).

Other dissemination activities were carried out, i.e. preparation and presentation of dissemination

material, attendance to conferences, seminars and meetings, and the introduction of the project to

relevant stakeholders and authorities. A more detailed explanation of the dissemination activities

carried out, as well as several routes for the exploitation actions expressed by project partners to

date regarding the results, are available in the Final Plan for Using and Disseminating the

Knowledge.

The management of the project (WP9) has been carried out in parallel to the coordination

activities, ensuring the correct coordination, communication and cooperation between the partners.

The consortium agreement was submitted as the first deliverable of the project (D01) by the

general coordinator, as well as the report on communication channels within the consortium (D38)

within task 9.1.

The five short project updates reports foreseen in the DoW in task 9.3 (D9, D18, D42, D54 and

D73) were prepared by the reporting coordinator to keep the consortium updated on all project

activities. Within task 9.3, all periodic and final reports were produced after each reporting period.

In addition, five local development reports were submitted (D08, D19, D41, D58 and D72) by the

local coordinator. The scientific coordinator prepared two scientific development reports (D30 and

D64) within task 9.2.

The NETSSAF project officially started the 1st June, 2006, and launched during the Kick-Off

Meeting in June 25th – 28th 2006, held at the facilities of the Swedish University of Agricultural

Sciences, Uppsala, Sweden. Since then, the project has been managed by the four coordinators,

TTZ (being the general and financial coordinator), TUHH (the scientific coordinator), CREPA (the

local coordinator) and BioAzul (the reporting coordinator). Two more official meetings took place

during the project, the mid term meeting organised by BOATA in Bamako, Mali, from the 21st to the

25th June, 2007, and the final meeting organised by CREPA in Ouagadougou, Burkina Faso, the

27th of September 2008 after the International Conference.

In addition to daily management activities, extraordinary activities were carried out during the 30

months of the project. Two ad-doc meetings were organised in Eschborn (22-23.02.07) and in

Page 9of 15

NETSSAF Deliverable 68

Ouagadougou (27.02-01.03.07) in order to review the activities performed in the project and to re-

orient the work of WP2, WP3 and WP8. The meetings were a great success, counting with the

participation of all the members of the team. As expected, the NETSSAF consortium reached a

consensus in the procedures to conclude the active activities and defined the path to follow in the

following work packages.

Table 3. Main achievements of the NETSSAF project

WP1: Definition of evaluation

criteria Partners Involved Main achievements

Task 1.1: Multidisciplinary criteria

for evaluation and classification of

peri-urban and rural settlings with

no access to improved sanitation

CREPA, BOATA, IEES,

IWA, SLU, MTM, Ville-de-

SYA, KNUST, GTZ, TUT

·

Identification of a set of multidisciplinary criteria (including climatic,

soil and groundwater, demographic and cultural, financial and

economic, institutional and health) for the evaluation and classification

of sustainability of sanitation systems in rural and peri-urban areas in

West Africa.

Task 1.2: Criteria for evaluation ·

Identification of a set of general criteria for the evaluation of sanitation

and systematisation of TTZ, TUHH, BIOAZUL, systems comprising health issues, environmental issues, technical

conventional and innovative low IEES, ESCA, GTZ, SLU and operational aspects, financial and economical aspects, social and

costs sanitation technologies cultural issues and gender related issues, which are considered

crucial for the evaluation of sanitation systems.

Task 1.3: Criteria of identification

of key stakeholders

CREPA, BIOAZUL,

BOATA, IEES, MTM,

Ville-de-SYA, GTZ, TUT

·

Development of steps and tools to identify and analyse key actors to

be included in the information dissemination process and to choose

appropriate communication mechanisms and tools. Three categories

of stakeholders and seven major communication tools relevant to the

dissemination of NETSSAF results have been identified.

WP2: Regional evaluation and

classification of typical

settlements

Partners Involved Main achievements

Task 2.1: Selection of potential

study population/areas

CREPA, BOATA, IWA,

UAA, MTM, Ville-de-SYA,

KNUST, CEPAPE, SEI,

GTZ

·

Identification of 66 potential study communities spread over eleven

countries in which partners recommend that further NETSSAF

activities, displaying the following characteristics: mix of rural, periurban

and semi urban locations, range of population size from 300 to

20 000, different socio-cultural and ethnic backgrounds, poorly

developed sanitation infrastructures, and a range of different technical

elements.

Task 2.2: Regional assessment

of rural and peri-urban

settlements

CREPA, BOATA, UAA,

MTM, Ville-de-SYA,

KNUST, CEPAPE, GTZ

·

Database of key actors and stakeholders across the West African

region including among others municipalities, rural associations,

regional and local authorities, for future dissemination activities.

·

Regional assessment of rural and peri-urban settlements including six

typical cases for rural settlements and six typical cases for peri-urban

settlements.

Task 2.3: Classification of typical

settlements

TUHH, CREPA, BOATA,

CEPAPE, SEI, GTZ

·

Identification, assessment and classification of typical settlements

which lack access to improved sanitation in West Africa, distributed

into three regions: Region A (Mauritania, Mali, Niger and Equatorial

Guinea), Region B (Senegal, Ghana and Côte d’Ivoire) and Region C

(Burkina Faso, Benin, Togo and Bissau Guinea).

Task 2.4: Selection of typical

examples/ study cases

TUHH, CREPA,

BIOAZUL, UAA, KNUST,

CEPAPE

·

Selection of 11 typical examples of each typical settlement: Ghana (3

sites), Cote d’Ivoire (2 sites), Senegal (1 site), Burkina Faso (2 sites),

Mali (2 sites), and Mauritania (1 site).

WP3: Sanitation technologies Partners Involved Main achievements

Task 3.1&3.2: Existing sanitation

systems and technologies

configurations

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES,

IWA, SLU, EAWAG, Ville-

de-SYA, ESCA, KNUST,

ULeeds, CEPAPE, SEI,

GTZ, TUT

·

After joining the two original tasks of WP3, elaboration of a report on

systematization, description and assessment of sanitation systems

and technologies.

WP4: Identification of potential

sustainable sanitation

technologies

Partners Involved Main achievements

Task 4.1: Assignment of

appropriate low-cost technologies

according to characteristics of

typical settlements

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES,

IWA, UAA, SLU, EAWAG,

Ville-de-SYA, ESCA,

KNUST, ULeeds, SEI,

GTZ, TUT

·

Development of a conceptual planning approach for supporting

decisions in the field of sanitation on a large scale in West Africa.

·

Identification of suitable sanitation technologies for exemplary rural

and peri-urban settlements, according to the characteristics and

needs regarding technical, social, economical, environmental,

institutional and legal aspects.

Task 4.2&4.3: Identification of TTZ, TUHH, CREPA,

technical and non-technical BIOAZUL, BOATA, IEES, ·

Identification of a set of technical and non-technical requirements for

requirements for large scale IWA, UAA, EAWAG, Villeeach

of the eight major phases for the successful implementation of a

implementation for each selected de-SYA, ESCA, KNUST, sustainable sanitation project.

technology ULeeds, SEI, GTZ, TUT

WP5: Regional identification of Partners Involved Main achievements

Page 10 of 15

NETSSAF Deliverable 68

possible suppliers/actions

Task 5.1: Identification and

mapping of possible regional

suppliers of technological

requirements

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, UAA,

MATAM, Ville-de-SYA,

KNUST, ULeeds, GTZ,

TUT

·

Identification of 160 companies involved in the design, planning,

manufacturing, sales, supply, implementation, maintenance,

monitoring, evaluation and quality control of the technical aspects of

sanitation systems within the West Africa region.

Task 5.2: Identification of current

technology transfer and

implementation activities and

their actors

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, UAA,

MATAM, Ville-de-SYA,

KNUST, ULeeds, GTZ,

TUT

·

Identification of 198 organisations offering sanitation services and

generally specialized in the non-technical aspects of sanitation in

West Africa.

Task 5.3: Data Base Platform

construction

TTZ, UAA

·

Yellow pages of sanitation and wastewater treatment solutions

including companies and organisations mapped, available in internet

at http://www.yellowpagesofsanitation.com/

WP6: Adapted Sustainable

Sanitation Management

System

Partners Involved Main achievements

Task 6.1: Development of the

decision making support tool

TTZ, TUHH, CREPA,

BIOAZUL, IEES, SLU,

EAWAG, CEPAPE, TUT

·

·

The knowledge acquired during all the previous WPs was compiled

and incorporated in a computer-software that is freely available on-

line for its downloading.

Decision making supporting tool being freely available on-line for its

downloading compiling all knowledge acquired during all the previous

WPs.

Task 6.2: Strategy of

implementation: Manual for

planning and implementation

TUHH, CREPA, BOATA,

IWA, UAA, MATAM, Ville-

de-SYA, KUST, SEI, GTZ

·

Guide for large scale planning and implementation of Low Cost

Sanitation Technologies based on the decision making supporting

tool.

WP7: Coordination and

research and technology

development

Partners Involved Main achievements

Task 7.1: Mapping current

research

CREPA, IWA, UAA,

ESCA, KNUST, CEPAPE,

SEI

·

·

Report on current research in the field of sustainable sanitation within

and outside the NETSSAF consortium in the field of sustainable

sanitation.

Mapping and evaluation of current research in the field of sustainable

sanitation within and outside the NETSSAF consortium in the field of

sustainable sanitation.

Task 7.2: Formation of research

clusters

IWA, UAA, SLU, ESCA,

KNUST, CEPAPE

·

Clustering according to their research activities and their

characteristics of the research activities carried out on sustainable

sanitation systems by research institutions throughout West Africa

and European organisations working in rural and peri-urban West

Africa.

Task 7.3: Formation of platform

database

BIOAZUL, KNUST,

CEPAPE

·

Development of the public library to provide information on

Sustainable Sanitation in Africa. The information is available for the

general public, including, background information, NETSSAF public

documents, sustainable sanitation documents, research on

sustainable sanitation, useful links, database of regional suppliers of

sanitation technologies in West Africa and database of technology

transfer organisations and networks.

·

Updating of the public library that provides information on Sustainable

Sanitation in Africa. The information is available for the general public,

including, background information, NETSSAF public documents,

sustainable sanitation documents, research on sustainable sanitation,

useful links, database of regional suppliers and technology transfer

organisations and networks working on sanitation in West Africa.

Task 7.4: Recommendations for

future research, technology

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES

IWA, SLU, EAWAG,

·

Recommendations for future research based on information from

WP3 and WP4. Identification of current gaps and needs for the

successful implementation of sustainable sanitation in West Africa.

development and cooperation ESCA, KNUST, ULeeds,

SEI, TUT

·

Network solidification report including potential ways for further

collaboration between stakeholders in the field of sustainable

sanitation and funding schemes to realise it.

WP8: Sustainable Sanitation

extension and dissemination

programme

Partners Involved Main achievements

Task 8.1: Extension activities

sensitive to end users

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES,

IWA, UAA, SLU, MTM,

Ville-de-SYA, KNUST,

CEPAPE, GTZ, TUT

·

·

Production of guidelines (in English and French) for the adequate

communication with communities in West Africa based on 84

interviews with local key players and end users in 6 countries (12 in

Burkina Faso, 5 in Ivory Coast, 13 in Ghana, 47 in Mali, 6 in Niger and

1 in Senegal).

Assessment of means, mechanisms and channels of communication

of local key actors and end users.

·

·

Printed material (awareness kit) for the end-users workshops

14 capacity building workshops for end users in seven West African

countries

Task 8.2: Capacity building of

authorities for future

implementation and

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES,

IWA, UAA, SLU, MTM,

·

The objective of this task is to implement the capacity building of

authorities and to disseminate the outcomes of the project. A work

plan has been developed and disseminated for this purpose.

Page 11 of 15

NETSSAF Deliverable 68

dissemination Ville-de-SYA, KNUST,

CEPAPE, GTZ, TUT

·

·

·

14 capacity building workshops for authorities in seven West African

countries.

Awareness kits in English and French for the workshops.

Strategy of authority capacity building, empowering local and national

authorities for the deployment of dissemination programs for

sustainable sanitation in rural and peri-urban areas of West Africa.

Task 8.3: Linking and

empowering existing and new

specialised training activities

TUHH, UAA, SLU, ESCA,

KNUST, CEPAPE

·

·

Compilation of specialised training activities on sustainable sanitation

carried out by NETSSAF partners, as well as a review of the

educational programmes at the West African universities (KNUST,

UAA and CEPAPE) where sustainable sanitation could be introduced

or strengthened.

Development of three workshops to increase the awareness of

training institutions on sustainable/ecological Sanitation and to

improve the Capacity of Teachers and Researchers on this new

emphasis on sanitation organized in Ivory Coast by UAA, Burkina

Faso by CEPAPE and Ghana by KNUST.

·

Formulation of possible links and cooperation strategies among

institutions to offer a broader scale of activities related to specialised

training. A report on these strategies includes activities needed in the

short-term as well as longer term, and NETSSAF partners’ activities

that are ongoing and under planning, both within NETSSAF and in

other contexts, that can contribute to fulfilling the aim of linking and

empowering specialised training activities in West Africa

Task 8.4: Development of tools

and activities for mass

dissemination

TTZ, TUHH, CREPA,

BIOAZUL, BOATA, IEES,

IWA, UAA, SLU, MTM,

EAWAG, Ville-de-SYA,

ESCA, KNUST, Uleeds,

·

·

·

·

·

·

Designing and setting on-line the official web page in July 2006 that

works as a dissemination tool as well as a communication platform for

the partners. It is available in English and French versions. Updates of

the web page (www.netssaf.net )

Updating of the official webpage of the project.

Inclusion of a special feature in the welcome page with a link to each

WP.

Production of the first promotional leaflet as the principal disseminator

for the Final Conference that will take place in Burkina Faso at the

end of the project. Distribution of 2000 exemplars in English and 1500

in French.

Inclusion of a special feature in the webpage devoted to the Final

Conference.

Production of the second promotional leaflet in French and English for

the wide dissemination of the Final Conference that took place in

CEPAPE, SEI, GTZ, TUT

·

·

·

·

·

·

Burkina Faso. Distribution of 1500 exemplars in each language.

Production of a promotional poster of the International Conference in

English and French.

Publication of several articles based on WPs results.

Production of 19 publishable articles on SuSan related topics.

Development of the Final Conference agenda, Programme and

related documentation.

Final Conference held in September 2008.

Several dissemination activities as the presentation of the project in

seminars, meetings, conferences, contact with relevant stakeholders,

etc.

WP9: Project management Partners Involved Main achievements

Task 9.1: General coordination

and financial project management

TTZ

·

·

·

·

The management of the project during all this time in parallel to

coordination activities, ensuring the correct coordination,

communication and cooperation between the partners.

The consortium agreement signed by all project partners.

The report on the communication channels within the consortium

Compilation and checking of all Financial Statements and Audit

certificates from project partners.

Task 9.2: Scientific project

management TUHH

·

·

Scientific coordination and revision of all the coordination activities

and main deliverables for ensuring and encouraging the proper

communication flow within the partnership.

Two Scientific development reports.

Task 9.3: Report project

management BIOAZUL

·

·

·

·

·

Elaboration of the five project updated reports

Preparation of the of three periodic activity and management reports.

Preparation of the minutes of the meetings, kick off, ad-hoc and mid

term meetings.

Preparation of the Final activity and Final management reports

Preparation of the Mid-term and Final review.

Task 9.4: Local project

management CREPA ·

·

Elaboration of the five local development reports.

Coordination of activities carried out by African partners

Page 12 of 15