Final Activity Report

|  | Virtual Reality and Human Factors Applications for Improving Safety |
| --- | --- |

Final Activity Report

Document No: VIRTHUALIS-D0.FAR

Covering period: 01 May 2005- 30 May 2010

Instrument:			Integrated Project

Thematic Priority: 	3.4.2.3-1 NMP Hazard reduction in production plant and storage sites

Report Preparation Date:	30 July 2010

Prepared by:			PMO

Classification:			Confidential

Contract Start Date:		01.05.2005

Duration: 			61 months

POLIMI, DAPP, DEMOS, UNIMORE, TCD, DTU, UNIMI, CERTH/HIT, TUC, KITE, INERIS, STR, EXIMIA, MW, LBORO.CO, VR&MMP, ICCS, IFF, TECNATOM, TOTAL, STATOIL, S-VURUP, PFI, OVGU, SONATRACH, POLITO, RELCONSULT, SIS, EIMM

Partners:

|  | Project funded by the European Community under the “Integrating and Strengthening the European Research Area” FP6 Programme (2002-2006) |
| --- | --- |

Project Co-ordinator:

Name: Simone Colombo. Organisation: POLITECNICO DI MILANO. Address: Dipartimento di Chimica, Materiali e Ingegneria Chimica "G. Natta", Piazza Leonardo da Vinci, 32, 20133 Milano - ITALY. Phone Number: +39.02.23.99-3263 Fax Number: +39.02.70.63.81.73. E-mail: simone.colombo@polimi.it. Project websites & other access points: www.VIRTHUALIS.org.

# Table of Content

Table of Content	3

Year 1 - 01.05.2005 – 30.04.2006	11

1	Publishable Executive Summary	11

Description of project objectives	11

Consortium	11

Coordinator contact details	12

Summary of work performed and Achievements	13

Expected results	15

Intentions for use and impact	15

Using and disseminating the knowledge	15

2	Project Objectives and major achievements during the reporting period	16

2.1	General Project Objectives and relation to state-of-the-art	16

2.1.1	General Project Objectives	16

2.1.2	State of the art	17

2.2	Objectives for the reporting period, work performed, contractors involved and main achievements in the period	17

2.3	Problems encountered and corrective actions	20

3	Workpackage major progress of the period	22

3.1	Objectives and relevant progress per WP	22

3.1.1	WP1	22

3.1.2	WP2	22

3.1.3	WP3	23

3.1.4	WP4	25

3.1.5	WP5	26

3.1.6	WP6	27

3.1.7	WP10	28

3.1.8	WP11	28

3.1.9	WP12	29

3.1.10	List of Deliverables	29

3.1.11	List of Milestones	31

4	Consortium Management	33

4.1	Consortium management tasks	33

4.2	Problems encountered	33

4.3	Changes in contractors’ responsibilities	33

4.4	Project timetable	33

4.5	Partners’ communication and meetings	34

4.6	Cooperation with other projects / programmes	35

5	Plan for using and disseminating the knowledge	36

5.1 - Exploitable knowledge and its Use	36

5.2 – Dissemination of knowledge	37

Publications	37

Year 2 - 01.05.2006 – 30.04.2007	40

6	Project Objectives and major achievements during the reporting period	40

6.1	Overview of general project objectives and relation to state-of-the-art	40

6.2	Summary of the recommendations from previous review (if any)	41

6.3	Objectives for the reporting period, work performed, contractors involved and main achievements in the period	42

6.3.1	Objectives for the reporting period	45

6.3.2	Work performed	46

6.3.3	Contractors involved	47

6.3.4	Main achievements	48

6.4	Problems encountered and corrective actions	49

EB Composition	50

7	Workpackage progress of the period	51

7.1	WP 4 - Impact on Safety Actions	51

7.1.1	WP 4 - Workpackage objectives and starting point of work at beginning of reporting period	51

7.1.2	WP 4 - Progress towards objectives	51

7.1.3	WP 4 - Deviation from the project programme and corrective actions taken\suggested	52

7.1.4	WP 4 - List of deliverables	52

7.1.5	WP 4 - List of milestones	52

7.2	WP 5 - Requirement	53

7.2.1	WP 5 - Workpackage objectives and starting point of work at beginning of reporting period	53

7.2.2	WP 5 - Progress towards objectives	53

7.2.3	WP 5 - Deviation from the project programme and corrective actions taken\suggested	54

7.2.4	WP 5 - List of deliverables	55

7.2.5	WP 5 - List of milestones	55

7.3	WP 6 - Prototyping	56

7.3.1	WP 6 - Workpackage objectives and starting point of work at beginning of reporting period	56

7.3.2	WP 6 - Progress towards objectives	56

7.3.3	WP 6 - Deviation from the project programme and corrective actions taken\suggested	58

7.3.4	WP 6 - List of deliverables	59

7.3.5	WP 6 - List of milestones	59

7.4	WP 10 – Dissemination of Virthualis Technology	60

7.4.1	WP 10 - Workpackage objectives and starting point of work at beginning of reporting period	60

7.4.2	WP 10 - Progress towards objectives	60

7.4.3	WP 10 - Deviation from the project programme and corrective actions taken\suggested	61

7.4.4	WP 10 - List of deliverables	61

7.4.5	WP 10 - List of milestones	61

7.5	WP 11 – Cost benefit & Socio Economic Impact of Virthualis technology	62

7.5.1	WP 11 - Workpackage objectives and starting point of work at beginning of reporting period	62

7.5.2	WP 11 - Progress towards objectives	62

7.5.3	WP 11 - Deviation from the project programme and corrective actions taken\suggested	62

7.5.4	WP 11 - List of deliverables	62

7.5.5	WP # - List of milestones	63

7.6	WP 12 - WP Title	63

7.6.1	WP 12 - Workpackage objectives and starting point of work at beginning of reporting period	63

7.6.2	WP 12 - Progress towards objectives	64

7.6.3	WP 12 - Deviation from the project programme and corrective actions taken\suggested	64

7.6.4	WP 12 - List of deliverables	64

7.6.5	WP 12 - List of milestones	64

8	Consortium management	65

8.1	Consortium management tasks	65

8.1.1	Problems occurred and actions taken	65

8.2	Changes in the consortium	66

8.2.1	Changes in contractors’ responsibilities	66

8.3	Project timetable and status	67

8.4	Partners’ communication and meetings	67

8.5	Co-operation with other projects/programmes	69

German Platform for Industrial Safety - IFF	69

Halden Reactor Project (HRP) Initiative – POLIMI	69

V3S Project – INERIS	70

8.5.1	PERFRV2 – LAA-P5	70

8.5.2	Greek Platform for Industrial Safety - DEMOS	70

8.5.3	HILAS and TATEM projects -TCD	70

Year 3 - 01.05.2007 – 30.04.2008	71

9	Project Objectives and major achievements during the reporting period	71

9.1	Overview of general project objectives and relation to state-of-the-art	71

9.2	Summary of recommendations from previous review (if any)	71

9.3	Objectives for the reporting period, work performed, contractors involved and main achievements in the period	71

9.3.1	Objectives for the reporting period	71

9.3.2	Work Performed	72

9.3.3	Contractors involved	72

9.3.4	Main Achievements	72

9.4	Problems encountered and corrective actions	72

10	Task progress of the period	75

10.1	WP1 Task6 RASVR STATOIL Case study	75

10.1.1	WP1 Task6 – Task objectives and starting point of work at beginning of reporting period	75

10.1.2	WP1 Task6 – Progress towards objectives	75

10.1.3	WP1 Task6 – Deviation from the project program and corrective actions taken/suggested	79

10.1.4	WP1 Task 6 – List of Deliverables	79

10.1.5	WP1 Task6 – List of Milestones	80

10.2	WP2 Task1 System Design and Detailed Specifications-	80

10.2.1	WP2 Task1 – Task objectives and starting point of work at beginning of reporting period	80

10.2.2	WP2 Task1 – Progress towards objectives	80

10.2.3	WP2 Task1 – Deviation from the project program and corrective actions taken/suggested	80

10.2.4	WP2 Task1 – List of Deliverables	80

10.3	WP2 Task1.1 – System Design and Detailed Specifications	80

10.3.1	WP2 Task1.1 – Task objectives and starting point of work at beginning of reporting period	80

10.3.2	WP2 Task1.1 – Progress towards objectives	81

10.3.3	WP2 Task1.1 – Deviation from the project program and corrective actions taken/suggested	81

10.3.4	WP2 Task1.1 – List of Deliverables	81

10.4	WP2 Task1.1.1 Methodologies consolodation and integration into safety engineering models	81

10.4.1	WP2 Task1.1.1 – Task objectives and starting point of work at beginning of reporting period	81

10.4.2	WP2 Task1.1.1 – Progress towards objectives	81

10.4.3	WP2 Task1.1.1 – Deviation from the project program and corrective actions taken/suggested	82

10.4.4	WP2 Task1.1.1 – List of Deliverables	82

10.5	WP2 Task1.1.2 - System and tools functional and quality specs def	82

10.5.1	WP2 Task1.1.2 - Task objectives and starting point of work at beginning of reporting period	82

10.5.2	WP2 Task1.1.2 - Progress towards objectives	82

10.5.3	WP2 Task1.1.2 - Deviation from the project program and corrective actions taken/suggested	82

10.5.4	WP2 Task1.1.2 - List of Deliverables	82

10.6	WP2 Task1.2 – IT System development	83

10.6.1	WP2 Task1.2 – Task objectives and starting point of work at beginning of reporting period	83

10.6.2	WP2 Task1.2 – Progress towards objectives	83

10.6.3	WP2 Task1.2 – Deviation from the project program and corrective actions taken/suggested	83

10.7	WP2 Task1.2.1 - IT Modules development	83

10.7.1	WP2 Task1.2.1 - Task objectives and starting point of work at beginning of reporting period	83

10.7.2	WP2 Task1.2.1 - Progress towards objectives	83

10.7.3	WP2 Task1.2.1 - List of Deliverables	83

10.8	WP2 Task1.2.1.1 DB & DBQ Database Query and Analysis Tools-	83

10.8.1	WP2 Task1.2.1.1 – Task objectives and starting point of work at beginning of reporting period	83

10.8.2	WP2 Task1.2.1.1 – Progress towards objectives	83

10.8.3	WP2 Task1.2.1.1 – Deviation from the project program and corrective actions taken/suggested	84

10.8.4	WP2 Task1.2.1.1 – List of Milestones	84

10.9	WP2 Task1.2.1.2 FTB+ESB-	84

10.9.1	WP2 Task1.2.1.2 – Task objectives and starting point of work at beginning of reporting period	84

10.9.2	WP2 Task1.2.1.2 – Progress towards objectives	84

10.9.3	WP2 Task1.2.1.2 – Deviation from the project program and corrective actions taken/suggested	84

10.9.4	WP2 Task1.2.1.2 – List of Deliverables	85

10.10	WP2 Task 1.2.1.3 Task Modeller	85

10.10.1	WP2 Task 1.2.1.3 – Task objectives and starting point of work at beginning of reporting period	85

10.10.2	WP2 Task 1.2.1.3 – Progress towards objectives	85

10.10.3	WP2 Task 1.2.1.3 – Deviation from the project program and corrective actions taken/suggested	86

10.10.4	WP2 Task 1.2.1.3 – List of Deliverables	86

10.11	WP2 Task 1.2.1.4 Competence Modeller	86

10.11.1	WP2 Task 1.2.1.4 - Task objectives and starting point of work at beginning of reporting period	86

10.11.2	WP2 Task 1.2.1.4 - Progress towards objectives	86

10.11.3	WP2 Task 1.2.1.4 - Deviation from the project program and corrective actions taken/suggested	86

10.11.4	WP2 Task 1.2.1.4 - List of Deliverables	86

10.12	WP2 Task 1.2.1.5 ALBA	86

10.12.1	WP2 Task 1.2.1.5 - Task objectives and starting point of work at beginning of reporting period	86

10.12.2	WP2 Task 1.2.1.5 - Progress towards objectives	86

10.12.3	WP2 Task1.2.1.5 - Deviation from the project program and corrective actions taken/suggested	87

10.12.4	WP2 Task1.2.1.5 - List of Deliverables	87

10.13	WP2 Task 1.2.1.6 - FPE module	87

10.13.1	WP2 Task1.2.1.6 - Task objectives and starting point of work at beginning of reporting period	87

10.13.2	WP2 Task1.2.1.6 - Progress towards objectives	87

10.13.3	WP2 Task1.2.1.6 - Deviation from the project program and corrective actions taken/suggested	87

10.13.4	WP2 Task1.2.1.6 - List of Deliverables	87

10.14	WP2 Task 1.2.2 - (IS)2 Product & subproduct Integration	88

10.14.1	WP2 Task 1.2.2 - Task objectives and starting point of work at beginning of reporting period	88

10.14.2	WP2 Task 1.2.2 - Progress towards objectives	88

10.14.3	WP2 Task 1.2.2 - Deviation from the project program and corrective actions taken/suggested	88

10.14.4	WP2 Task 1.2.2 - List of Deliverables	88

10.15	WP2 Task 1.3 HF-LAB	88

10.15.1	WP2 Task1.3 - Task objectives and starting point of work at beginning of reporting period	88

10.15.2	WP2 Task1.3 - Progress towards objectives	88

10.16	WP2 Task1.3.1 HF LAB releases	88

10.16.1	WP2 Task1.3.1 - Task objectives and starting point of work at beginning of reporting period	88

10.16.2	WP2 Task1.3.1 - Progress towards objectives	88

10.16.3	WP2 Task 1.3.1 - Deviation from the project program and corrective actions taken/suggested	89

10.17	WP2 Task 1.3.2 RASVR+TRVR STATOIL development	89

10.17.1	WP2 Task1.3.2 - Task objectives and starting point of work at beginning of reporting period	89

10.17.2	WP2 Task 1.3.2 - Progress towards objectives	89

10.17.3	WP2 Task 1.3.2 - Deviation from the project program and corrective actions taken/suggested	90

10.18	WP2 Task 1.3.3 RASVR+OSM SONATRACH development	90

10.18.1	WP2 Task 1.3.3 - Task objectives and starting point of work at beginning of reporting period	90

10.18.2	WP2 Task 1.3.3 - Progress towards objectives	90

10.18.3	WP2 Task 1.3.3 - Deviation from the project program and corrective actions taken/suggested	90

10.19	WP2 Task 1.3.4 AIS TOTAL Development	90

10.19.1	WP2 Task1.3.4 – Task objectives and starting point of work at beginning of reporting period	90

10.20	WP2 Task 1.4 Product Quality Assurance	91

10.20.1	WP2 Task 1.4 – Task objectives and starting point of work at beginning of reporting period	91

10.20.2	WP2 Task 1.4 – Progress towards objectives	91

10.20.3	WP2 Task 1.4 – Deviation from the project program and corrective actions taken/suggested	91

10.20.4	WP2 Task 1.4 – List of Deliverables	91

10.21	WP2 Task 2 Field Test and Validation	91

10.21.1	WP2 Task 2 - Task objectives and starting point of work at beginning of reporting period	91

10.21.2	WP2 Task 2 - Progress towards objectives	92

10.21.3	WP2 Task 2 - Deviation from the project program and corrective actions taken/suggested	92

10.22	WP2 Task 2.1 RASVR+TRVR STATOIL	92

10.22.1	WP2 Task 2.1 - Task objectives and starting point of work at beginning of reporting period	92

10.22.2	WP2 Task 2.1 - Progress towards objectives	92

10.22.3	WP2 Task 2.1 - Deviation from the project program and corrective actions taken/suggested	92

10.23	WP2 Task 2.1.1 Case Study Review	92

10.23.1	WP2 Task 2.1.1 – Task objectives and starting point of work at beginning of reporting period	92

10.23.2	WP2 Task 2.1.1 – Progress towards objectives	92

10.23.3	WP2 Task 2.1.1 – Deviation from the project program and corrective actions taken/suggested	92

10.23.4	WP2 Task 2.1.1 – List of Deliverables	92

10.24	WP2 Task 2.1.2 IT Tools installation	93

10.24.1	WP2 Task 2.1.2 - Task objectives and starting point of work at beginning of reporting period	93

10.24.2	WP2 Task 2.1.2 - Progress towards objectives	93

10.24.3	WP2 Task 2.1.2 - Deviation from the project program and corrective actions taken/suggested	93

10.24.4	WP2 Task 2.1.2 - List of Deliverables	93

10.24.5	WP2 Task 2.1.2 - List of Milestones	93

10.25	WP2 Task 2.1.3 Testing and Validation	93

10.25.1	WP2 Task2.1.3 - Task objectives and starting point of work at beginning of reporting period	93

10.25.2	WP2 Task 2.1.3 - Progress towards objectives	93

10.25.3	WP2 Task 2.1.3 - Deviation from the project program and corrective actions taken/suggested	93

10.25.4	WP2 Task 2.1.3 - List of Deliverables	94

10.25.5	WP2 Task 2.1.3 - List of Deliverables	94

10.26	WP2 Task 2.1.4 Results Analysis	94

10.26.1	WP2 Task 2.1.4 - Task objectives and starting point of work at beginning of reporting period	94

10.26.2	WP2 Task 2.1.4 - Progress towards objectives	94

10.26.3	WP2 Task 2.1.4 - Deviation from the project program and corrective actions taken/suggested	94

10.26.4	WP2 Task 2.1.4 - List of Deliverables	94

10.27	WP2 Task 2.2 RASVR+OSM SONATRACH	94

10.27.1	WP2 Task 2.2 – Task objectives and starting point of work at beginning of reporting period	94

10.27.2	WP2 Task 2.2 – Progress towards objectives	95

10.27.3	WP2 Task 2.2 – Deviation from the project program and corrective actions taken/suggested	95

10.27.4	WP2 Task 2.2 – List of Deliverables	95

10.28	WP2 Task 2.2.1 Case Study Specification	95

10.28.1	WP2 Task 2.2.1 - Task objectives and starting point of work at beginning of reporting period	95

10.28.2	WP2 Task 2.2.1 - Progress towards objectives	95

10.28.3	WP2 Task 2.2.1 - Deviation from the project program and corrective actions taken/suggested	95

10.28.4	WP2 Task 2.2.1 - List of Deliverables	95

10.29	WP2 Task2.2.2 IT Tools installation	95

10.29.1	WP2 Task 2.2.2 - Task objectives and starting point of work at beginning of reporting period	95

10.29.2	WP2 Task 2.2.2 - Progress towards objectives	95

10.29.3	WP2 Task 2.2.2 - Deviation from the project program and corrective actions taken/suggested	96

10.29.4	WP2 Task2.2.2 - List of Deliverables	96

10.29.5	WP2 Task2.2.2 - List of Deliverables	96

10.30	WP2 Task 2.2.3 Testing and validation	96

10.30.1	WP2 Task 2.2.3 - Task objectives and starting point of work at beginning of reporting period	96

10.30.2	WP2 Task 2.2.3 - List of Deliverables	96

10.30.3	WP2 Task 2.2.3 - List of Milestones	96

10.31	WP2 Task 2.2.4 Results Analysis	97

10.31.1	WP2 Task 2.2.4 – Task objectives and starting point of work at beginning of reporting period	97

10.31.2	WP2 Task 2.2.4 – List of Deliverables	97

10.32	WP2 Task 2.3 AIS TOTAL	97

10.32.1	WP2 Task 2.3 - Task objectives and starting point of work at beginning of reporting period	97

10.32.2	WP2 Task 2.3 - Progress towards objectives	97

10.32.3	WP2 Task 2.3 - Deviation from the project program and corrective actions taken/suggested	97

10.33	WP2 Task 2.3.1 Case study review	97

10.33.1	WP2 Task 2.3.1 – Task objectives and starting point of work at beginning of reporting period	97

10.33.2	WP2 Task 2.3.1 – Progress towards objectives	97

10.33.3	WP2 Task 2.3.1 – Deviation from the project program and corrective actions taken/suggested	97

10.33.4	WP2 Task 2.3.1 – List of Deliverables	97

10.34	WP2 Task 2.3.2 IT tools Installation	98

10.34.1	WP2 Task 2.3.2 - Task objectives and starting point of work at beginning of reporting period	98

10.34.2	WP2 Task 2.3.2 - Progress towards objectives	98

10.34.3	WP2 Task 2.3.2 - Deviation from the project program and corrective actions taken/suggested	98

10.34.4	WP2 Task 2.3.2 - List of Deliverables	98

10.34.5	WP2 Task 2.3.2 - List of Milestones	98

10.35	WP2 Task 2.3.3 Testing and validation	98

10.35.1	WP2 Task 2.3.3 - Task objectives and starting point of work at beginning of reporting period	98

10.35.2	WP2 Task 2.3.3 - Progress towards objectives	98

10.35.3	WP2 Task 2.3.3 - Deviation from the project program and corrective actions taken/suggested	98

10.35.4	WP2 Task 2.3.3 - List of Deliverables	98

10.35.5	WP2 Task2.3.3 - List of Milestones	99

10.36	WP2 Task 2.3.4 Results Analysis	99

10.36.1	WP2 Task 2.3.4 - Task objectives and starting point of work at beginning of reporting period	99

10.36.2	WP2 Task 2.3.4 - Progress towards objectives	99

10.36.3	WP2 Task 2.3.4 - Deviation from the project program and corrective actions taken/suggested	99

10.36.4	WP2 Task 2.3.4 - List of Deliverables	99

10.37	WP2 Task 3 Exploitation and Technology Transfer	99

10.37.1	WP2 Task 3 – Task objectives and starting point of work at beginning of reporting period	99

10.37.2	WP2 Task 3 – Progress towards objectives	99

10.37.3	WP2 Task 3 – Deviation from the project program and corrective actions taken/suggested	99

10.37.4	WP2 Task 3 – List of Deliverables	99

10.38	WP2 Task 3.1 Market Analysis Update	99

10.38.1	WP2 Task 3.1 - Task objectives and starting point of work at beginning of reporting period	100

10.38.2	WP2 Task 3.1 - Progress towards objectives	100

10.38.3	WP2 Task 3.1 - Deviation from the project program and corrective actions taken/suggested	100

10.38.4	WP2 Task 3.1 - List of Deliverables	100

10.38.5	2.38.4 WP2 Task3.1 - List of Milestones	100

10.39	WP2 Task3. 4 Dissemination activity	100

10.39.1	WP2 Task 3.4 - Task objectives and starting point of work at beginning of reporting period	100

10.39.2	WP2 Task 3.4 - Progress towards objectives	100

10.39.3	WP2 Task 3.4 - Deviation from the project program and corrective actions taken/suggested	101

10.39.4	WP2 Task 3.4 - List of Deliverables	101

10.39.5	WP2 Task 3.4 - List of Milestones	101

10.40	WP2 Task 3.5 Technology training	102

10.40.1	WP2 Task 3.5 – Task objectives and starting point of work at beginning of reporting period	102

10.40.2	WP2 Task 3.5 – Progress towards objectives	102

10.40.3	WP2 Task 3.5 – Deviation from the project program and corrective actions taken/suggested	102

10.40.4	WP2 Task 3.5 – List of Deliverables	102

11	Consortium Management	102

11.1	Consortium Management Tasks	102

11.1.1	Task Achievements	103

11.1.2	Problems occurred and actions taken	103

11.2	Changes in the consortium	105

11.2.1	Changes in contractors’ responsibilities	105

11.2.2	Changes to the consortium itself	105

11.2.3	Project timetable and status	105

Year 4 and 5 - 01.05.2008 – 30.05.2010	107

12	Project Objectives and major achievements during the reporting period	108

12.1	Overview of general project objectives and relation to state-of-the-art	108

12.2	Summary of the recommendations from pervious review	108

12.3	Objectives for the reporting period, work performed, contractors involved and main achievements in the period	108

12.3.1	Objectives for the reporting period	108

12.3.2	Work performed	114

12.3.3	Contractors involved	122

12.3.4	Main achievements	123

12.4	Problems encountered and corrective actions	123

13	Workpackage progress of the period	129

13.1	WP II.0  – Task 0.1 – Steering of the project	129

13.1.1	Objectives and starting point of work at beginning of reporting period	129

13.1.2	Progress towards objectives	129

13.2	WP II.0  – Task 0.2 – Administration of the project	129

13.2.1	Objectives and starting point of work at beginning of reporting period	129

13.2.2	Progress towards objectives	129

13.3	WP II.0  – Task 0.3 – Quality management	130

13.3.1	Objectives and starting point of work at beginning of reporting period	130

13.3.2	Progress towards objectives	130

13.3.3	Deviation from the project programme and corrective actions taken\suggested	130

13.4	WP II.1 – Task 1.1 – Design & Detailed Specification	131

13.4.1	Objectives and starting point of work at beginning of reporting period	131

13.4.2	Progress towards objectives	131

13.4.3	Deviation from the project programme and corrective actions taken\ suggested	131

13.4.4	List of deliverables	131

13.5	WP II.1 – Task 1.2 – IS2 System Development	132

13.5.1	Objectives and starting point of work at beginning of reporting period	132

13.5.2	Progress towards objectives	132

13.5.3	Deviation from the project programme and corrective actions taken\ suggested	132

13.5.4	List of deliverables	132

13.6	WP II.1 – Task 1.3 – Case study on Statoil Hydro and Sonatrach	133

13.6.1	Objectives and starting point of work at beginning of reporting period	133

13.6.2	Progress towards objectives	133

13.6.3	Deviation from the project programme and corrective actions taken\ suggested	133

13.6.4	List of deliverables	133

13.7	WP II.1 – Task 1.4 – IT-Tools validation	134

13.7.1	Objectives and starting point of work at beginning of reporting period	134

13.7.2	Progress towards objectives	134

13.7.3	Deviation from the project programme and corrective actions taken\ suggested	134

13.7.4	List of deliverables	135

13.8	WP II.1 – Task 1.5 – Product Quality Assurance	135

13.8.1	Objectives and starting point of work at beginning of reporting period	135

13.8.2	Progress towards objectives	135

13.8.3	Deviation from the project programme and corrective actions taken\ suggested	136

13.8.4	List of deliverables	137

13.9	WP II.2  – Task 2.1 – RASVR+TRVR STATOIL	137

13.9.1	Objectives and starting point of work at beginning of reporting period	137

13.9.2	Progress towards objectives	137

13.9.3	Deviation from the project programme and corrective actions taken\suggested	138

13.9.4	List of deliverables	138

13.10	WP II.2  – Task 2.2 – RASVR+OSM SONATRACH	138

1.1.1	Objectives and starting point of work at beginning of reporting period	138

13.10.1	Progress towards objectives	138

13.10.2	Deviation from the project programme and corrective actions taken\suggested	139

13.10.3	List of deliverables	139

13.11	WP II.3  – Task 3.1 – Market analysis update	139

13.11.1	Objectives and starting point of work at beginning of reporting period	139

13.11.2	Progress towards objectives	140

13.11.3	Deviation from the project programme and corrective actions taken\suggested	140

13.11.4	List of deliverables	140

13.12	WP II.3  – Task 3.2 – Definition of the IS2 product	141

13.12.1	Objectives and starting point of work at beginning of reporting period	141

13.12.2	Progress towards objectives	141

13.12.3	Deviation from the project programme and corrective actions taken\suggested	142

13.12.4	List of deliverables	142

13.13	WP II.3  – Task 3.3 – Developing a market strategy	142

13.13.1	Objectives and starting point of work at beginning of reporting period	142

13.13.2	Progress towards objectives	142

13.13.3	Deviation from the project programme and corrective actions taken\suggested	143

13.13.4	List of deliverables	143

13.14	WP II.3  – Task 3.4 – Dissemination activity	144

13.14.1	Objectives and starting point of work at beginning of reporting period	144

13.14.2	Progress towards objectives	144

13.14.3	Deviation from the project programme and corrective actions taken\suggested	144

13.14.4	List of deliverables	144

13.15	WP II.3  – Task 3.5 – Technology Training	144

13.15.1	Objectives and starting point of work at beginning of reporting period	144

13.15.2	Progress towards objectives	144

13.15.3	Deviation from the project programme and corrective actions taken\suggested	145

13.15.4	List of deliverables	145

14	Consortium management	146

14.1	Consortium management tasks	146

14.1.1	Put in place appropriate and effective corrective actions needed to ensure that project objectives were met. Tasks achievements	146

14.1.2	Problems occurred and actions taken	147

14.2	Changes in the consortium	147

14.2.1	Changes in contractors’ responsibilities	147

14.2.2	Changes to consortium itself	147

14.3	Project timetable and status	147

14.4	Partners’ communication and meetings	149

14.5	Co-operation with other projects/programmes	149

15	Final Review Meeting & Conclusions	150

# Year 1 - 01.05.2005 – 30.04.2006

# Publishable Executive Summary

Description of project objectives

The objective of the VIRTHUALIS project is to generate new technology, by merging Human Factors (HF) knowledge and Virtual Reality (VR) technologies, so as to develop products that will enable the reduction of hazards in production plant and storage sites by addressing end-users’ practical safety issues, such as training control room operators, designing proper alarm systems, training teams to cope with emergencies, assessing the impact of plant modifications on operators’ reliability, helping managers to see the impact of their decisions on sharp-end operators’ daily work. The VIRTHUALIS technology will enable the moving from static paper-based assessments to dynamic virtual simulations and will allow safety analysts to easily and quickly understand and integrate HF concepts into safety analyses.

Consortium

The VIRTHUALIS Consortium consists of 42 partners, covering the following research areas: Human Factors experts, Virtual Reality Experts, End users (industrials and consultants) and industrial associations. A full list of the Consortium members follows in the Table below.

| Participant name | Participant short name | Country |
| --- | --- | --- |
| HF EXPERTS |  |  |
| Politecnico di Milano | POLIMI | IT |
| D’Appolonia | DAPP | IT |
| Joint Research Centre | JRC | IT |
| Linkoping University | LIU | SE |
| Paris University | UnivParis5 | FR |
| Slovak University of Technology | STUBA | SK |
| Demokritos | DEMOS | GR |
| Modena University | UNIMORE | IT |
| Trinity College of Dublin | TCD | IE |
| Torino University | UNITO | IT |
| Risoe National Laboratories | RISOE | DK |
| Milan University | UNIMI | IT |
| Technical Research Centre of Finland | VTT | FI |
| Centre for Research and Technology Hellas /Hellenic Institute of Transport | CERTH/HIT | GR |
| Technical University of Crete | TUC | GR |
| KOMAG | KOMAG | PL |
| KITE Solutions | KITE | IT |
| INERIS | INERIS | FR |
| STR Solutions | STR | IT |
| VR EXPERTS |  |  |
| EXIMIA | EXIMIA | IT |
| Fraunhofer Institut | IFF | DE |
| TNO Human Factors | TNO | NL |
| Mother Way | MW | IT |
| Loughborough University | LBORO | UK |
| Virtual Reality & Multi Media Park | VR&MMP | IT |
| Institute of Communication and Computer Systems | ICCS | GR |
| DOMAIN EXPERTS (INDUSTRIES) |  |  |
| TECNATOM | TECNATOM | ES |
| British Petroleum | BP | UK |
| CARBID-FOX | CARBID-FOX | RO |
| SADACHIT | SADACHIT | RO |
| TOTAL | TOTAL | BE |
| STATOIL | STATOIL | NO |
| S-VURUP | S-VURUP | SK |
| OXON | OXON | IT |
| Phosphoric Fertilisers Industry | PFI | GR |
| CONSULTANTS |  |  |
| CRAIM-UBB | CRAIM-UBB | RO |
| SAUF Consulting | SAUF | UK |
| Det Norske Veritas | DNV | NO |
| CAPSICOM | CAPSICOM | FR |
| INDUSTRIAL ASSOCIATIONS |  |  |
| European Oil & Gas Innovation Forum | EUROGIF | BE |
| International Association of Oil & Gas Producers | OGP | UK |

Table 1: List of Consortium members of VIRTHUALIS

Coordinator contact details

Simone Colombo

POLITECNICO DI MILANO

Dipartimento di Chimica, Materiali e Ingegneria Chimica "G. Natta"

Piazza Leonardo da Vinci, 32

20133 Milano

ITALY

Phone: +39.02.23.99-3263

Fax: +39.02.70.63.81.73

E-mail: simone.colombo@polimi.it

Project website: www.virthualis.org

Summary of work performed and Achievements

VIRTHUALIS is organised in four phases and 13 work packages. Within the first reporting period, 10 work packages were active. The main activities and achievements in the first reporting period are described below.

WP0 deals with the project management and quality assurance. Within the reporting period lists of contact persons per WP and board have been developed, so as to facilitate partners’ communication. A project manual has been developed which presents the bodies that govern the project and their responsibilities and defines the procedures to be applied in order to guarantee high quality of project results and easy monitoring of project process. This manual is being followed in all project activities.

The objective of WP1 was to characterise the end-users’ applications of VIRTHUALIS technology, defined as a set of scenarios giving concrete illustration of how VR and HF could be integrated in safety actions (Training, risk assessment, accident investigation, safety management and audit). For that purpose, 42 interviews of various profiles of actors involved in safety were conducted in 15 chemical or petrochemical industrial sites in order to identify relevant needs that could be covered by VR. From these interviews, the WP1 produced a total of 15 interview synthesis, identified the main needs per safety activity (Training, Assistance to Operation, Design, Risk assessment, Accident investigation and Safety Management & Audit) and developed 21 scenarios which have been validated with industrial end-users.

The objective of WP2 was to define a common VR platform for developing and integrating appropriate safety scenarios through the definition of required software tools, definition of hardware interfaces and modules which will be supported and the definition of a common data exchange format. To reach the objective, a set of questionnaires regarding end users’ requirements, available VR systems and supported data formats were prepared. These questionnaires were discussed with the end users on-site in a set of interviews with IT and VR experts from the end users’ enterprises. An analysis of the interviews resulted in defining and shaping the deliverables of WP2 (5 deliverables) besides the necessary input for providing an initial specification of the VIRTHUALIS platform which will be developed in WP6. A glossary of VR and HF terms was also provided within the framework of WP2 and represents a data base for a common understanding of HF and VR issues in the consortium (and outside the consortium in the future).

The purpose of WP 3 was to define and develop the human factors methodologies required by the different VIRTHUALIS tools. In order to achieve its objectives WP3 was divided into three main lines of activities. Activity 3A, developed an integrated model of system safety with equal emphasis on human factors, technological functions, and organisational conditions. This corresponds to a systems view, according to which accidents are emergent rather than resultant phenomena. Activity 3B, defined the requirements to VR-enabled solutions and also identified appropriate tools. Activity 3C, provided the framework for computer-aided access to the mapping rules developed in WP 3B. The framework refers to the method and analysis principles, rather than to the VR-enabled solutions as such.

The main objectives of WP4 are the design of a Database on HF data that will enable the harmonisation of information derived from applying VR for different uses associated to HF impact on safety and the definition of possible case studies for the development of the VIRTHUALIS tools. A thorough literature review has been performed on existing tools and cases of applying HF on safety related actions. The global objectives of the database per safety action have been defined, namely who will use the database, what type of information should be collected, what type of classification and taxonomies have to be used for the information, what type of data analysis and queries should be set. A set of templates has been produced to support the work of identifying how different HF methods in connection to specific scenarios can be improved by the use of VR technologies.  The templates are being completed by partners. Finally, a methodology has been defined for prioritising the scenarios proposed in WP1 according to their expected impact. The scenarios are being rated according to a variety of criteria, aiming to estimate each scenarios’ expected impact. The scenarios with the higher ratings will be selected for further elaboration into case studies.

The main objective of WP5 is to extract the requirements from end-users and propose the most appropriate tools for the 4 cases to be developed in WP6. Within the reporting period a new template for the scenarios has been developed, which aims towards consolidating functional requirements needed by VR experts. This template will be the basis for the development of the final scenarios to be developed in WP6.

WP6 has started within the reporting period, although it was planned to start in month 13. The objective of WP6 is to develop the actual VIRTHUALIS applications. This will be carried out into two stages, the first being the SafeVR toolbox and the second being the actual applications development. So far the first stage is active (SafeVR toolbox – task1) and the main activities performed have included the initial system architecture as a draft and final and splitting of the work into sub-tasks according to the partners’ responsibilities and resources. As far as the system architecture is concerned, detailed documentation has already been produced on the actual system layout, operating blocks as well as interconnections between them. Furthermore close cooperation between the VR experts has resulted into the identification of the system (SafeVR toolbox) main blocks as well as their organisation into time and partners’ responsibilities. Through cooperation with WP4 and WP5, the scenario and model needs have been identified and will be finalised soon.

The aim of WP10 is to greatly disseminate VIRTHUALIS technology to the relevant scientific, academic industrial and societal sector. Within the reporting period, a review of mechanisms for technology transfer and diffusion has been performed and the dissemination strategy for VIRTHUALIS has been defined. It is planned that each WP leader occasionally communicates the results of its WP to WP10, and WP10 takes care for their appropriate diffusion. A VIRTHUALIS brochure has been defined and a web site has been developed. Moreover, an intranet has been established, where all project documentation is being maintained.

The objectives of WP11 for the first year of the VIRTHUALIS project was to extract market characteristics, to determine the current market trends and the present, relevant to VIRTHUALIS technology, systems and applications and to highlight the organisational and technical requirements for supporting the VIRTHUALIS applications. Towards the achievement of the aforementioned objectives extended web and literature surveys were conducted with regard to similar to VIRTHUALIS applications upon common defined forms. Based on these surveys, significant main conclusions concerning state of the art in the respective fields have been outlined, enriched with comparative figures, whereas the current trend in such systems/services has been primarily identified.

The objective of WP12 is to examine standards relevant to the project and finally define a clear set of policy recommendations for relevant authorities. Within the reporting period the areas –legislation needs of impact for VIRTHUALIS outcome have been identified, based on a template / questionnaire that has been developed for this scope. Data have been already collected and analysed. The results will be presented in Deliverable 12.1.

Expected results

The final result of VIRTHUALIS will be an integrated VR tool to will assist designers, plant operators, plant managers and safety engineers to carry out safety related tasks. The VIRTHUALIS technology will be composed by the SafeVR platform and 4 specific tools. The platform will be common to all tools and enable to run them representing their common environment. Each of the 4 tools will enable to perform a safety action, i.e., the training, the risk assessment, the accident investigation, and the safety management & audit activity.

Intentions for use and impact

The consortium intends to greatly use and diffuse the VIRTHUALIS results. For this reason, there are discussions for the establishment of a network, sustainable after the end of VIRTHUALIS project, with the mission to promote new interdisciplinary science-based approaches and solutions to Safety, Security, Environment and Health issues initially based on the VIRTHUALIS Technology concept and on the European Technology Platform on Industrial Safety.

Using and disseminating the knowledge

Several communications materials and tools have been developed during the 1st year of the project life to disseminate the project concept and available results. More specifically:

- The Project Web Site has been established at early project stage. It can be visited at: www.virthualis.org

- An intranet structure has been established and is being used as document and data repository for the project.

- A project logo and brochure have been designed to communicate the project concept, objectives and main results during European and International Conferences, Project Workshops and Events and other related dissemination actions.

- 3 paper presentations have been already made to international conferences and another 5 are currently planned. Moreover, a special session and exhibition on VIRTHUALIS is planned during the 9th IFF science days and the 3rd conference on virtual reality under the motto “Virtual Reality and Augmented Reality for Planning, Testing and Operating Technical Systems”, in Madgeburg, Germany, in the period 21-22 June 2006.

- VIRTHUALIS has been presented / demonstrated on the occasion of another 8 international events and exhibitions.

VIRTHUALIS aims to commercially exploit the SafeVR toolbox and the four tools, in order to provide services like:

- Technology services (training, organisational set-up, knowledge, etc.);

- Creation of plant-specific scenarios;

- Supply and test of new and emerging VR technologies (VR centre of excellence);

- Supply of Human Factors courses properly shaped;

- Maintenance services;

- Optimisation of the VIRTHUALIS technology to the specific case so to  reduce the costs (scale economies).

# Project Objectives and major achievements during the reporting period

## General Project Objectives and relation to state-of-the-art

### General Project Objectives

The overall objective of VIRTHUALIS is to produce an affordable and accessible technology for hazards reduction in production plant and storage sites. The achievement of this objective will allow:

- To sensibly reduce accidents and incidents in the process industry;

- To enhance system operability within the overall life-cycle;

- To reduce costs associated with safety production.

The overall objective will be reached through the fulfilment of the following specific objectives:

- To characterise end-users’ applications of VIRTHUALIS technology based on chemical and petrochemical industry Priorities Topics;

- To define a suitable and common platform (both hardware and software) for VR modelling so as to facilitate the exchange of each part of VIRTHUALIS technology amongst the centres of reference;

- To develop a synthesis of safety analysis methods with human factors knowledge that can adequately represent the dynamic nature of human and system performance;

- To evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions, i.e. Training, Safety Analyses and Safety management & audit;

- To identify, evaluate and eventually propose the spectrum of tools to develop in the prototyping phase;

- To create an integrated VR tool that will assist designers, plant operators, plant managers and safety engineers to carry out safety related tasks;

- To check the sharpness of the tools on the different working contexts and to tune the different tools;

- To adapt each tool of VIRTHUALIS technology to SMEs needs;

- To apply best practice principles of technology & human factors implementation to the introduction of VIRTHUALIS technology in the end-user companies and check the degree to which the tools have met the end-users’ needs identified in WP1;

- To disseminate both scientific findings and VIRTHUALIS technology to potential users in order to improve and to enhance safety policies and actions;

- To account for the economic aspects of VIRTHUALIS technology so as to enable its adoption by the industry;

- To identify the relevant existing and “in-pectore” EU legislations and policies to which VR and HF may be contributing as relevant technologies, and define how and in which form the VIRTHUALIS technology could become a standardised set of tools and support their implementation in practice.

Globally, VIRTHUALIS will contribute to provide the chemical and petrochemical industry of tomorrow with the necessary tools for efficient life-cycle design, production, use and recovery. This will decrease at the same time internal and external costs and it will reduce major accidents hazards by improving safety and crisis management as well as safety audit power.

### State of the art

The state of the art review performed regarding the current Virtual Reality market has presented some important points. Most industries that choose VR technology do so due to the effectiveness of such applications as far as the training and design process are concerned.

Most of the products and projects that have been reviewed concern design improvement, employees training and risk assessment. However, it is very important to point out that Human Factor analysis is not implemented in these products. Only a small number of products has taken into account human factors (especially those involved in training) but none of them has taken the idea into such a depth like VIRTHUALIS aims. Most of the competitive products rely on the exact simulation of a certain situation, trying to supply the user with as many information as possible concerning certain environments (e.g. weather conditions for flight simulation, realistic movement and sounds for virtual battle training of soldiers, etc.).

## Objectives for the reporting period, work performed, contractors involved and main achievements in the period

| Project objectives | Work performed - status | Major achievement |
| --- | --- | --- |
| WP1 |  |  |
| End-user needs identification | - 42 interviews of various profiles of actors involved in safety were conducted in 15 chemical or petrochemical industrial sites. | 15 interview synthesis Needs identification in 6 safety activities |
| Creation of scenarios | - 33 initial scenarios have been developed and validated with end-users | 21 scenarios have been selected |
| WP2 |  |  |
| Definition of end users’ requirements (software and hardware) | - Finished and delivered in D2.1 | Base for developments in WP6 |
| Overview of available VR systems and products | - Finished and delivered in D2.2 | Base for developments in WP6 |
| Analysis of available data exchange formats and selection of VIRTHUALIS supported data formats | - Finished and delivered in D2.3 | Base for developments in WP6 |
| Specification of VIRTHUALIS platform | - Finished and delivered in D2.4 | Base for developments in WP6 |
| Glossary of HF and VR terms and definitions | - Finished and delivered in D2.5 | Knowledge data base for the entire VIRTHUALIS consortium |
| WP3 |  |  |
| Listing existing methods | - Delivered | Base for developments in WP4 and 5 |
| Definition of sources of difficulties | - Delivered | Base for developments in WP4 and 5 |
| Prioritisation between hazard identification and safety improvement | - Delivered | Base for developments in WP4 and 5 |
| Process detailing for each task to perform. | - Delivered | Base for developments in WP4 and 5 |
| Streamlining of processes and skills | - Delivered | Base for developments in WP4 and 5 |
| Existing guidelines collection | - Delivered | Base for developments in WP4 and 5 |
| Definition of requirements both from HF method and VEs to better perform safety actions | - Delivered | Base for developments in WP4 and 5 |
| Identify critical actions/tasks/boundaries to perform the safety actions | - Delivered | Base for developments in WP4 and 5 |
| Guidelines regarding all HF parameters analysed in WP3A | - Delivered | Base for developments in WP4 and 5 |
| Comparison between criticalities and potentials of VR tools | - Delivered | Base for developments in WP4 and 5 |
| WP4 |  |  |
| Evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions. | - On-going. Relevant HF methodologies and VR models are being evaluated. Methodology to prioritise WP1 scenarios has been developed and prioritisation is being carried out. | Scenarios of WP1 are being ranked according to their expected impact on several criteria. The top most scenarios will be further developed into case studies. |
| Preliminary design of a Database on HF data. | - On-going | Database structure has been defined. |
| WP5 |  |  |
| Extract and evaluate requirements from end-users. | - On-going | WP1 requirements are being analysed. |
| Propose the most appropriate tools for the 4 cases. | - On-going | Template for detailed definition of scenario has been developed. |
| WP6 |  |  |
| System Architecture | - Close cooperation and suggestions for improvements were performed between the VR experts to decide on an (initially) draft version of the system architecture which resulted into the final one | Final System Architecture |
| System Blocks | - System analysis to define and divide the whole architecture into main building blocks | Definition of system blocks |
| System Blocks | - Detailed theoretical system analysis was performed by the VR experts to determine the exact operation for each of the system building blocks | Documentation for each of the system blocks |
| Scenario needs | - Cooperation with WP5 for the determination of the scenarios needs | Determination of scenarios needs |
| Model needs | - Cooperation with WP5 and inter-WP partners concerning model needs | Determination of model needs |
| Work organisation | - Exhaustively detailed Gantt chart produced concerning all tasks of the system architecture including exact partners responsibilities | Detailed Gantt Chart |
| Inter WP cooperation | - Direct cooperation between WP4 and WP5 has been achieved through meetings etc towards the ensuring of results perfect fitting into WP6 | Ensuring proper feedback from other WPs |
| WP10 |  |  |
| Disseminate the VIRTHUALIS results. | - On-going | VIRTHUALIS logo and brochure have been designed. A strategy for dissemination has been defined. VIRTHUALIS has been presented in several conferences and exhibitions. |
| WP11 |  |  |
| To extract market characteristics and to determine the current market trends and the present, relevant to VIRTHUALIS technology systems and applications. | Formulation of common forms for questionnaire and web surveys (one for research products and one for commercial ones). State of the art web and literature surveys conduction regarding similar to VIRTHUALIS applications. Results gathering from questionnaires and surveys). Extension of the survey in INTUITION Consortium. Consolidation of collected result. Conclusions concerning State of the art and comparative figures were derived and the current trend in such systems/services is primarily identified. | Initial market analysis survey results on relevant to VIRTHUALIS applications and services. |
| WP12 |  |  |
| To identify the relevant legislations and policies to which VR and HF may be contributing as relevant technologies. | - On-going. Template for collection of relevant legislation has been developed and completed. Data have been analysed. | List of legislation and policies relevant to VIRTHUALIS. |

## Problems encountered and corrective actions

Changes in contractors responsibilities

WP0

The Quality Manager of the VIRTHUALIS project has changed from E. Bekiaris to V. Portouli, both belonging to CERTH/HIT, which is the responsible Partners for the respective task.

WP1

In the WP1, the risk assessment Task Leader has been changed as WP1 leader (UnivParis5) and vice versa.

Additional responsibilities : UnivParis 5 undertook Phase 2 co-leadership instead of DEMOS.

WP6

After the WP leader’s himself request, LBORO has decided to resign from the WP leader position, transferring the leadership to ICCS as an administrative leader and VR&MMP as a technical leader. This was mainly done since LBORO did not have enough resources allocated to WP& management, especially when the workload was getting increasingly complex.

Partners inside the WP6 have decided to start the WP6 works earlier so that there is enough time for the developments and the organization of work. So the WP has started in M9 instead of M13, however keeping the resources the same throughout its whole duration (18M).

This WP will be implementing the actual VIRTHUALIS toolbox and the related applications. After cooperation and discussions with the consortium end-users, it was suggested and decided that the applications implementation is changed a bit. This means that instead of building four applications, one on each safety action and a different industrial site, build a first application for two different plants and then a second application again applied for two different sites (potentially different from the ones used in the first application). Each application would focus on a given safety action, which will be implemented on two different plant models.

This could mainly indicate better the technology applicability and transferability, while at the same time it gives the opportunity to perform comparisons between the application of the same technology (same application) to different sites. Additionally, this could solve possible issues in case not enough information are provided for four industrial sites. Even if the information for two site is provided, still the technology is applied.

It can be noted here that no particular issues or problems have been emerged during the WP6 works so far. The above actions were not taken as corrective in terms of correcting any issues, rather than for better work organization and ensuring that there is time for the implementations to take place.

# Workpackage major progress of the period

## Objectives and relevant progress per WP

### WP1

The aim of the work package 1 is the identification of end-users needs. The specific production of this WP is a series of scenarios illustrating how Virtual Reality would cover specific needs of industry in the area of human factors aspects of safety.

The following methodology was followed during the WP :

- Collect existing documentations on safety organisation in end-users companies;

- Identify end-users;

- Create a template for WP1 interviewers;

- Perform structured interviews based on the interview guide. These interviews have been coordinated with WP2 partners,

- Validate interviews by interviewees;

- Synthesise interviews based on a common template;

- Develop scenarios based on a common template. At the end of this phase, 33 scenarios have been developed covering the 4 safety activities (training, risk assessment, accident investigation, safety management & audit)

- Validate scenarios based on:

  - HF implications;

  - End-users relevance;

  - VR feasibility.

The validation of these scenarios has been achieved during a 2-day workshop held at the European Commission, Brussels on 9 & 10 November, 2005. This workshop was structured to enable HF experts, end-users and VR expert to review the 33 scenarios. A total of 35 persons have attended the meeting. The final deliverable of this WP summarizes the work achieved during the workshop.

### WP2

To reach the goal of WP2 of defining a common VIRTHUALIS platform, the work in WP2 was distributed into 5 main tasks. Each task was lead by a research partner. The 5 tasks of WP2 are:

- Task 2.1: User Needs Analysis on VR-Technology: Software and Hardware;

- Task 2.2: Market Overview of available VR-products;

- Task 2.3: Analysis of available standard data exchange formats;

- Task 2.4: Specification of VIRTHUALIS Platform;

- Task 2.5: Glossary of VR&HF Terms and Definitions.

It was agreed to launch tasks 2.1, 2.2, 2.3 and 2.5 immediately with the project start and start task 2.4 in M4 (end of August/beginning of September) due to its dependency on the results obtained in 2.1, 2.2 and 2.3. The overall period of WP2 was 6 months. The results obtained in WP2 were documented in D2.1, D2.2, D2.3, D2.4 and D2.5.

Below is a summary of the working approach followed in WP2:

- Building the tasks teams from the partners participating in WP2 (5-7 research partners for each task)

- Focusing on Tasks 2.1, 2.2, 2.3 and 2.5 (and postponing task 2.4 until initial results from tasks 2.1, 2.2 and 2.3 were available)

- Defining and merging the questionnaires covering the contents of tasks 2.1, 2.2 and 2.3

- Coordination with WP1 to conduct joint interviews at end users’ enterprises

- Contacting the end users and conducting the interviews

- Analysis and evaluation of the interviews for extracting the results necessary for the tasks and deliverables

- Launching task 2.4 (after the provision of initial results from tasks 2.1, 2.2 and 2.3)

- In parallel, the necessary work for task 2.5 (glossary of HF and VR terms) was being carried out

- Documentation of the results in the deliverables D2.1, D2.2, D2.3, D2.4 and D2.5

A list of “user roles” has been defined that should be considered as reference persons that will use the new tools. A list of requirements have been extracted from the interviews with industries. The fact that today only a few of them has installed VR hardware and software leaves a wider margin to define the platform for the new tools. As a consequence Windows-based PCs become a potential candidate for the VR platform to work with.

A complete market analysis has been conducted indicating all relevant products and devices in the area of VR (overview of available VR-platforms – SW & HW). The market research has covered both commercial VR systems and VR systems of the VIRTHUALIS consortium (VR experts). The analysis indicates each device’s main specifications in general, giving the opportunity to select the optimal device for a certain application at any time. Additionally, further tasks for the improvement of certain specifications can be identified aiming to the improvement of certain products to match the VIRTHUALIS technological needs.

Furthermore, data exchange formats and contents have been analysed, i.e., the data formats and contents (attributes, parameters, etc.) to be exchanged (created, imported and exported) inside and outside the intended VR platform. After a general analysis of available data exchange formats and standards (CAD, VR and supplementary data formats) an analysis of the current situation in the end users’ enterprises regarding data exchange systems and formats has been performed. The result of this analysis shows that no standard for exchanging data in the end users’ enterprises exists. However, most of these enterprises are using popular CAD systems which allow integrating different data formats and are also ready to implement conversion interfaces in their working units to integrate necessary data and information. Furthermore the difficulty of finding “a standard data exchange format” which manages the data and information necessary for creating the VIRTHUALIS scenarios calls for establishing “a data exchange content” by specifying 4 categories of data to be exchanged in the VIRTHUALIS platform. These 4 categories are: objects, HF, process and safety attributes.

Based on these surveys, the VIRTHUALIS platform has been specified.

In parallel, a Glossary of VR and HF Terms and Definitions has been established, which aims to enhance the communication and understanding among the project members. It is clustered in 11 sections and currently includes 355 terms.

### WP3

The purpose of WP 3 was to define and develop the human factors methodologies required by the different VIRTHUALIS tools. Safety analysis methods have traditionally been based on a sequential accident model that describes accidents as the outcome of a chain of events that may even be assumed to occur in some fixed and imaginable order. An accident is thereby described as a series of linked cause-effect pairs, where the analysis begins from the last effect – the “accident” – and proceeds backwards until it finds the first – or “root” – cause. In a more contemporary view of safety, accidents are seen as the outcome of an alignment of conditions and occurrences each of which is necessary, but none alone sufficient. This is also known as a systemic accident model, with origins going back to Perrow’s notion of “Normal Accidents”.

Conventional safety analysis methods reflect the sequential accident model by representing risks as a variation of a branching sequence, either as event or fault trees. Such approaches have three major disadvantages. First, they predominantly describe technological (mal) functions, which make it difficult adequately to account for the impact of human – and organizational – factors. Second, they cannot represent the outcome of events that have not already been included in the formal representation, i.e., unexpected conjunctions or confluences are excluded from analysis. Third, risks are associated with identifiable components or functions, but not with coincidences and functional dependencies.

In an attempt to overcome the first difficulty, risk and safety analysis methods have rather straightforwardly added the human factor – typically in the form of “human error” – in the sanguine hope that this would make the analysis complete. Quite apart from the embedded implication that humans can be treated as machines, this solution also disregards the fact that human and organisational performance are not just a possible source of failures but are also an essential resource for system safety. Sensible human actions provide the very foundation for a system’s stability throughout its life-cycle. Rather than simply adding a human factors component to existing methods, human factors must therefore become an integral part of the foundations of safety management methods. In practise this requires a change from linear to non-linear (systemic) accident models, which creates a need for more powerful methods and solutions. In order to achieve its objectives as stated above, WP 3 was divided into three main lines of activities;

- WP 3A, developed an integrated model of system safety with equal emphasis on human factors, technological functions, and organisational conditions. Within the work WP 3A collected detailed information about methods for risk assessment, accident investigation and safety management. Totally 53 methods was investigated. Of those seven was selected as the most interesting for the VIRTHUALIS tools. None of those seven could however alone fulfil the purpose of VIRTHUALIS

- WP 3B, defined the requirements to VR-enabled solutions and also identifies appropriate tools. Two types of fidelity can be addressed in training simulations: physical fidelity and psychological fidelity. Physical fidelity is the degree to which real-world operational equipment is reproduced. Psychological fidelity can be referred to as the degree to which training tasks reproduce actual behaviours, task situations or behavioural processes that are required for the job. A first distinction can be made between “Shallow-end” strategy and “deep-end” strategy. In the “shallow-end” strategy, the task is initially simple, and assistance is given to the trainee. In this approach, the user is smoothly “driven” to the top-end difficulty of the scenario through a well-proceduralised task. V&AR can enable to apply this strategy much better than reality by allowing trainers/trainees to change scenario variables in a desired manner in term of speed of the time sequence. The “deep-end” strategy proposes a completely different starting point. It exposes the trainee to full complexity of the task, with guidance and feedback only at the end of the session. In this second approach, the operator is breathlessly immersed in the complexity of the task/situation he/she has to cope with. For this purpose, the VE can have a support in further stressing the situation maybe by complicating the intricacy of the interrelations amongst the different plant variables (components, flows, interlocks) or by speeding up the pace at which they normally occur. A kind emphasis that, symmetrically to that used in the shallow-end strategy, allows to over train people by overrunning the process or, more broadly, the scenario at hand.

The aim of training for safety analysts is to train them to allow the identification hazards and the representation of safety-critical scenarios as combination of the identified hazards, conventionally by means of logic trees. In line with the shallow-end strategy described above, safety analysts can be trained by means of the “shaping process”, which foresee that things ought to grow gradually while being learnt. Similar descriptions for the activities of designers, of safety managers, and of trainers will be developed by the continued work in WP 3. V&AR also has potential in Risk Assessment & Accident Investigation as it usefully can be divided into events involving technology-related hazards and events involving human-related hazards.

The main use of V&AR technology in Safety Management & Audit will probably be in relation to accident prevention and handling of emergencies – both areas in which recent international events can provide a deplorable plethora of examples.

- WP 3C, provided the framework for computer-aided access to the mapping rules developed in WP 3B in order to provide users with a functional framework for identifying the methods that are most appropriate methods within the different and various stages of safety activities, as well as, the potential VR-enabled solutions. A web based tool has been developed so that it will require no installation and will be easily accessible by all interested end-users. The tool is developed mainly for safety analysts. The structure of the packaging tool follows the structure of the analysis performed in the context of WP3A and WP3B. It addresses all VIRTHUALIS areas (Training, Safety Analysis and Safety Management & Audit) and goes across the stages, the applicable HF methodologies in each case and the processes/skills distinguished for each area. Each HF methodology has its own description, reference and guidelines as well as its applicability in VIRTHUALIS related areas A link for each aforementioned issue exists in the main page of the tool, after a short description of the addressed area and the ambitions concerning the latest in the context of the VIRTHUALIS project an additional link exists for the “VR ENABLED SOLUTIONS” in each case which leads to the respective web page.

### WP4

The first objective of this WP is to evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions, i.e. Training, Safety Analyses, Safety management & audit, Accident Investigation.

The second objective is to follow up a preliminary design of a Database on HF data that will enable the harmonisation of information derived from applying VR for different uses associated to HF impact on safety (Risk Assessment, Training, Safety Audit and Management).

Prior to the formal Kick Off meeting, a questionnaire regarding the contribution of ideas from the members has been sent to all the partner, in order to define the expertise and degree of involvement in the various tasks and deliverables. A reasonable number of partners replied to this request.

WP4 has been kicked-off on the 13th of September 2005 during a common meeting at ISPRA (IT) with almost all partners. During this meeting a new plan of WP4 organization has been decided: the outcome was to perform the work in four parallel tasks instead of the three initially specified. These tasks are:

- Literature Review (Coordinated By JRC)

- Definition of Models, Methodologies, Key applications (Coordinated By VTT)

- Database: Requirements, Definition, Specification, Structure (Coordinated By TCD)

- Case Studies: Identification, Selection, Development (Coordinated By HIT)

Each task had to cover the three safety actions issues (Training, Safety Analysis-Accident Investigation and Safety Management) which were the object of the previous tasks.

Several mail exchanges and conference call meetings were then held between the four coordinators (JRC, VTT, TCD and HIT) in order to plan the deliverables chapters and the work to be done, on the basis also of the suggestions of other WP4 partners specific; a document reports this work assignment. Then every coordinator has been charged to extend the indication of the content of the chapters and to assign the work to the partners belonging to each task.

Following the scheduled activities, two of the four tasks have concluded their activities: Literature Review and Database Requirements tasks.

- For Literature Review task, JRC planned the work due to the fact that the outcomes are necessary for all the other tasks; a document reported this work assignment. Most of the partners involved in LR contributed to this collection. The review process and harmonization of these contributions for the purpose of the other WP4 tasks and deliverables has already begun and will fall within deliverable 4.1 and 4.2

For Database Requirements task, the work has been followed up in terms of technical requirements for the design of the database as well as scientific issues relating to content management, classifications of various models and methodologies, and all the issues related to the core problems (Training, Safety Analysis-Accident Investigation and Safety Management); all these issues will fall within the Deliverable 4.1: “Requirements and preliminary design of a Database for HF Data based on VR applications”

For the Case Studies task, the starting point is the 24 scenarios proposed and developed by WP1 of the project. A methodology for prioritising these scenarios has been developed. This methodology is based on various criteria, which aim to estimate the expected benefits by the implementation of VIRTHUALIS technologies for each specific scenario. Experts from within the consortium are currently rating the expected impact of each scenario for each specific criterion, in a scale from -4 (most negative effect) to +4 (most positive effect), 0 being neutral (no effect). The average of the ratings will then give the overall ranking of scenarios. Weights for the criteria are being developed via similar ratings. This means that every criterion will have its own weight factor, which will be the average of all ratings. The scenarios with the highest ranking will be then developed into case studies. A template for the case studies has been also developed. Moreover, the applicability of each scenario per VIRTHUALIS industrial partner is being investigated separately as well as the interest of the organisation for each scenario.

### WP5

WP5  has been designed as the middle VIRTHUALIS Work Package of PHASE II intending to a) Extract the requirements from end-users, b) Evaluate them and then) Propose the most appropriate tools for the 4 cases.

This is a core WP in the proposed methodology as it is the one to get all findings of WPs 1,2 and 3 and running in parallel with WP4 to have as an output the optimised catalogue for the VIRTHUALIS prototype that is going to be defined in WP6.

From early November DEMOS, as WP5 leader, started a close co-operation with WP5 task leaders (mainly HF experts) and selected partners (like TUC, IFF, VR&MMP, ICCS and others) trying to better define and fine-tune the objectives of WP5 and describe the work to be done also in relation with the members activities and capabilities. During November 2005 (month 7), a document has been sent to all WP5 participants, describing the notion of a “storyboard” and urging them to present their experiences in the same form. A creative conversation has been initiated on this basis, resulting in the production of some more storyboards, all uploaded at the WP5 area of the VIRTHUALIS server.

Apart from personal e-mailing, DEMOS has also produced several discussion documents describing its vision for the work in WP5 and moreover the VIRTHUALIS project. Special care and mentioning has been taken, so that the HF experts develop a common understanding with the VR ones regarding the overall VIRTHUALIS tool and methodology to be proposed. This is an issue that will remain “alive” across the whole duration of WP5.

The culmination point of this period is the organisation of the WP5 kick-off meeting in Athens, Greece, on January 31st, 2006. All research participants of WP5 have attended this half–day meeting, contributing to a constructive discussion and to two specialised workshops afterwards, where the main parts of the work to be elaborated within WP5 have been set together with the role that most participants wanted to undertake. As this meeting has been organised in succession to a WP4 meeting and before a WP6 one, the members of WP5 (most of them participating also in the other two WPs) had the opportunity to discuss the best way to synchronise the work in WP5 with the other two WPs time schedule, so as to maximise research efficiency and resources optimisation.

### WP6

This WP was started by partners’ motivation earlier on M9 instead of M13 mainly due to the great amount of work to be performed. This has not affected WP resources at all, but it has spread the same amount of resources through the M9 to M30 instead of M13 to M30 period. Also the WP leader has been replaced (by ICCS and VR&MMP) due to mainly funding and overload reasons.

Concerning the main actions and methodology followed so far, they can be summarised below:

- Draft system architecture

- Initial suggestion by TNO & VR&MMP

- Discussion/comments by ICCS

- Final system architecture

- Discussions between all VR experts

- Definition of system blocks

- Based on the building blocks identified in system architecture

- Documentation for building blocks and interconnection mechanisms

- Based on the building blocks identified in system architecture

- Intercommunication solutions (between modules) have also been created

- Identification of scenarios needs

- Close cooperation with WP4 and WP5 to ensure their results fit the WP6 needs 	and expectations

- Identification of model needs

- Close cooperation with WP4 and WP5 to ensure proper feedback

- Work organisation

- Tasks list created including partners and resources

- Tasks combined to better represent implementation modules

- Distribution and adjustment of partners’ resources between tasks

- Discussion with partners regarding their contributions

- Extensive final Gantt chart created including tasks, partners and resources

### WP10

An extensive review on state of the art on technology transfer and knowledge diffusion has been performed. Based on this a knowledge dissemination process for VIRTHUALIS has been defined two main dimensions: One internal the consortium and one external. This latter regards all the potential final users for the outputs produced by the Consortium.

It is indicated that the Consortium should initiate a strategic alliance with relevant enterprises and industries in the initial stages of the project. This network should include industries which face similar risks and which struggle with the same organisational problems, for example the management of operational knowledge in large socio-technical systems. This network, in attempting to solve these common problems could maximise the potential of a VR platform and would give the Consortium the opportunity to profit from the economies of scale and scope afforded by this collaboration.

As a first step to develop new alliance with strategic partners an effective external dissemination strategy has been defined. This includes the project web site, the production of specific material (i.e. brochures, posters) for the divulgation of project’s aims and objectives, the presentation of papers in conferences and other events, the demonstrations in specific exhibitions.

### WP11

The objectives of WP11 for the first year of the VIRTHUALIS project was to extract market characteristics, to determine the current market trends and the present, relevant to VIRTHUALIS technology, systems and applications and to highlight the organisational and technical requirements for supporting the VIRTHUALIS applications.

The work performed in WP11 is the following:

- Formulation of the methodological framework to be followed and of the common forms for questionnaire and web surveys (one for research products and one for commercial ones).

- State of the art web and literature surveys conduction regarding similar to VIRTHUALIS applications.

- Extension of the survey in INTUITION Consortium.

- Results gathering from questionnaires and surveys.

- Consolidation of collected results.

- Conclusions concerning state of the art and comparative figures were derived and the current trend in such systems/services is primarily identified.

The final results from these surveys show that the main advantage of VIRTHUALIS in comparison with every product that exists right now in the market is the implication of human factors. Since technology has served VR in the form of producing lively 3D graphics and highly sophisticated mathematical-physical models to simulate nature, it is time that an innovation takes the current state of VR into a different path. In order to succeed in this a complete package should be delivered containing excellent representation of the environment (given the current state of technology, VIRTHUALIS can settle for no less) and a useful insight in human factor requirements dictated by the relevant methodologies. This is certainly something different that will ensure the project’s success in a very competitive environment, flourishing with talented people and innovative ideas.

### WP12

The principal objective of this WP was to identify the relevant existing and “in-pectore” EU legislations and policies to which VR and HF may be contributing as relevant technologies, and define how and in which form the VIRTHUALIS technology could become a standardised set of tools and support their implementation in practice.

WP12 has been kicked-off on the 31st of May 2005 during a common meeting at MILAN (IT) with almost all partners. During this meeting deliverable D 12.1 has been reassigned to Task 12 A, which objectives coincide with the deliverable. Due to few resources allocated, all the partners belonging to WP12 have been involved in the contribution to this deliverable. It has been decided in that meeting, owing to the limited manpower allocated to Task A of WP12, to turn to the members of the consortium for collecting the national legislation bodies for some countries, exploiting already done work.

Successively, a template has been developed by DEMOS and JRC for gathering the required information, finalised with the comments of the partners. This template has been distributed among WP12 project partners for filling in the current legislation for as much as possible countries (represented by corresponding members of the consortium).

The data collection has been followed up by means of compilation of the templates; this process endured about 6 months with several integrations, revisions and amendments. In order to structure the whole set of data coming from the compiled templates, a small database has been developed, filled in by means of MS-Access tools and on purpose SQL scripts. The data archived in the tables are presently allowing query procedures. At present there is a follow up of the deliverables in terms of editing and reviewing process.

### List of Deliverables

| Del. No | Deliverable title | WP No | Due Date (Month) | Actual/ Forecast delivery date | Comments | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- |
| D0.1 | Project manual, including financial planning manual, quality assurance plan. | 0 | Month 3 | Month 6 |  | CERTH/ HIT |
| D0.2 | Project website | 0 | Month 3 | Month 3 |  | POLIMI |
| D0.3 | Database with contact details of all participants detailed by role in the project | 0 | Month 3 | Month 5 |  | DAPP |
| D0.4 | First biannual assessment and review report for the overall IP | 0 | Month 6 | Month 6 |  | DAPP |
| D0.5 | First annual report to the European Commission | 0 | Month 12 | Month 12 |  | DAPP |
| D1.1.A | End User requirement related to Training | 1 | Month 6 | Month 7 |  | TCD |
| D1.1.B | End User requirement related to Risk Assessment | 1 | Month 6 | Month |  | RISOE |
| D1.1.C | End User requirement related to Acc. Investigation | 1 | Month 6 | Month 7 |  | DAPP |
| D1.1.D | End User requirement related to Safety Management & Audit | 1 | Month 6 | Month 7 |  | DEMOS |
| D1.1 | End-users Application identification (Including the five previous reports and a synthesis of the findings) | 1 | Month 6 | Month 8 |  | Paris 5 |
| D2.1 | User Needs Analysis on VR Software and Hardware | 2 | Month 6 | Month 7 |  | VRML |
| D2.2 | Market Overview of COTS VR Products and Comparison with Systems of Partners of the Consortium | 2 | Month 6 | Month 7 |  | ICCS |
| D2.3 | Analysis of available standard Data Exchange Formats | 2 | Month 6 | Month 7 |  | IFF |
| D2.4 | Specification of VIRTHUALIS Platform | 2 | Month 6 | Month 7 |  | LBORO |
| D2.5 | Glossary of VR and HF Terms and Definitions | 2 | Month 6 | Month 8 |  | CERTH/HIT |
| D3.1 | HF Methodology Definition | 3 | Month 6 | Month 7 |  | LiU |
| D4.1 | Requirements for database | 4 | Month 12 | Month 15 | Planning modified with respect to the original Technical Annex | TCD |
| D4.2 | Applications of VR to HF, Case Studies | 4 | Month 15 | Month 18 | Planning modified with respect to the original Technical Annex | CERTH/ HIT |
| D5.1 | Check lists and Questionnaires to verify the acceptability/utility of proposed tools and the end users requirements satisfaction | 5 | Month 12 | Month 13 | Slight delay so as to compensate for the later start of WP5 and to get the maximum input from WP4 which is delivering after this date. | TCD |
| D10.1 | VIRTHUALIS review of literature in technological transfer, technology concepts and usefulness diffusion | 10 | Month 6 | Month 12 | Delayed because of lack of information and team composition | UNIMORE |
| D10.2 | Analysis of the application cases of VIRTHUALIS tools and methodologies | 10 | Month 6 | Month 18 | Re-scheduled to wait for the necessary information | UNIMORE |
| D11.1 | Extended market analysis survey results on relevant to VIRTHUALIS applications and services. | 11 | Month 12 | Month 12 |  | CERTH/ HIT |
| 12.1 | Report on Areas and Legislation Domains | 12 | M 11 | M 14 | Delay due to some deviations in collecting “raw” data. | DEMOS/ EUROGIF |

### List of Milestones

| WP | Milestone | Planned date | Actual date | Comments |
| --- | --- | --- | --- | --- |
| WP1 | M1.1. Risk Assessment Scenarios for Design, Operation and Decommissioning | Month 6 | Month 8 | Final version annex of the D1.1 |
| WP2 | M2.1 Identification of End-Users Requirements (Hardware and Software, draft) | Month 3 | Month 4 |  |
| WP2 | M2.2 Market overview of available VR-products and data standards (draft) | Month 4 | Month 4 |  |
| WP2 | M2.3 Definition of common language (glossary first draft) | Month 4 | Month 5 |  |
| WP3 | M3.1 Integrated F and Systemic Risk Model | Month 5 | Month 5 |  |
| WP3 | M3.2 Prototype Demonstration of HF-Risk based Visualisation Principles | Month 6 | Month 6 |  |
| WP4 | M4.1 Identification of Target Cases | Month 12 | Month 12 | Initial ranking of scenarios exists. Scenario applicability per industrial partner has been surveyed. |
| WP5 | M5.1 Enlargement of the end users community | Month 10 | Month 10 | Organisation of information days in Greece and in other countries. |
| WP5 | M5.3 Checking of methodology acceptability by end users’ personnel/philosophy | Month 10 | Month 10 |  |
| WP 10 | M10.1 Identification of potential users for Application | Month 3 | Month 6 | Presented in D10.1. |
| WP 11 | M11.1: Initial market analysis survey results on relevant to VIRTHUALIS applications and services. | M6 | M6 | An update version was prepared in M8. |
| WP 12 | M12.1 Definition of Areas/Legislation Needs | M 6 | M 6 |  |

# Consortium Management

## Consortium management tasks

A detailed Project Manual has been developed which presents the bodies that govern the project and their responsibilities and defines the procedures to be applied in order to guarantee high quality of project results and easy monitoring of project process. This manual is being followed in all project activities.

Mailing lists have been established for the various Boards of the project and for each WP.

The pre-financing for the first 18 months has been disseminated to all partners.

## Problems encountered

During the first year of the project life, 3 partners have decided to resign the project (Snamproggeti, SEI, SYNTHEXIM), due to restructuring of company, or inexperience in handling EC projects.

The relevant changes have been implemented in an updated Technical Annex, which has been submitted to the project officer for appropriate actions.

## Changes in contractors’ responsibilities

UnivParis 5 undertook Phase 2 co-leadership instead of DEMOS.

WP6 leader has changed from LBORO to ICCS (administrative leader) and VR&MMP (technical leader).

## Project timetable

WP5 initiation has been originally planned for month 4 from project start, i.e. August 2005. However, this was not feasible from a practical view point, as WP5 expects a lot of input from WP1-4, which on their turn could not deliver earlier that month 7, i.e. November 2005. The WP5 leader, DEMOS, in accordance with Phase I leaders and project office, decided to postpone the actual work start within WP5 for November 2005, although some effort had been undertaken by selected partners (like DEMOS, ICCS and VR&MMP) to establish the links with the preceding WPs (1-4), so that the deliverables of the latter would fit correctly the input needed for WP5.

WP6 started earlier than planned, in Month 9 instead of Month 13 mainly due to the great amount of work to be performed.

Deliverable 5.1 has been slightly delayed by one month, so as to receive input from WP4 which runs in parallel.

Deliverable 10.1 and 10.2 have been delayed.

The D10.1 one because of lack of information and team composition and D10.2 is re-scheduled to wait for the necessary information.

Deliverable 12.1 is slightly delayed by three months, due to some delays in collecting partners’ feedback.

## Partners’ communication and meetings

The following meetings have been already performed.

| Title | Date and Place | Main conclusions |
| --- | --- | --- |
| EB and AP meeting | 30 May – 1 June 2005, Milan, Italy | Meeting Minutes were devised and sent to all. |
| WP3 meeting | 28-30 June 2005 | Meeting Minutes were devised and sent to all. |
| WP1 end-users interviews series | From July till November | Knowledge base for scenario creation |
| Phase 1 meeting | 5 August 2005, Copenhagen |  |
| WP2 meeting | 25-26 August 2005, Magdeburg | Meeting Minutes were devised and sent to all. |
| EB, PB, WP3, WP3 meetings | 13-14 September 2005, Ispra | Meeting Minutes were devised and sent to all. |
| WP1 workshop | 9-10 November 2005 | Storyboard presentation for scenarios identification and selection |
| WP6 meeting | 10 January 2006, Paris |  |
| EB, PB, WP4, WP5, WP6 meetings | 31 January – 2 February 2006, Athens | Meeting Minutes were devised and sent to all. |
| EB, PB | 8 March 2006 | Change in structure of EB, Change in responsibilities of EB and PB |
| WP4 meeting | 30-31 March 2006, Dublin | Meeting Minutes were devised and sent to all. |
| WP6 technical meeting | 6 April 2006, Milan |  |
| WP5 Task 1 meeting | 12-13 April 2006, Paris |  |

The following meetings are planned.

| Title | Date and Place | Main conclusions |
| --- | --- | --- |
| AP meeting, WP4, WP5, WP6 meetings | 15-17 May 2006 |  |
| WP4 meeting | 14-16 June 2006, Roskilde |  |
| EB meeting | 28 June 2006, Greece |  |

## Cooperation with other projects / programmes

A close cooperation has been established between VIRTHUALIS and the INTUITION Network of Excellence, through ICCS who is the coordinator of INTUITION. INTUITION is a Network of Excellence on Virtual Reality and Virtual Environments Applications for Future Workspaces. The templates and questionnaires developed within VIRTHUALIS are being circulated among the INTUITION consortium and feedback is being collected. Moreover, INTUITION is being informed about the developments in VIRTHUALIS.

# Plan for using and disseminating the knowledge

5.1 - Exploitable knowledge and its Use

THE VIRTHUALIS exploitable products include the following:

  - A Human Factors methodology enabling to cope with safety issues using VEs to be properly used for Health, Safety & Environment (HSE) purposes.

  - A database for saving HF data.

  - A toolbox for developing VR applications.

  - Four applications using the toolbox.

  - Policy recommendations for relevant authorities.

The consortium intends to greatly use and diffuse the VIRTHUALIS results. For this reason, there are strong considerations to establish a network, sustainable after the end of VIRTHUALIS project, with the mission to promote new interdisciplinary science-based approaches and solutions to Safety, Security, Environment and Health issues initially based on the VIRTHUALIS Technology concept and on the European Technology Platform on Industrial Safety.

The network will be an open and flexible European network, including centres in each European Country. Each of the centres will share facilities with the remaining ones enabling researchers to investigate different aspects of the complexity of Safety, Security, Health and Environment (HSSE) issues and share the results with the network. The main inspiration of the Network organisational structure will be to enable remote collaboration on HSSE issues so as to diminish efforts and take the most from reciprocal synergies.

This network will have a direct impact on the following strategic objectives:

- Reference Centre for the conception, design, testing and application of a new generation of “Integrated Multidisciplinary Science-based Environments and Solutions for Safety, Security, Environmental Protection and Health” based on the most advanced Human and Organizational Factors (H&OF) methodologies and Virtual & Augmented Reality, Computing, Information and Communication technologies, which can allow for “safer” and “fault tolerant” products, systems, operational environments and processes.

- Reference Centre for the diffusion of a new culture of Safety and Security inside public and private institutions, media, social bodies, industrial (large as well as small and medium-sized enterprises) and financial entities and universities, research and technology developers.

- Reference Centre for the development and the implementation of a new generation of low-cost solutions and environments specifically conceived for small and medium public and private realities.

- “Trait d’ union” amongst European Universities, Research Centres, Industries, Public Organizations and Society fostering the development and the implementation of a new two-way cooperation framework.

- Definition of new educational curricula and educational initiatives aimed at creating a new generation of distinctive professionals characterized by a new culture, innovative experiences and interdisciplinary competences.

- Coordination Centre for the industrialization and future development of the VIRTHUALIS technology

# Benchmarking & Test Bed Centre for new technologies and integrated solutions

The network is expected to play an important role in promoting and coordinating a European ”Integrated Multidisciplinary Science-based Approach to Safety, Security, Environmental Protection and Health” towards developing countries in African, Asian and South American continents. It will also play an important role in promoting the new European approach towards North America and Asian countries

5.2 – Dissemination of knowledge

### Publications

| Author(s) | Title of paper | Conference details (name, date, place) |  |
| --- | --- | --- | --- |
| ATTENDED |  |  |  |
| Burkhardt J. M., Cabon P., Gounelle C., Salem, W. | Virtual Reality, Human Factors and safety-related issues: the VIRTHUALIS project | Proceedings of Virtual Concept 2005. Biarritz, France, November 8th – November 10th, 2005 |  |
| Teodor Winkler, Dariusz Michalak, Waleed Salem, Timo Maatta and Simone Colombo | VR technology in the life cycle of technical artefacts: a possibility of methodology transfer within high risk industries | KOMTECH, 6th International Conference, 15th-17th November 2005, Zakopane– Poland. |  |
| Waleed Salem, Simone Colombo, Philippe Cabon, Heike Kissner | Enhancing the Trainees’ Awareness in a Virtual Training Environment | Interactive Mobile and Computer Aided Learning 2006 (IMCL 2006), Amman, Jordan, April 19th-21st, 2005 |  |
| FORESEEN |  |  |
| Prof. Paul Chung, Dr Xiaolei Shang, Dr Luca Vezzadini, Konstantinos Loupos | The Integration of VR and Rule-Based Technologies to Improve Process Safety | IFF Science Days, Magdeburg, Germany, June 21-23, 2006 |
| Cabon, P., Gounelle C., Burkhardt J. | Improving Safety with VR technology through a user-centred design approach | IFF Science Days, Magdeburg, Germany, June 21-23, 2006 |
| Xiaolei Shang, Paul W. H. Chung, Luca Vezzadini, Konstantinos Loupos, Wytze Hoekstra | Integrating VR and Knowledge-Based Technologies to Facilitate the Development of Operator Training Systems and Scenarios to Improve Process Safety | ESREL conference Estoril, Portugal, 18-22 September 2006 |
| Fabre, D. Couix, S., Burkhardt J. M., Cabon P., Gounelle C. | Virtual Reality to support Human Factors integration for safety : where we are and where we (aim to) go | ESREL conference Estoril, Portugal, 18-22 September 2006 |

Moreover, a whole VIRTHUALIS session will be organized in the 9th IFF science days and the 3rd conference on virtual reality under the motto “Virtual Reality and Augmented Reality for Planning, Testing and Operating Technical Systems”, in Madgeburg, Germany, in the period 21-22 June 2006. The VIRTHUALIS session is scheduled for Thursday, 22 June, 9:00-12:00, with the title “Safer production with integrated VR - Human Factor solutions”. Presenters will be LAA-P5, LBORO, VR&MMP, ICCS, TECNATOM, RISOE, IFF and it will be chaired by POLIMI.

The VIRTHUALIS project will be also demonstrated at one of the boots in the exhibition area in front of the conference rooms.

Other dissemination activities:

| Description | Date |
| --- | --- |
| - Organisation for VIRTHUALIS & MOST initiative presentation in 2nd INTUITION workshop in Paris | Nov 2005 |
| - Dissemination of VIRTHUALIS and support over VIRTHUALIS and the MOST initiative during workshop in Paris | Nov 2005 |
| - Dissemination of VIRTHUALIS to INTUITION partners through market surveys (extension of related market analyses to INTUITION users) | June 2005 |
| - Porte Aperte all’Innovazione (Turin, October 2005). VR&MMP had a booth in the main arena where it presented its activities. A press release dedicated to VIRTHUALIS was also published. | October 2005 |
| - Workshop on future R&D challenges in the Networked Audio-Visual Systems (NAVS) area (EC offices, Brussels, October 6-7, 2005). VR&MMP attended the workshop and distributed brochures including a press release dedicated to VIRTHUALIS. | October 2005 |
| - Virtuality Conference (Turin November 3-6, 2005) – www.virtualityconference.it. A presentation was made about VIRTHUALIS project. | November 2005 |
| - DIADI technology transfer communication initiative (Turin, November 2005) – www.diadi.it. An article about VIRTHUALIS was published in Diadi Report, issue 4, November 2005, entitled “Progetto VIRTHUALIS. Realtà Virtuale e Fattori Umani per la prevenzione dei rischi nelle imprese”. | November 2005 |
| - VIRTHUALIS booth during the exhibition “Plant Engineering of the Future”, Magdeburg, Germany | March 2006 |

# Year 2 - 01.05.2006 – 30.04.2007

# Project Objectives and major achievements during the reporting period

This section 1covers the project work development for the period M13-M24 in terms of tasks accomplishment and outcomes according to the objectives settled in the work plan.

It also addresses the major problems encountered and describes how the consortium dealt with them.

## Overview of general project objectives and relation to state-of-the-art

Give an overview of general project objectives, show the project’s current relation to the state-of-the-art.

The key scientific and technical goal for the reporting period is to provide the first release of the VIRTHUALIS technology by developing the SafeVR platform and extracting the specifications of the safety applications that will be built on top of the SafeVR platform. The aim of this bit of project activities is that once the first release of the SafeVR platform of VIRTHUALIS is produced , the preparation for the development of practical cases is initiated in parallel to that activity (The first release of the SafeVR platform and its components was presented in October 2006, M18). This is to allow for the first release of the platform to go through a sort of preliminary validation and improvement phase; although still theoretical as done by comparing the coming specifications with the platform features under construction, and not by trying it in practice. The tight interlink between WP5 (devoted to producing tools requirements) and WP6 (devoted to prototyping them together with the platform) enabled for this reciprocal check of the advancements. In this process the HF modelling, i.e., the definition of HF precepts for the methodological side of VIRTHUALIS, was fostered by WP4 work which ended in M20 and was meant to shape the VIRTHUALIS “what & how to do” on the ground of the existing HF methodologies available both in the scientific arena and on the market.

This is reflected in the following objectives which are expression of the work performed:

1.	To evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions, i.e., Training, Safety Analyses and Safety management & audit (WP4);

2.	To provide a Preliminary design of a Database on HF data that will enable the harmonisation of information derived from applying VR for different uses associated to HF impact on safety (Risk Assessment, Training, Safety Audit and Management) (WP4);

3.	To select the final scenarios and provide inputs to WP5, and WP6 for the creation of integrated tools and VR platform for implementing VIRTHUALIS approach (WP4);

4.	To identify, evaluate and propose the spectrum of tools to be developed in the prototyping phase to accommodate the identified safety issues (WP5);

5.	To build, on the basis of the actual industrial and HF needs, an integrated VR toolbox for building safety applications (WP6);

6.	To start building the safety applications (tools) based on the the input provided by WP5 during industrial field works

7.	To shape the framework of the VIRTHUALIS Handbook (initially planned in WP5 and moved to WP13);

With relation to the fourth objective which represents an interlink between the activities of WP4 and WP6, WP5 had the role of transforming the HF/VR methodology (WP4) into a specification of the tools to be developed (WP6).

To ensure that the latter covers the industrial needs and, even more important, can be adequately used in an industrial environment, a full support from the industrial partners was required.

This was done first by going “to the field” to conduct appropriate task analysis and extract the requirements from the end-users, and second by evaluating them and subsequently proposing the most appropriate tools for the safety applications.

In this perspective, fieldwork has been initiated with first visits of HF experts to Total  Feluy (BE) plant in June 2006, and subsequently with a multidisciplinary team composed by HF and VR experts together with Process engineers and the Project co-ordinator to BP Saltend site (UK)  on July 2006 (18-20) and STATOIL Kårstø plant (NO) on September 2006 (19-21).

The objectives of the visits were:

- To present VIRTHUALIS project, its vision, and its current state of progress to safety personnel and management;

- To get support from both from management and safety personnel for further development of a case study;

- To identify a specific case study to develop further and that meets the requirements both of the specific industrial partner and VIRTHUALIS;

- To specify, at outline level, a simuscape and modules for each case study;

- To carry out high level task profiling and start the detailed task analysis of a critical task;

- To test the VIRTHUALIS field-work methodology.

Follow up visits have been performed on October and November and first reports on the findings of the visits (including the definition of one or more scenarios for each industrial site, i.e., simuscapes) have been prepared and are available on the VIRTHUALIS workspace as part of D5.1 and D5.2. The goal of the follow up visit was to finalise the task analysis that was started in the initial visits and detail the operational procedures that will be used as base for developing the safety applications (story boards).

In Parallel, another preparatory visit has been made to SLOVNAFT (SK) in order to investigate their potential needs and willingness to offer data for a case study. A follow up visit have been organized at the end of September. Moreover, ongoing work is progressing with French industries to formulate another SIMUSCAPE, i.e., the loading & unloading one. A report on the findings of the last has been prepared and uploaded in the intranet. This work, despite not foreseen in the Technical Annex, was performed as conceived strategic to link the activities of process industries with the transportation of dangerous goods.

## Summary of the recommendations from previous review (if any)

This paragraph, if applicable, should also contains a brief description of how the recommendations have been taken up by the consortium.

## Objectives for the reporting period, work performed, contractors involved and main achievements in the period

Summary of the objectives for the reporting period, work performed, contractors involved and the main achievement in the period.

| Project objectives | Work performed – status | Major achievement |
| --- | --- | --- |
| WP4 |  |  |
| Potential Applications of VR in Support to HF Methods and Definition of Layout of Case Studies | It has been achieved according to schedule | The most relevant HF methods and VR –methods has selected. D4.2 is delivered |
| Selection of future developed case studies | It has been achieved according to schedule | Scenarios of WP1 are being ranked according to their expected impact on several criteria. The top most scenarios will be further developed into case studies. D4.2 is delivered |
| Profile of a Database that could contain HF Data Collected with VR Approaches | It has been achieved according to schedule | Database structure has been defined. D4.1 is delivered |
| WP5 |  |  |
| The main bulk of the work in this period has been the prototyping of the Task Analysis Methodology. | It has been achieved according to schedule. | Questionnaire to be used in the fieldwork Taks Analysis Methodology proposed and adopted by partners to lead field work D5.1 Ready and reviewed |
| The execution of fieldwork for the extraction of requirements of HF and VR has been another milestone of this period. | Most of the fieldwork has been organised and the first series of visits to the End Users sites have been completed | The HF and VR requirements have been extracted from end users. - D5.2 Ready for internal WP review |
| The proposal of case studies to be developed in the prototyping (WP6) phase is another main objective of WP5 | The Scenarios short –listed in WP4 have been presented to the End Users at their sites and a common decision has been taken about the final case studies to be developed | General definition of case studies to be developed in the prototyping phase together with End Users. |
| WP6 |  |  |
| Platform final design | - Important features missing in the Delta framework have been implemented; - A prototype state manager is now available; - Network communication works and allows distributed applications. Master and satellite applications can communicate correctly now. | State Manager |
| Platform final design | - First implementation of the library is available and working and it’s integrated with the state manager; - Only a few basic components added so far, still waiting for detailed input from HF partners; - This will evolve while developing applications. | Component library |
| Platform final design | - Interactive rendering of complex 3D models available; - Basic interaction implemented, allowing free navigation in complex 3D models, and including collision detection; - Work ongoing on trackers. | Satellite application |
| Platform final design | - Design completed, implementation still ongoing; - Sample materials created (Demo available); - Interface with Plant Model Builder well defined and ready to be used. | Material system |
| Platform final design | The platform for now can support tasks of 3 types: - Single (Atomic action); - Ordered list of atomic actions; - Group of atomic actions to be executed in any order. | Task modelling |
| Platform final design | - Interaction with a 3D model demo created showing communication with CLIPS (open-source rule-based system); - Integration of CLIPS into platform almost completed. | Rule-based module |
| Platform final design | - First prototype interface to DynSim now available and working; - Need to extend it and to better define messages exchanged with state manager. | Process simulator |
| Platform final design | - The Delta3D framework provides advanced logging features. KITE has evaluated them and has examined in details the kind of information that can be logged; - A tool that reads a log file and extracts it in tabular format is available for easier evaluation of the file contents. Useful for merging data into DBs. | Log manager |
| Platform final design | - A first version of the Builder interface is available; - Several functionalities implemented (import of 3D objects from component library, visualisation of the 3D models, and hierarchical modification of the scene, set objects’ parameters); - A document describing the functionalities will be discussed with HF experts based on the 1st version of the PMB. | Plant Model Builder |
| WP10 |  |  |
| New VIRTHUALIS.org | Still working to improve the website and backend | Website Online |
| Definition of coordinated items of communication to be produced and definition of VIRTHUALIS Colours and Pantones | Ready | VIRTHUALIS Colours and pantones ready |
| VIRTHUALIS Font | Ready | Font ready |
| VIRTHUALIS leaflet and poster | Ready | 1st VIRTHUALIS poster and leaflet |
| VIRTHUALIS newsletter | Ready | 1st newsletter ready |
| VIRTHUALIS artworks and images for all communication items VIRTHUALIS cover for CDs and DVDs, and new VIRTHUALIS template for presentation | Ready | Images for all communication items |
| Dissemination Strategy | Ready | Dissemination Strategy defined |
| WP11 |  |  |
| Market Analysis | Deliverable 11.1 is submitted and updated three times during the period May-October 2006. The constant updates reflected the need of ensuring up-to-date information on the deliverable, since the VR market is constantly evolving. | Definition of the current VR Market. Analysis of the current VR projects. Assessment of the current software that is used for safety audit and training from industries as a basis for VIRTHUALIS comparison and development. |

### Objectives for the reporting period

WP4

The first objective of this WP is to evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions, i.e. Training, Safety Analyses, Safety management & audit, Accident Investigation.

The second objective is to follow up a preliminary design of a Database on HF data that will enable the harmonisation of information derived from applying VR for different uses associated to HF impact on safety (Risk Assessment, Training, Safety Audit and Management).

WP5

The goal of WP5 in the reporting period has been first to investigate and shape end-users' REQUIREMENTS regarding the new VR technology and then to present the spectrum of tools to be developed with a user-centred approach in the prototyping phase of the VIRTHUALIS project, which will be composed of a toolbox or platform, with the brand name SafeVR, and of four tools by developing four corresponding applications. The platform will be common to all tools and will enable them to run a case study by the use of a common representation environment. Each of the four tools will have the potential to perform a separate safety action, namely on an accident investigation, safety management & audit, training or on a risk assessment related activity.

WP6

Concerning WP6 the work has been focused on the needs and modules that need to be developed to create an integrated VR tool that will assist designers, plant operators, plant managers and safety engineers to carry out safety related tasks. At this stage of the project the work has been focused in implementing the SafeVR platform, thus the platform where the VIRTHUALIS applications will be adjoined including various levels of implementations ranging from architectural to particular modules.

WP10

For WP10 the objectives can be summarised as follows:

- Individuate VIRTHUALIS-relevant Target Groups and Contact channels.

- Disseminate VIRTHUALIS technology and results to the general public and to Target Groups

- Finalize operational Dissemination Items

WP11

Updating the initial results of the market analysis was the milestone of the reporting period, since the VIRTHUALIS consortium based a good proportion of the Business plan and strategy to the existing products and services that competed with the final product in the VR market. The D11.2 is the deliverable that contains extensive information for the current market and contains information from numerous partners of the consortium. The objective has been met clearly, and the existing document is a very good basis for the work that will commence during the next months of the project and it will be finalized during the last reporting period.

WP12

### Work performed

WP4

WP4 has completed successfully its work in the reporting period. The tasks have been performed according to flowing plan:

1. Literature Review (Coordinated by JRC who withdrew from the project in June 2006. See section 1.4)

2. Definition of Models and Methodologies (Coordinated By VTT)

3. Definition of HF Database requirements, specification and structure (Coordinated By TCD)

4. Identification, selection and elaboration of case studies (Coordinated By HIT)

Each task covered the four safety actions tackled in the project, namely Training, Safety Analysis, Accident Investigation and Safety Management.

WP5

WP5 has finished successfully its work in the reporting period. The tasks have been performed successfully and achievements made with reference to planned objectives comprise: a) the prototyping of the Task Analysis Methodology, b) The execution of the fieldwork for the extraction of requirements of HF and VR, c) the proposal of four case studies to be developed in the prototyping (WP6) phase and d) the production of three Deliverables, namely D5.1, D5.2, D5.3, where all the above information is contained.

WP6

The work that has been performed included various aspects of the platform design that was specified in D6.1 and D6.2. Concerning the master and satellite applications, interactive rendering of complex 3D models is now available. Additionally user interaction mechanisms have been developed to allow for navigation in 3D complex environments (models). Also support for a series of commercially available tracking systems has been included. Support for rule-based systems (CLIPS) has also been provided allowing for interaction with 3D models. Concerning task tracking, the platform now supports three levels of tasks: Atomic, Ordered list of atomic and group of atomic actions and their execution is allowed in any order. Full and bi-directional communication with process simulation is supported with full interface to DynSim allowing for full communication with the platform and able to send/receive messages to/from the process simulator. The supervisor station is also ready, including all the related UI for the supervisor to perform certain tasks including scenario load and start/stop, message exchange display between the applications, etc.

WP10

Concerning WP10 and the work performed it can be summarised as follows:

- Internal and External Dissemination:

Communication Items as per 10.3

Website

Dissemination Strategy

Contact research

Dissemination Procedures

VIRTHUALIS External Disseminations (details below)

WP11

Reporting on new market trends, services, existing software, safety features and simulation procedures, all aided towards the completion of D11.2 as an addition to the successful D11.1. The report has been delivered for review, reassessed based on comments and then submitted to the EC. The D11.2 is a living document that needs to spot the activities on a constantly changing market environment, so partners (of WP11 mostly) are expected to update the information on the report in frequent time intervals, with new information and data.

WP12

### Contractors involved

WP4

The contractors involved in the elaboration of WP4 are presented per Task in the following: 1.) Literature Review has been led by JRC with the participation of UNITO, TUC, LIU, IFF, INERIS and RISOE.

2.) Definition of Models and Methodologies has been led by VTT with the participation of UNIMI, POLIMI, INERIS, DEMOS, DAPP, STUBA, RISOE and KITE

3.) Definition of HF Database requirements, specification and structure has been led by TCD also in charge of D4.1 with the participation of KITE, ICCS, LIU, DAPP, UNIMI,  TECNATOM and VRMMP.

4.) Identification, selection and elaboration of case studies has been led by HIT also in charge of D4.2 with the participation of VTT, POLIMI, VRMMP, STUBA, ICCS, TECNATOM, BP, CARBID-FOX, SADACHIT, TOTAL, STATOIL and S-VURUP

WP5

The contractors involved in the elaboration of WP5 are presented per Task/Activity in the following: a) The Task Analysis Methodology has been led by TCD, also in charge of D5.1 together with LAAP5, INERIS with the participation of DEMOS and TUC; b) The Training Task has been also led by TCD together with DEMOS being both in charge of organising the fieldwork for developing the training case study and the requirements for this area with the participation of HIT, STUBA, TUC, ICCS and BP; c) DAPP has been in charge of the Task Risk Analysis and of D5.2 together with the organisation of the fieldwork for developing the risk analysis case study and the requirements for this area with the collaboration of RISO, STATOIL, POLIMI, DEMOS VTT, Mw and S-VURUP; d) LAAP5 has been in charge of organising the fieldwork for developing the Accident Investigation case study and the requirements for this area with the help of LIU, IFF, UNIMI, DEMOS, TOTAL and CARBIDFOX, e) INERIS has been in charge of organising the fieldwork for developing the Safety Management case study and the requirements for this area together with TCD, TNO, UNITO, VRMMP, EXIMIA, SADACHIT and f) DEMOS has been in charge of D5.3 with the input of all four Task Leaders, TCD, DAPP, LAAP5 and INERIS.

WP6

The main contractors involved in the WP and their particular role for the reporting period are the following:

- ICCS (WP leader, user interfacing, User input – VRPN, supervisor station),

- VRMMP (WP leader, master & satellite applications)

- IFF (Plant model builder)

- LBORO (Dynamic simulations, rule based system - CLIPS)

- TNO (networking, master & satellite applications)

- MW (Modelling)

- POLIMI (Process simulator interfacing)

WP10

The main contractors involved in this reporting period are the following:

- POLIMI

- DAPP

- CERTH

- IFF

- ICSS

- UNIMORE

- VRMMP

WP11

CERTH/HIT as the leader of the WP, coordinated the action of reporting, getting info from all WP 11 partners that were involved with the market analysis, namely:

- ICCS

- FhG

- DEMOS

- POLIMI

- KITE

While the partners with less man power like CRAIM UBB and EUROGIF were aiding towards the editing, correction and referencing of reports.

WP12

### Main achievements

WP4

The WP4’s main achievements of the reporting period are:

- Definition of technical requirements for the preliminary design of the database

- Definition of VR-model per HF-methodologies

- Identification of the VR application boundaries and correlations with requirements of HF methods

- Prioritisation of the case studies according to the impact expected from the application of VIRTHUALIS technologies.

WP5

The main achievements of the reporting period are: a) the Questionnaire that has been used in the fieldwork, b) The Task Analysis Methodology developed within WP5 and then adopted by partners leading the field work, c) The HF and VR requirements have been extracted from end users regarding the use of the new technology, d) The general definition of the four case studies to be developed in the prototyping phase together with the End Users according to the priorities set by the VIRTHUALIS EB.

WP6

The main achievements can be summarised as follows:

- Master Application, satellite application and tracking

- Rule-Based system

- Task-Tracking system

- Full bi-directional communication with process simulation software

- Supervisor station to start/stop simulation, load particular scenarios, watch users, message exchanging etc.

The work has been demonstrated at EB level with two DEMOs the first taking place in Brussels in October 2006 and the second in Turin in April 2007. The former DEMO showed to the whole consortium the functionality provided by the SafeVR platform elements whereas the latter showed more advanced features of the platform.

WP10

The main achievements in this reporting period are the following:

- 10 Paper Publications to major International Conferences;

- VIRTHUALIS Presence to 10 International Events;

- Finalizing of VIRTHUALIS Communication Material;

- Conceptualization of VIRTHUALIS International Conference;

- Enhancement and implementation of VIRTHUALIS Dissemination Procedures (as per Knowledge Protection and Dissemination efficiency);

- Independent and field-research resulting in The information acquired constitutes an overall picture of VR state of the art in the areas of Plant and Oil Facility Design, Safety Analysis and Accident Analysis and include the top 50 Engineering Firms, top 50 Contractors and more than 150 VIRTHUALIS-related companies and contacts.

WP11

Obviously the finalization of D11.2 as the updated market analysis, stands out in the main achievements. However, special reference needs to be given to the creation of the questionnaires about the CBA/CEA analysis that will be included in the D11.3 deliverable during the final months of the project. The questionnaires are ready to be circulated to industrial partners.

WP12

## Problems encountered and corrective actions

This section presents the changes occurred in contractors’ responsibilities during the reporting period.

WP 0

Given the complains expressed by several partners concerning the lack of efficiency of the Quality Management, EB members asked the QM, during the meeting held in Milan on 9th June 2006, to improve the aspects pertaining to the project  procedures, schedules and templates. In particular, they recommended the QM to be proactive.

At the last EB Meeting organized in Brussels, on October 12th 2006, quality issues have been raised again, as the situation worsen, and members agreed to nominating a vice-leader, for a 3 months period, to follow closely with the actual team the quality management activities.

A review of the progresses shall be made and a decision will be taken at the next EB meeting foreseen at mid December.

The QM decided autonomously after the EB Meeting to resign both from the position of the quality manager of VIRTHUALIS project and from the VIRTHUALIS EB, as of November 1st, 2006.

The QM shall however continue performing the Deliverables’ reviews till the end of December 2006.

Being quality a pressing issue to address without any further delay, it has been agreed that the Project Coordinator investigates who, within the consortium, could be the best candidate and go back to the EB members with a proposal.

### EB Composition

Inclusion into EB of a Process & Simulation Manager.

Maurizio Rovaglio has been nominated during the last EB Meeting, Process & Simulation Leader, i.e., the person in charge of developing the links with “the existent”, i.e., dynamic process simulation, fluids dispersion, fire & explosion simulations, and the like.

From an operational standpoint the decision making flow will not change significantly. In practice, this means that the two technical managers, i.e., Philippe Cabon for the HF part & Waleed Salem for the VR one, will have to involve the P&S Leader when their decisions could impinge the link with the existent, and vice versa. On the contrary, the two decision making processes, i.e., the HF & VR and the P&S one, will go in parallel as done so far.

WP 4

A change in WP4 leadership was made after withdrawal of JRC who led WP4 until June 2006.  The leadership was then assigned to VTT.

Due to the strong overlap between WP4 and WP5 activities the EB decided to conclude WP4 activities by M18 (October 2006) and finalise WP4 deliverables by that date

WP6

A change in the roles of HF experts inside WP6 has been made to optimise the development work inside WP6 and avoid wasting resources by having a dedicated group of HF experts inside WP6. This dedicated HF group inside WP6 provides VR experts of WP6 with the HF support needed to create the safety applications and interlinks WP6 with the newly established WP13 (handbook). This HF group has competencies in usability and interface design as well knowledge in the safety application under development. This group consists of LAA-P5, UNITO, UNIMI, POLIMI and TUC.

WP12

After withdrawal of JRC who led WP12 until June 2006, it has been decided that POLIMI will temporarily take over the leadership until a suitable substitute will be found.

At the last EB it was decided for WP12 to change strategy and investigate with the pertinent authorities and bodies, i.e., EC, CEN, and the like, the procedure for the standardisation process, in order to figure out the feasibility of a standardisation process, and maybe starting it, within project activities and before the project ends.

Seen the strategic relevance of the WP, it was agreed that, should not be possible to find a suitable candidate internal to the consortium, an external institution will be searched for. In the meantime, POLIMI will keep searching and investigating how this can be done.

# Workpackage progress of the period

Provide an overview of the actions carried out in the reporting period, based on the workpackages (with exclusion of the Management workpackage) which were active or planned to be active during the reporting period. A section as 2.1 or 2.2 is needed for each active work package.

## WP 4 - Impact on Safety Actions

### WP 4 - Workpackage objectives and starting point of work at beginning of reporting period

The first objective of this WP is to evaluate and integrate the peculiarities and goals of HF methods and VR technology for enhancing safety actions, i.e. Training, Safety Analyses, Safety management & audit, Accident Investigation.

The second objective is to follow up a preliminary design of a Database on HF data that will enable the harmonisation of information derived from applying VR for different uses associated to HF impact on safety (Risk Assessment, Training, Safety Audit and Management).

After a reorganization of the work in WP4 it has been decided to distribute the work into four parallel tasks instead of the three initially specified. These tasks are:

1. Literature Review (Coordinated by JRC who withdrew from the project in June 2006. See section 1.4)

2.Definition of Models and Methodologies (Coordinated By VTT)

3. Definition of HF Database requirements, specification and structure (Coordinated By TCD)

4. Identification, selection and elaboration of case studies (Coordinated By HIT)

Each task covered the four safety actions tackled in the project, namely Training, Safety Analysis, Accident Investigation and Safety Management.

A change in WP4 leadership was made after withdrawal of JRC who led WP4 until June 2006.  The leadership was then assigned to VTT as of July 2007. The strong overlap between WP4 & WP5 was reported to EB and followed by the EB decision of wrapping up all results of WP4 in M18 and fine tuning and utilising these results in WP5 and WP6.

Following the scheduled activities for each of the listed tasks, all the four tasks have concluded their activities in M18. The results have been reported in D4.1 and D4.2

### WP 4 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

The literature review task provided an information background for all WP4 tasks and was an integral part of the results in these tasks as well as D4.1 and D4.2.

For the task “Definition of Models and Methodologies”, the work focused on the definition of relevant HF methods for the 4 safety actions (Training, Safety Analysis, Accident Investigation and Safety Management). Selection of the HF methods was based on the input from WP1, WP3 and from the literature review task. The selection procedure has been made in an interactive manner via a meeting of the HF-experts of the project in Dublin. Also identification of the VR application boundaries and correlations with requirements of HF methods has been defined within the framework of this task.  All these findings and results were integrated into D4.2: “Potential Applications of VR in Support to HF Methods and Definition of Layout of Case Studies”

For the task “Definition of HF Database”, the focus was on the definition of technical requirements for the design of the database, e.g., content management, classifications of various models and methodologies and safety-action specific information. The works and results of this task were integrated into D4.1: “Requirements and preliminary design of a Database for HF Data based on VR applications”

For the task “Identification, elaboration and selection of case studies”, the starting point was the 24 scenarios proposed and developed by WP1 of the project (phase 1). A methodology for prioritising these scenarios has been developed in WP4. Based on a prioritisation process that took into consideration the expected impact of these case studies as a building element in the VIRTHUALIS technology, these scenarios have been merged into a final list of 8 scenarios. Selected scenarios had been further developed into case studies (e.g., detailed sequences of events, specifications of the industrial working environment, human factors aspects, etc.). The results of this task have been documented in D4.2: “Potential Applications of VR in Support to HF Methods and Definition of Layout of Case Studies”

### WP 4 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

A change in WP4 leadership was made after withdrawal of JRC who led WP4 until June 2006.  The leadership was then assigned to VTT.

There has been the strong overlap between WP4 & 5, thus the EB decision to stop working in WP4 and simply wrap up what has been produced up to now.

### WP 4 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D4.1 | Requirements and preliminary design of a Database for HF Data based on VR applications | 4 | M15 | M17 |  |  | TCD |
| D4.2 | Potential Applications of VR in Support to HF Methods and Definition of Layout of Case Studies | 4 | M18 | M18 |  |  | CERTH/HIT |
| *) if available |  |  |  |  |  |  |  |

WP 4 – Deliverables List

### WP 4 - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |
| M 4.2 | Selection of the case studies to work on | 4 | M 18 | M 18 | CERTH/HIT |

WP 4 - Milestones List

## WP 5 - Requirement

### WP 5 - Workpackage objectives and starting point of work at beginning of reporting period

The goal of WP5 has been to first to investigate and shape end-users' REQUIREMENTS regarding the new VR technology and then to present the spectrum of tools to be developed with a user-centred approach in the prototyping phase of the VIRTHUALIS project, which will be composed of a toolbox or platform, with the brand name SafeVR, and of four tools by potentially developing four corresponding applications. The platform will be common to all tools and will enable them to run a case study by the use of a common representation environment. Each of the four tools will have the potential to perform a separate safety action, namely on an accident investigation, safety management & audit, training or on a risk assessment related activity

### WP 5 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

WP5 has finished successfully its work in the reporting period. The tasks performed and achievements made with reference to planned objectives, together with the contractors involved are presented in the following Table.

| Task/ Activity | Partners and roles | Workplan | Date of Completion |
| --- | --- | --- | --- |
| 0.Task Analysis Methodology | TCD has been in charge of D5.1 together with LAAP5, INERIS Participants: DEMOS, TUC | The first draft of the D5.1 was ready at the end of May 2006. It has undergone the foreseen internal quality review and the authors had received the reviewers’ comments in the late July. The WP5 leader asked them to modify the D5.1 accordingly. In a SKYPE meeting among TCD and DEMOS in mid September it has been agreed that the thorough review of D5.1 will be completed after the ending of the fieldwork, which came to an end at the beginning of December 2006, from which important findings on the TASK Analysis methodology application have been drawn. TUC has, in parallel, prepared documents related to both the Task Analysis Methodology of all four Safety Areas and to the requirements of each one of them which have been used in Deliverables 5.1.and 5.2. | End of December 2006 |
| 1. Task Training | TCD together with DEMOS has been in charge of organising the fieldwork for developing the training case study and the requirements for this area. HIT, STUBA, TUC, ICCS, BP | Fieldwork has been initiated with a visit to a BP Saltend site in England, where a multidisciplinary team composed by HF and VR experts together with Process engineers and the Project co-ordinator visited the site for 3 days in July (18-20). A follow up visit has been held in early December 2006. A report on the findings of the visit (including simuscape presentation) has been prepared by TCD. An outstanding issue has been the confidentiality agreement, which needs to be signed between BP and the VIRTHUALIS consortium for further use of the obtained data. | End of December 2006 |
| 2. Task Risk Analysis | DAPP has been in charge of D5.2 and of organising the fieldwork for developing the risk analysis case study and the requirements for this area. RISO, STATOIL, POLIMI, DEMOS VTT, MW, S-VURUP | The first draft of the D5.2 has been prepared at the end of October 2006. It has been sent to internal quality review and the authors have received comments and updates. Fieldwork has been initiated with a visit to a STATOIL Stravenger site in Norway, where a multidisciplinary team composed by HF and VR experts together with Process engineers and the Project co-ordinator visited the plant for 3 days in September (19-21). A follow up visit has been held in late November 2006. A report on the findings of the visit (including simuscape presented) has been prepared by the participants of the visit. Another preparatory visit has been made to SLOVNAFT, Slovakia in order o investigate their potential needs and willingness to offer data for a case study. A follow up visit will be programmed in due time. A follow up meeting to work on fieldwork findings has been held in Athens, on December 5&6, 2006 to finalise the RA methodology. | End of December 2006 |
| 3. Task Accident Investigation | LAAP5 has been in charge of organising the fieldwork for developing the Accident Investigation case study and the requirements for this area. LIU, IFF, UNIMI, DEMOS, TOTAL, CARBIDFOX | Fieldwork has been initiated with a visit to a TOTAL site in Belgium, where a team composed mainly by HF visited the site for 3 days in June 2006 on various days. A report on the findings of the visit (including the task analysis performed) has been prepared by LAAP5. A follow up meeting to finalise the work findings has been held in Paris on November 24, 2006. | End of December 2006 |
| 4. Task Safety Management Horizontal Task | INERIS has been in charge of organising the fieldwork for developing the Safety Management case study and the requirements for this area. TCD, TNO, UNITO, VRMMP, EXIMIA, SADACHIT DEMOS is in charge of D5.3 | Fieldwork has been initiated with a visit to a BP Saltend site in England, where a multidisciplinary team composed by HF and VR experts together with Process engineers and the Project co-ordinator visited the site for 3 days in July (18-20). INERIS has not participated in the follow up visit is of December 2006. However, in Parallel, INERIS has been progressing work with industries within France to formulate another SIMUSCAPE, the loading-unloading one. A report on the findings of the last has been prepared by INERIS. The first draft of the D5.3 has been prepared at the end of November 2006. However, as most Task leaders have completed their fieldwork at the beginning of December, the document has under upgrading till the end of January 2007. | End of December 2006 End of January 2007 |

### WP 5 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

WP5 started with a delay of two months owing to anticipated delayed input to be received by previous WPs. It was expected to finishes its works at the end of October 2006, but its leading team (PhII L and WP5L+TLS) decided to prolong its duration foe another two months, so as to compensate for the delayed starting and to conclude the fieldwork still on-going.

Possible delays to the smooth continuation of the work in WP6 (the main recipient of WP5's Deliverables) has, somehow been absorbed by the fact that all VR partners and developers in WP6 where participating in the Data collection in WP5, having thus direct access and opinion on the data collected.

### WP 5 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D5.1 | Methodology for VR tool design and case study development |  | 12 | 13 |  |  | TCD |
| D5.2 | Report on the necessary requirements for the application of HF+VR techniques to be used in the prototyping phase |  | 16 | 18 |  |  | DAPP |
| D5.3 | List of specific tools to be developed for Training, Safety Analyses and Auditing and Risk Assessment |  | 18 | 20 |  |  | DEMOS |
| *) if available |  |  |  |  |  |  |  |

WP 5 – Deliverables List

### WP 5 - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |
| M5.1 | Enlargment of the end users community | 5 | 10 | 10 |  |
| M5.2 | Development of questionnaire/tool for retrieving end users opinion on the proposed methodology | 5 | 15 | 16 |  |
| M5.3 | Checking of methodology acceptability by end users’ personel/philosophy | 5 | 15 | 18 |  |
| M5.4 | Adaptation of end users’ suggestion to the proposed methodology | 5 | 15 | 18 |  |
| M5.5 | Identification of end users need for the development of specific tools | 5 | 17 | 19 |  |

WP 5 - Milestones List

## WP 6 - Prototyping

### WP 6 - Workpackage objectives and starting point of work at beginning of reporting period

To create an integrated VR tool that will assist designers, plant operators, plant managers and safety engineers to carry out safety related tasks. The tool that will be created will be implemented based on the actual industrial and HF needs.

The VR experts in the consortium will work closely with the HF experts in designing and testing the tools. The VR experts will also work closely with each other to ensure that all the tools will share common features, models and program code.

The tools that will be created will be focused on two safety actions (of the four stated above) and they will both be applied to two industrial sites according to their needs to indicate the transferability of the created tool and enhance industrial support during the implementations.

### WP 6 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

The main target during this reporting period was to produce the version of the SaveVR platform based on feedback from user-needs and also technological improvements that were needed. A new demonstration integrating all the features have been produced and shown to the Executive Board members in April 2007.

The work implemented during this working period have concerned mainly the SafeVR platform and can be summarised as follows:

- Master and Satellite applications: Interactive rendering of complex 3D models is available,  while interaction has been implemented as well, allowing free navigation in complex 3D models, and including collision detection. A great support of tracking systems has also be included (supporting VRPN).

- Task modelling: The platform for now can support tasks of 3 types:

- Single (Atomic action)

- Ordered list of atomic actions

- Group of atomic actions to be executed in any order.

- Rule-based module: Interaction with a 3D model demo has been created showing communication with CLIPS (open-source rule-based system) while the integration of CLIPS into the platform has almost completed.

- Process simulator: Full support to DynSim simulator is now available and working. The platform can read and update any value to/from the process simulator now.

- Plant Model Builder: A first version of the Builder interface is available. Several functionalities implemented (import of 3D objects from component library, visualisation of the 3D models, hierarchical modification of the scene, set objects’ parameters).

Concerning HF resources in the WP, it was also decided that WP6-HF-related resources could be used for the preparation of the VIRTHUALIS Handbook. HF resources in WP6 should be more than enough for defining the usability. Then a good number of PMs can be devoted to editing of the Handbook. All this work will be moving to WP13, so most of the HF resources will be moving to WP13, while a dedicated group of HF partners will still exist in WP6 to act as the link between the technological and HF sides.

Concerning identified risks, it was indicated in the previous PAR that the state of work could be delayed 4-6 months due to issues in receiving WP5 inputs due to WP5 delays and also delays in deciding the first plant. To overcome the situation it has been decided unanimously to go for the benchmark application, i.e., develop it a first application. This will allow the consortium to:

- Catch up with the delay;

- Develop the first application more quickly as all data are available;

- Give the consortium extra time to deal with the non-disclosure agreement issue.

| Project objectives | Work performed - status | Major achievement |
| --- | --- | --- |
| Platform design | Interactive rendering of complex 3D models available, - User interaction implemented, allowing free navigation in complex 3D models, and including collision detection - Trackers support | Master application, satellite application, tracking |
| Platform design | - Interaction with a 3D model demo created showing communication with CLIPS (open-source rule-based system) | Rule-based system |
| Platform design | - Interaction with a task-tracking module to monitor user action. The platform for now can support tasks of 3 types: - Single (Atomic action) - Ordered list of atomic actions - Group of atomic actions to be executed in any order | Task-tracking system |
| Platform design | - Interface to DynSim now available and working - Full communication with platform - Able to send/receive messages to/from process simulator | Full, bi-directional communication with process simulation |
| Platform design | - Construction of the related UI for the supervisor to perform certain tasks. Construction of methods for messages exchange between the applications. | Supervisor station to start/stop simulation, load scenarios, watch users, message exchanges, etc |
|  |  | Plant model builder |
| 1st DEMO | First integrated demo to show to the whole consortium the functionality provided by the SafeVR platform elements | First demo show in the consortium meeting in October 2006 in Brussels |
| 2nd DEMO | Second demo to show more advanced features of the platform | Second demo shown to the Executive Board meeting in Turin in april 2007 |

### WP 6 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

1st Deviation: Restructuring the development plan inside WP6:

Deviation causes:

- A delay in consolidating and compiling VR requirements in WP5

- Solving the legal issues needed to protect industrial data and confidentiality

- The need for a new internal demo has arisen and therefore the dev team has placed a non-planned effort on this extra task (M21-M24)

These facts lead to a non-absorbable total delay of 5 months inside WP6. Since delaying the results of WP6 by 5 months does not represent a viable solution, there was a need for restructuring the development plan inside WP6 based on the following guidelines:

- reduce as much as possible the impact of the delays accumulated on the input side;

- integrate feedback received by HF and industrial partners during the two demonstrations; based on that, extend the SafeVR platform to include features that were not originally scheduled;

- Deliver the tools to cover the first two safety actions;

After discussion with Executive Board members (meeting, Turin, April 2007 after the second demo) and in agreement with technical managers and project coordinator, a revised strategy for the second part of WP6 has been identified. The main changes can be summarized as follows (corrective measures):

- Putting more effort than originally planned on the SafeVR platform, to extend its feature set;

- Optimize the effort on applications, also by slightly reducing their scope; in particular do not work on porting the tools to real site, but keep on working on the example developed internally (i.e., the gas plant developed by the PoliMi team, also referred to as the “benchmark site”).

- Close WP6 by M32 instead of M30, i.e. with a 2-months delay. This will allow the following work-packages (especially WP7) to start their work almost on time.

The description of the new development plan is provided in the document of next implementation plan. Here is an overview of the main modifications:

- 1st application will be the RA application based on the benchmark site (by M29). A second version of the same application will be released on M32 including features of the training safety action (RA+TR).

- 2nd application will be the AI application; as the tool – specified in WP5 – does not rely mainly on VR technology, some initial technical investigation will be carried out, in parallel with the detailed definition of functional specifications (by M32)

- For both applications, the functional specifications as described in the template of functional specifications (WP6 template) will be provided by a dedicated HF group, in the timeframe specified by the new WP6 work plan.

2nd Deviation: Creation of WP6-HF task force and reallocating HF partners to WP13 (handbook):

Deviation causes:

- The need of having a focused HF group (task force) inside WP6 that acts as an interface between VR experts and all HF experts of the consortium

- The need for allocating HF partners and resources to work on the handbook (previously scheduled in WP5 and shifted into a new Workpackage “WP13”)

Based on that it was agreed to (corrective measures):

- Split the HF partners of WP6 into two groups, one group working inside WP6 on providing necessary HF specifications for developing the tools and applications and;

- The second group which consists of the remaining HF experts will work inside WP13 and provide any additional support that might be needed to accomplish the work of WP6

### WP 6 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D6.1 | General Guidelines for System Design and Documentation | 6 | M14 | M14 |  |  | VRMMP & ICCS |
| D6.2 | SafeVR Prototype, Toolbox Design Document | 6 | M18 | M18 |  |  | LBORO |
| *) if available |  |  |  |  |  |  |  |

WP 6 – Deliverables List

### WP 6 - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |
| M6.1 | Completion of general guidelines for system design and documentation | 6 | M14 | M14 |  |
| M6.2 | Completion of SafeVR toolbox draft design | 6 | M16 | M16 |  |
| M6.3 | 1st release of SafeVR toolbox | 6 | M18 | M18 |  |
| M6.4 | Completion of specifications and design documents for the two Safety Tools | 6 | M18 | M18 |  |
| M6.5 | Application site selection and porting | 6 | M18 | M24 |  |

WP 6 - Milestones List

## WP 10 – Dissemination of Virthualis Technology

### WP 10 - Workpackage objectives and starting point of work at beginning of reporting period

· Increase public’s awareness of the project to the public

· Disseminate the results acquired by VIRTHUALIS to specified target groups

· Define VIRTHUALIS applications cases and define a plan for promoting them to managers of institutions, companies, and relevant stakeholders.

### WP 10 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

The work progress for this reporting period can be summarised as follows:

- Finalizing of Deliverable 10.1

- Finalizing of Deliverable 10.3

- Finalizing of Deliverable 10.4

- Versions for Print of VIRTHUALIS Communication Items

- Groundwork for VIRTHUALIS Demo

- Groundwork for the update of VIRTHUALIS Dissemination Procedures

- Upgrade to VIRTHUALIS Website (graphic update, contents, "My Virthualis" section)

- Contributions to Deliverable 11.2 (key VIRTHUALIS-related Companies and Products)

- Conceptualization and preliminary work for VIRTHUALIS 2008 International Conference to be held in Milan.

- Groundwork for long term Exploitation Plan

- Groundwork for VIRTHUALIS Contact Database

- Groundwork for VIRTHUALIS Contact Ranking (with the use of data mining technology for clustering)

- Groundwork for Contact Plan

- Finalizing of VIRTHUALIS Journal and Newsletter

- Coordination of VIRTHUALIS Presence during Dissemination Events

### WP 10 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

Regarding objective: "Definition of VIRTHUALIS applications cases": it was deemed more useful to postpone the application cases in a later stage of the project when more information will be available. Field research is currently undergoing.

### WP 10 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 10.1 | Review of Literature in Technology Transfer, Technology Concept and Usefulness Diffusion. | 10 | 18 | 18 | 2 | 2 | UNIMORE |
| 10.2A | Analysis of the Application Cases of Virthualis Tools and Methodologies | 10 | 18 | 40 | 2 |  | UNIMORE |
| 10.2B | Analysis of the Application Cases of Virthualis Tools and Methodologies | 10 | 20 | 40 | 2 |  | UNIMORE |
| 10.3 | Dissemination Materials | 10 | 18 | 19 | 2 | 2 | UNIMORE/POLIMI |
| 10.4 | Dissemination Plan and Strategy | 10 | 18 | 19 | 2 | 2 | UNIMORE |
| *) if available |  |  |  |  |  |  |  |

WP 10 – Deliverables List

### WP 10 - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |
| 1 | Preparation of the communication contact plan | 10 | 13 | 20 | UNIMORE |
| 2 | Identification of Potential Users | 10 | 20 | 20 | UNIMORE |
| 3 | Initial User Forum lists | 10 | 18 | 18 | UNIMORE |
| 4 | Website first update and structure | 10 | 18 | 18 | UNIMORE |

WP 10 - Milestones List

## WP 11 – Cost benefit & Socio Economic Impact of Virthualis technology

### WP 11 - Workpackage objectives and starting point of work at beginning of reporting period

	To extend the market analysis that was performed within the first 12 months of the project, depicting more efficient market trends.

To highlight organizational requirements for supporting the VIRTHUALIS application.

To perform a cost benefit analysis based in the creation of questionnaires that will be circulated to industrial partners

To evaluate the project’s results from a cost-effectiveness perspective

### WP 11 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

Updated version of D11.1 was supplied and based on reviewers comments an even more complete version was uploaded with the contribution of all partners. The deliverable D11.2 (the update of D11.1) is now available on the VIRTHUALIS and is a living document, receiving updates from all active partners in the WP and the consortium

After discussion with the project board and the executive board, the process of cost benefit analysis and strategic orientation has initiated, following steps that are chosen from the managerial department of the VIRTHUALIS. The initial questionnaires were created from WP11 partners, and some initial results were collected. The process is yet ongoing since the strategy of disseminating strategic decisions to industry requires extensive care and planning.

The initial guidelines of performing the Cost Benefit Analysis and Cost Effectiveness Analysis are ready and reported in an initial version of D11.3. However, the deliverable is not public yet, since the missing part is the aforementioned data from the questionnaires.

### WP 11 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

The initial planning for the questionnaires distribution was issued to begin after the publication of D11.2. However, discussions with the Executive Board of the project have shown that the process needed to be slowed down slightly until the situation with industries is well thought out and planned ahead. The virtual delay in the process will be sustained by reporting the D11.3 that will contain results from both the initial CBA/CEA and the questionnaires.

### WP 11 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D11.1 | Extended Market Analysis survey on relevant to VIRTHUALIS applications and services | 11 | 12 | 12 |  |  | CERTH/ HIT |
| D11.2 | Updated Market Analysis | 11 | 18 | 19 |  |  | CERTH/ HIT |
| 3 | D11.3 Cost Benefit and Cost effectiveness Analysis | 11 | 44 | 44 |  |  | CERTH/ HIT |
| 4 | D11.4 Cost Benefit and Cost Effectiveness Analysis Update and Strategic Planning formulation | 11 | 46 | 46 |  |  | CERTH/ HIT |
| *) if available |  |  |  |  |  |  |  |

WP 11 – Deliverables List

### WP # - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |
| 1 | M11.1 Initial Market Analysis survey results on relevant to VIRTHUALIS applications and services | 11 | M18 | M18 | CERTH/ HIT |
| 2 | M11.2 Initial Results derived from CBA questionnaires | 11 | M18 | M18 | CERTH/ HIT |
| 3 | M11.3 Business oriented criteria definition for the evaluation of the VIRTHUALIS applications from a business and a market perspective | 11 | M18 | M18 | CERTH/ HIT |
| 4 | M11.4 Collection of CBA/CEA questionnaires for Industries | 11 | M42 | M42 |  |
| 5 | M11.5 Strategy Decision for the VIRTHUALIS project products (EB decision along with WP11 partners) | 11 | M45 | M45 |  |

WP 11 - Milestones List

## WP 12 - WP Title

### WP 12 - Workpackage objectives and starting point of work at beginning of reporting period

### WP 12 - Progress towards objectives

Description of the tasks worked on and achievements made with reference to planned objectives, identify contractors involved.

### WP 12 - Deviation from the project programme and corrective actions taken\suggested

Identify the nature and the reason for the problem, identify contractors involved.

### WP 12 - List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| *) if available |  |  |  |  |  |  |  |

WP 12 – Deliverables List

### WP 12 - List of milestones

| Milestone |  | WP | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |
| N. | Description |  |  |  |  |

WP 12 - Milestones List

# Consortium management

This section focuses on the major organizational and operational issues surrounding the management of VIRTHUALIS project for the reporting period.

Chapters 3.1 and 3.2 describe the way VIRTHUALIS work progress is monitored and the actions taken to increase effectiveness and reduce deviations from the project work plan

Chapters 3.3 and 3.4 discuss respectively the main operational problems encountered and the major changes in contractors’ responsibilities, while chapter 3.5 recaps how sources of risk in the project have been assessed and which working and timing adjustments have been made.

In the last two chapters, are summarized correspondingly the meeting held and planned, and the linkages made with other programs and projects.

## Consortium management tasks

To enable preventing problems and reacting as and not after they arise, the reporting patterns have been reviewed and a new set of responsibilities has been established and communicated to all contributors as explained hereafter:

- To increase effectiveness and reduce misunderstandings in partners’ communications on tasks’ assignments and in particular, to avoid duplication of efforts and delays especially on activities updating and reporting, it has been decided and agreed upon by the EB members that each organization has to nominate 1 Technical representative and 1 Administrative person for administrative matters, i.e., cost reporting signatures (pure administrative things). Exception is made just for industry that is allowed to have 2 technical persons of reference, i.e., 1 at corporate level and 1 at operational one, and 1 administrative.

The technical representative has to take under his/her own responsibility the fulfilment of the activities assigned by the WP leaders and according to their role in the project.

He/She will be liable towards the project for the timely accomplishment of duties assigned to the organisation.

In practice this means that he/she will be the unique interface on technical matters, and the unique having the rights to delegate tasks internally to the organisation as well as to VIRTHUALIS partners.

All VIRTHUALIS Contributors have been already asked to communicate to the Project Management Office (PMO) their representatives.

- In addition, to a better monitoring of the technical work progress:

- PhLs have been asked to provide the project management with a report in sufficient detail on technical performance every three weeks.

- It has been also agreed to perform the Technical & Financial Reporting on a six-monthly basis instead of a quarterly basis, so as to avoid an excessive reporting workload.

### Problems occurred and actions taken

As for the reporting process, the following problems have been noticed:

- Control procedures are resisted by some partners who do not understand the benefits or necessity of using the formal controls of the work progress

- Information Partially reported by WPLs and PhLs on non- or poorly- performing partners,

- Only one factor, i.e., financial resources, is considered by some partners, yet others such as schedules and technical reporting are ignored.

To minimize these problems, PhLs and WPs leaders have been charged to actively support the monitoring process.

Further, to avoid poor technical reporting, at the last EB meeting it was decided not to accept reimbursement claims unless duly accompanied by a technical description of the associated work performed. In other words, the technical and financial reporting will be tightly linked and basis for expenses approval.

Same applies to deadlines, i.e., those not respecting deadlines will not be allowed to claim any reimbursement for the period they did not respect the submission deadline for.

The focal point of control is the work package as all activities – authorization, data collection, work progress evaluation, problems assessment and corrective actions – occur within daily activities.

PhLs who have the responsibility to manage all WPs activities, have been requested to immediately report to the PMO all problems that stem from lack of work and information quality, accuracy, timeliness, poor data collection, and the like.

They are responsible to aiding the management foreseeing and forestalling potential problems, and taking immediate actions as they arise.

As agreed upon during the last EB Meeting held in Brussels, whenever inefficiencies occur, the following correctives actions will be taken:

- WPLs should report directly to the management on non- or poorly-performing partners

- Non- or poorly-performing partners cannot claim resources for the concerned period.

A key issue is the confidentiality agreement, which needs to be signed among the industrial partners, i.e., BP, STATOIL and TOTAL, and the consortium for a further use of site specific data obtained during the fieldwork. Actually, industrial partners raised the point that just 5 years of confidentiality for their sensitive data are not enough as they normally require a minimum period of 20 years.

To resolve this issue, it has been decided to tackle this issue at project level instead of going for bilateral agreements. This means that the Consortium Agreement is being revised to extend the Non-Disclosure Agreement (NDA) from 5 to 20 years.

## Changes in the consortium

### Changes in contractors’ responsibilities

Due to the withdrawal of JRC, who led WP4 and WP12, VTT took over the leadership of WP4 and Polimi took over temporarily WP12 leadership.

At the last EB meeting held in Brussels, the Project Coordinator stressed the need of redirecting WP12 work towards a real standardisation process for the VIRTHUALIS technology.

Thus, it has been decided that POLIMI will take care of investigating the feasibility of setting up the process and, as far as a new suitable profile will be found, WP12 activities are momentary frozen.

## Project timetable and status

Project timetable and status, including an updated, frontlined barchart. Clarify changes and impact on the planned milestones, if any.

Overlaps between WP4 & WP5 were recognized, thus the decision during the last EB meeting held in Brussels on October 12th, to stop WP4 work and wrap up what has been produced up to date and to use the remaining resources for improving WP5 work.

- A postponement of the conclusion of WP5 work and a delay in the completion of D5.1, D5.2 by 1 month has been considered necessary, due to the later project start and to the confidentiality issues raised by the industrial partners BP, STATOIL and TOTAL during WP5 fieldwork.

- To overcome the risk of a deferment in WP6 work, due to the delay in receiving WP5 inputs, it has been unanimously decided at the conclusion of the VIRTHUALIS week organized in October at Total Offices in Brussels, to go for the benchmark. This will allow the consortium to develop the first application more quickly as all data are available; and will give the consortium extra time to deal with the non-disclosure agreement issue. This will let WP6 activities not to be delayed and to have some extra time to solve the issue of the NDA and to select which industrial site will be the first for testing.

The first scenario to develop as agreed by all industrial representatives is the representation of fluids dispersion.

It has been agreed in addition, that the HF group will split into two groups. One group will be devoted to work on the usability part of the application being developed, while the other one on the development of the VIRTHUALIS Handbook. POLIMI will formulate a proposal on how to proceed with the handbook, i.e., structure, tools to developing the handbook, resources needed and partners involved. A new WP for the Handbook development will probably be created and coordinated by POLIMI.

## Partners’ communication and meetings

| Title | Date and Place | Main conclusions |
| --- | --- | --- |
| Annual Plenary Meeting | 16-17 May 2006, Milan | Material uploaded in the intranet |
| Annual Review Meeting | 08 June 2006, Milan | Material uploaded in the intranet |
| Strategic EB Meeting | 09 June 2006, Milan | Material uploaded in the intranet |
| Tactical EB Meeting | 12 October 2006, Brussels | Material uploaded in the intranet |
| Strategic EB meeting | 21 December 2006, Brussels, TOTAL Offices |  |
| WP4 |  |  |
| WP4 Meeting | 15 May 2006, Turin | Status of WP4, Next steps and Deadlines |
| WP4 Developers Meeting | 30 May 2006, Milan | WP4 Development meeting |
| WP4 Meeting | 10 October 2006, Brussels | Status of WP4, Next steps and Deadlines of deliverables. |
| WP5 |  |  |
| Methodology development meeting WP5 | 9 May 2006, Sosterberg NL | Methodology development |
| WP5 Meeting | 15 May 2006, Turin | Status, Next steps, general organisation |
| Methodology development meeting WP5 | 24/5 and 31/6 2006, TOTAL | Fieldwork |
| Developers Meeting W5 | 7 July 2006, Paris | Development meeting |
| Methodology development meeting WP5 | in S-VURUP, Slovakia, 30 August, 2006 | Fieldwork |
| Methodology development meeting WP5 | in BP Saltend, UK 18-20 July, 2006 and 8-11 November 2006 | Fieldwork |
| Methodology development meeting WP5 | in STATOIL Stravenger, Norway 19-21 September, 2006 and 13-17 November 2006 | Fieldwork |
| WP5 Meeting | 11 October 2006, Brussels | Status of WP, next steps, VIRTHUALIS Demo, discussions on case studies, fieldwork, scenarios, cooperation with WP6, risks and issues, corrective actions and solutions. |
| STATOIL Fieldwork 2 | 13-17 November 2006, Statoil Kårstø plant | Detailed fieldwork and task analysis on Risk Assessment |
| Methodology development meeting WP5 | 4-5 December 2006, Athens | Methodology development, case studies selection |
| Several SKYPE meetings among Tls of WP5 | Once a week | Methodology development, case studies selection |
| WP6 |  |  |
| WP6 Meeting | 15 May 2006, Turin | Status, Next steps, general organisation |
| Developers Meeting | 30 May 2006, Milan | Development meeting |
| WP6 Meeting | 10 October 2006, Brussels | Status of WP, next steps, VIRTHUALIS Demo, discussions on handbook and HF resources, scenarios, cooperation with WP5, risks and issues, corrective actions and solutions. |
| STATOIL Fieldwork | 19-21 September 2006, Statoil Kårstø plant |  |
| VIRTHUALIS Week | 10-12 October 2006, Brussels TOTAL Offices | WP4, WP5 & WP6 Meetings on 10 and 11 October EB Meeting on 12 October |
| WP10 |  |  |
| Dissemination | Dissemination in EB meeting, Brussels, 12 October 2006 | Dissemination strategy to be submitted soon Newsletters and leaflet Final poster |
| Phase 2 |  |  |
| Coordination Meeting | 23 October 2006, Paris | Coordination about current and remaining work in phase 2 |

## Co-operation with other projects/programmes

### German Platform for Industrial Safety - IFF

A link with the German Platform for Industrial Safety was established through the IFF who is leading the focus group “Information Technology”. A presentation of project results is planned in the next plenary meeting of the German Platform for Industrial Safety (September 2007) with the purpose of achieving common synergies and utilising project results to push safety-related research with German stakeholders.

### Halden Reactor Project (HRP) Initiative – POLIMI

The HRP, despite focused on the nuclear sector (very much similar to the chemical & petrochemical ones), it is a very interesting and stimulating international initiative. Its main objective is to perform research on Human Reliability Assessment & Modelling. As such, it is very much pertinent with the VIRTHUALIS project. At the time of writing the HRP initiative is launching a benchmark study on existing HRA methods using the full scale simulator set-up at Halden (NO), i.e., a control room for nuclear power plants (with an innovative layout).

The idea is to link VIRTHUALIS project activities with the benchmark at HRP in order to see how the two initiatives can benefit from one another.

Potential reciprocal benefits can be synthesised as follows:

- Test the fuzzy tool under construction in VIRTHUALIS with real operators in a full scale simulator;

- Test the fuzzy tool in the virtual simulator to be produced by VIRTHUALIS and provide the HRP with a feedback on its reliability and usability;

- Provide the HRP with insights on how the fuzzy modelling could be adapted for being used even in the nuclear sector;

- Proposing the VIRTHUALIS approach to the HRP initiative as an innovative way of assessing Human Reliability even in the nuclear sector;

### V3S Project – INERIS

INERIS proposes to link the V3S project with VIRTHUALIS as there are strong complementarities between the two. The objective of V3S is to produce VR tools to help subcontractors (loading/unloading and maintenance) in their HSE risk management, decision making, and training. The innovative part of V3S can be summarised as follows:

- innovation based on a multi-agent approach

- use of ergonomic knowledge and artificial intelligence to develop “clever” cognitive agents (avatars);

- realistic simulation of phenomena based on physical laws;

- diagnostic and feedback solutions based on risk indicators.

The idea the two projects are working on to better capitalise reciprocal efforts is the following:

- V3S will build its tools on VIRTHUALIS platform;

- V3S will share HF data with VIRTHUALIS;

- VIRTHUALIS will use V3S results.

The “joint venture” will enable to better capitalise results coming from both projects, and to produce a synergy which product will certainly be greater than the simple sum of the two efforts.

### PERFRV2 – LAA-P5

Paris 5 is involved in the French PERFRV2 project and is going to participate to a second one (V3S, to be started at the end of this year) that could be linked to VIRTHUALIS. The PERF-RV2 Platform (Plateforme d’Etude et Recherche Française de Réalité Virtuelle), funded by the new French research agency (ANAR) since December 2005, aims to demonstrate that integrating virtual humans in the digital factory can improve the design process in terms of effectiveness and in terms of the ergonomics value of the working stations. In this project, our task is to provide task analysis formalism and models to support the implementation of ecological behaviours in virtual simulations of work. An associated project (V3S - Virtual Reality for Safe Seveso Subs tractors) is to be launched in the near future to develop a training application based on a subset of the formalism dimensions developed in PERF-RV2 with an extension to support intelligent tutoring and assistance functions. This latter project will also involve INERIS.

### Greek Platform for Industrial Safety - DEMOS

A link with the Greek Platform for Industrial Safety is created. DEMOS has been among the organisers of the launching event on October 18, 2006.

### HILAS and TATEM projects -TCD

TCD have been engaged in a detailed dialogue with other European Projects – specifically HILAS and TATEM – to develop a common approach to defining, understanding, modelling and describing operational processes including the related human and social processes;

# Year 3 - 01.05.2007 – 30.04.2008

# Project Objectives and major achievements during the reporting period

## Overview of general project objectives and relation to state-of-the-art

The key scientific and technical goal for the reporting period is to provide the second release of the VIRTHUALIS technology by developing the SafeVR platform and extracting the specifications of the safety applications that will be built on top of the SafeVR platform. The aim of this bit of project activities is that once the second release of the SafeVR platform of VIRTHUALIS is produced , the preparation for the development of practical cases is initiated in parallel to that activity together with the development of a set of IT tools to facilitate a global representation and analysis of each case study. In parallel to these activities the setting of the three case studies STATOIL, SONATRACH and TOTAL is progressed with STATOIL one to be ready for demonstration at the end of the reporting period.

## Summary of recommendations from previous review (if any)

No recommendations provided.

## Objectives for the reporting period, work performed, contractors involved and main achievements in the period

### Objectives for the reporting period

This section covers the project work development for the period M25-M36 in terms of tasks accomplishment and outcomes according to the objectives settled in the work plan. It also addresses the major problems encountered and describes how the consortium dealt with them.

### Work Performed

The work performed covers all methodological aspects from the consolodation of the HF methodology for performing the analysis, through the elaboration of the set of IT tools to back up the four types of Analysis (RAS, OSM, AIS and TR, the evolution of the HFlab to the actual creation of the Industry based case stadies to prove the technology potential.

### Contractors involved

Work Package 1 The contractors involved in the elaboration of WP 1 are presented per Task in the following: 1.1.1 TUC, POLIMI, TCD, DAPP, RELCONSULT, DEMOS, DTU, POLITO. 1.1.2 EXIMIA LBORO, IFF, VRMMP,DEMOS, SONATRACH,UNIMI, POLIMI,POLITO, TCD, TOTAL STATOIL 1.2.1 EXIMIA LBORO, IFF, TUC, VRMMP,DEMOS, SONATRACH,UNIMI, POLIMI,POLITO, TCD, TOTAL STATOIL DAPP, VRMMP, KITE,OVGU,INERIS, DTU. 1.3 VRMMP,ICCS, TNO,MW,IFF,POLIMI, STATOIL,SONATRACH, TOTAL 1.4 OVGU, DEMOS,STATOIL, UNIMI Work Package 2 The contractors involved in the elaboration of WP 2 are presented per Task in the following: 2.1 STATOIL, DAPP, DTU, LBORO, POLIMI, POLITO, TCD, OVGU, TECNATOM, TNO, UNITO 2.2 SONATRACH, DAPP, DTU, LBORO, POLIMI, POLITO, TCD, OVGU, UNITO, DEMOS,VRMMP 2.3 TOTAL, LBORO, POLIMI, POLITO, OVGU, UNITO, LAAP5, TUC, EXIMIA Work Package 3 The contractors involved in the elaboration of WP 3 are presented in the following: CERTH/HIT, POLIMI, UNIMO, TECNATOM, TCD, LAAP5, ICCS, INERIS, TUC.

### Main Achievements

- The HF methodology has been consolidated. - The IT tools set has been developed to a great extend - The HFlab has evolved - The RASVR STATOIL case study is operating.

## Problems encountered and corrective actions

During the concerned period the following problems have been faced: Transition from PHASE I to PHASE II - New product concept definition - New Partnerships - New NIP definition: - Partners' role and leaderships - Resources allocation - Scheduling and planning - New organization set-up PHASE II - Technical adjustments: - Task 1.1.1 delays As consequence of Task 1.1.1 leader TUC reporting (as forseen in NIPM25-M42) critical delays due to low reactions of some partners to contribute to work completion, PMO was activated to take actions to get the needed contribution. The bulk of Task 1.1.1 is completed successfully. - Safety barriers methodology and software integration into VIRTHUALIS platform On the way to the definition of Task 1.1.1. DTU has suggested introducing in the pipeline of VIRTHUALIS methodology the Safety Barrier approach, proposing the integration of their BowTie software tool. The proposal was warmly supported by Peter Kafka as deputy WPII-1 leader. The PMO activated to figure out both the IPR rights and maintainability issues associated with the proposed DTU tool integration, as well as evaluating the MM implications and task scheduling. The PMO decision was to accept the proposal, and plan its implementation in NIP M37-M54. - IPR related issue in FPE module development During the integration of FPE software module it was discovered that part of the first version of the code proposed by DEMOS was developed jointly with an institution not part of VIRTHUALIS consortium. To avoid IPR future conflicts PMO decided to rewrite the entire code, and assigned this work jointly to POLIMI and DEMOS. The work was completed on time. - Software development group set-up and harmonization During the kick-off meeting of WPII-1 the PMO has proposed that a programming task force was set up in a common place where the people responsible for the actual programming will work for a 3 month period in order to establish a common programming framework and understanding among the different IT-tools developer. This decision has been implemented and allowed to reach effective results in a very short time frame, with a limited number of human resources. - System functional specification During system software specification, Task 1.1.2, partners playing the role of end-users had difficulties in providing requirements and needs given the high complexity and innovation of the proposed tools. PMO in agreement with the task leader, decided to postpone detailed system specs and start software development to provide a version capable of demonstrating the major features to end users, thus adopting a structured agile approach. - HFLab development freezing for solving usability issues and better specs definition After the internal reviews of SafeVR platform in december 2007 and january 2008, the PMO decided to focus the activity on improving usability. The current state of usability was strongly criticized by PMO as well as by advisors Alessandra Re (HF expert) and Remo Galvagni (safety engineering expert). It was therefore decided to stop development and to drive the effort to improve usability. To this aim PMO has requested to the task 1.3 leader to prepare functional specification necessary to drive the improvement and to submit the specs to review to Peter Kafka. Moreover PMO has also taken the decision to submit a usability test to experienced field and control room operators. - Decision to stop Plant Model Builder development During the internal reviews of SafeVR platform in december 2007 and january 2008, the PMO observed that the Plant Model Builder module, implemented by IFF, had unclear purpose for the platform as well asa poor and elementary functionalities. Moreover the feature of plant model building can be perfectly satisfied by adopting powerful and solid commercial products. PMO has consequently decided to stop the development and reject the proposed module. - Decision to postpone development of interface to Configuration tool Configuration tool at the internal review time (january 2008) was still missing, being limited to the editing of an XML file describing configuration parameters. A better analysis on the experimental process highlighted the opportunity to offer to a supervisor person the possibility to control and change simulation parameter at run time also. The best solution to solve this problem is the integration of the HFLab with an OTS. The selected choice of adopting INVENSYS platform, as required at WPII-3 kick-off meeting, was frustrated by INVENSYS default. PMO has therefore decided to postpone configuration tool design and development to avoid wasting time and resources. - Kårstø plant model building Beginning of january 2008 was scheduled to start STATOILHYDRO case study plant model building by MW. Surprisingly PMO discovered at the WPII-2 kick-off meeting in Paris, that CAD data were already available in the hands of IFF since more than 8 months. Immediately contacted by PMO, IFF sent a CD, of non readable data. To find a solution to get readable data took a lot of mail messages exchange, eventually reaching the conclusion to ask new data to STATOILHYDRO. This time has negatively impinged on plant model scheduling, thus forcing MW to hire lately 8 graphics designer to respect deadlines. - Organization of field operators usability tests To experiment and test HFLab usability, in light of the forthcoming APM and ARM, PMO has requested to MW, as Demo Group leader, to take over the direction of the development group, to improve usability and organize the usability test. In addition PMO coordinated with STATOILHYDRO to identify and invite two skilled operators at the VR Lab of UNIMI partner in Milano in middle june 2008. - Anticipation of ALBA tool development and postponement of development of FTB and ESB On the basis of the specific use case to develop for STATOILHYDRO, i.e., from the gas release onwards, PMO, in agreement with POLITO, decided to develop the ALBA tool first and postpone development of FTB and ESB and of the relative solvers to be selected for integration in the IT Tools subsystem. - Change in TM development strategy to solve its integration with ALBA tool The analysis of functional specification has highlighted the strong correlation between task analysis and ALBA. Therefore PMO has decided to consider this requirement as highest priority and to ask the developers to solve the integration issue by providing a software module to link with ALBA. - Definition of the Knowledge Base module into development road-map Given the complexity of scenarios to test with VIRTHUALIS and associated data, the decision was taken to start the development of a knowledge base construction and its inferential engine. To this aim a task group has been formed. - Selection of software development environment and IPR issues related to SW development environment selection In agreement with EXIMIA task 1.2 leader, a software development platform suitable for a flexible and portable development has been selected. The decision of Java Enterprise environment was made of the basis of both technical power as well as IPR issues, to guarantee the absence of limitative licensing rules. - HF identification in STATOILHYDRO use case definition To arrive to an accurate definition of the STATOILHYDRO use case, a revision has been performed, and a daily guidance provided to the involved partners to help them to focus on the relevance of human factors. Such guidance, performed by the PMO, has produced a final deliverable that required a very light internal formal review. - Market analysis update Despite an initial set up of the market analysis update, which was organized in a first commercial analysis, followed by a technical one by IT experts, the INVENSYS defaulting and hostile actions have distracted PMO from following closely this activity. - Dissemination freezing for IPR issues To solve the IPR issues PMO appointed a law firm expert in EU legislation and IPR treatment in IT field. The recommendations to treat the disclosure of research results in a safe way have obliged the PMO to stop publications until the WPII-3 leader would have fixed rules. The defaulting of INVENSYS has extended the deadline beyond an acceptable limit. - Anticipation of Technology training activity to synchronize to product development PMO accepted the proposal by task 3.5 leader TCD to anticipate the activity on technology training, originally planned from july 2008. The reason of this decision was the necessity to synchronize technology training to an emerging new release plan, aimed at having a first beta release by december 2008. - Programmers recruitment The strong change in project focus on system development, has made evident the strong need to strengthen the development capabilities in terms of human resources and specific skills. This was even worsening by the withdrawal of TNO partner. PMO has directly activated partners to search for resources during the kick-off meeting on WPII-1 held in Milano on december 2007. Most responding partners have been: MW (2 programmers, 8 graphics designers), UNIMI (2 programmers) and TCD (1 programmer)..

# Task progress of the period

| ## WP1 Task6 RASVR STATOIL Case study |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP1 Task6 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| This WP is responsible for producing the first version of the Risk Assessment application. As it has been decided during the project restructuring – and as described in the new NIP, this work-package will provide the basis for the future development of the HFLab in the context of (IS)2 platform. Within the first two years of the project, the focus was on gathering end-users needs and creating the first version of the VIRTHUALIS platform. The goal of the remaining part of WP6 was to develop the first prototype of the RAS application and to deliver a first complete version of the HF Lab. These tools will then be passed to WP II.2 for their validation and fine-tuning; the HF Lab will be also passed to WP II.1 for further development. The main results of this work package have been available at the end of Month 32. The starting point for this work package was to take the output from the previous WPs on hardware and software reviews and the end-users’ requirements into consideration. This has informed the decision of hardware and software development system selection and the overall design of the tools. A common design and coding standard has been agreed from the outset for all VR partners. |  |  |  |  |  |  |  |
| ### WP1 Task6 – Progress towards objectives |  |  |  |  |  |  |  |
| To achieve the objectives of the reporting period, the VR experts in the consortium have been working closely with the HF experts in designing and testing the tools. Also, the feedback received from industrial partners (the end users) was constantly evaluated to check which additional features might be needed in the SafeVR platform and eventually those features to be implemented. The first version of HF Lab tool will be delivered as a result of this WP. In the first part of WP I.6, two demonstrations of the SafeVR platform features have been prepared and shown (one to the whole consortium and the other only to the Executive Board). These check-points have allowed the VR team to collect initial feedback both from HF and industrial partners and to introduce the notion of the HF Lab. In particular industries have identified potential features that would make the HF Lab even more interesting for their applications; the most relevant example in this sense concerns the gas-dispersion models. Industries have asked to consider integrating to systems that can compute the effect of fluid releases (effects such as gas clouds, pool fires and so on) as this is a relevant element for them. In the beginning only the integration of the gas-dispersion models had been decided; other features will be evaluated in the course of WPII.1. These requests must clearly be addressed at the platform level as they are not application- specific. Therefore, WP I.6 has allocated more effort than originally planned on the SafeVR platform and on the HF Lab, even in its second part. WP I.6 completed the applications using only one dataset, i.e. the gas plant model and process simulation created internally. This implies that WP I.6 did not port applications to any real site provided by industries. Such a decision has been agreed with the industrial partners as they recognized the available dataset as a meaningful example for their activity. Therefore, rather then putting effort on porting the tools to real sites, for which the data would have to be prepared, WP I.6 has kept on working in the selected example and will move the saved effort to the platform. For this reason, the HF Lab and the RAS application are based on the benchmark plant created internally by the VIRTHUALIS group. More analytically the tasks and modules designed and developed can be found in the description that follows: - RA Specifications This task has focused on gathering, analysing and producing the final RA specifications as extracted from the actual industrial and HF partners concerning requirements do-ability, resources needs and general planning. It has been led by LBORO with the aid of all VR partners and with a restricted group of HF partners (with expertise in Risk Assessment and in Human-Computer Interaction). It has thus resulted into the production of the specification, design, problem solving and documentation of the Risk Assessment Tool v1 (first release). The document has been split into various sections including a short introduction and the SafeVR risk analysis tool (the HF Lab) and then proceeds into defining the high-level requirements. The document also provides a features description and also an overview of the things to be modelled into the virtual world as well as the workflow and UI of the separate applications to be developed (MasterOfLab Configurator, Supervisor Station and Player User Interfaces – Control Room, Supervisor station and Field operator). Further to this several aspects have been identified, designed and specified for several key components missing from the Risk Assessment Tool specifications, including a Control Room Operator’s Graphical User Interface and a Supervisor Station for the Safety Analyst running the HFLabSession. The document closes with a summary of future implementations. These documents described (or parts of them) have been included in the Deliverables D6.3 and D6.4 due for M32. - AI Specifications During this task the Accident Investigation specifications have been defined starting from similarities and differences of them with the Risk Analysis and Training ones as well as investigation of possible overlapping between them. This task has been led by mainly IFF and LBORO having quite good experience from the extraction and definition of the RA specifications definition. The document includes features descriptions involving offline tools configuration, preparation of the accident investigation session, common understanding of features facts, as well as results checking and analysis management. Additionally the document extends to dissemination issues such as re-usage of existing applications dissemination but also constraints in the implementation plan that could be foreseen and the actual implementation plans. The document is now frozen due to different modeller used in the project workplan, but has resulted to an analysis of future evolutions of the applications/tools. This document will be of particular importance when starting implementing the actual AI tools. - Platform (several components) In the HF Database and Post-Process tool, KITE was the partner responsible for this task. This has involved the design of the HF database Development of the first version of the design of Results Database and ended with the draft and publication on VIRTHUALIS intranet of the document “Results Database Design v1.0”. Further to this, KITE in cooperation with the other VR partners (VRMMP & LBORO) of the consortium has worked on the study and choice of the technical tools (programming language and database) for the development of the “log post-process” tool. This has resulted into a solution for post-processing the simulation log files. Further to this, several investigations about the DB tool were made concerning events reconstruction and retrieval from the log file of Delta3D relying basically on the task tracking module responsible for capturing players’ actions. Finally several approaches concerning the integration of the tool with the rest of the modules have been investigated ranging from c++/JNI to Python solutions. – Environment and Components This task has covered work concerning both the improvements on the benchmark 3D model and the SafeVR platoform features. First, it has involved the inclusion of a new set of real-time particle system in the VIRTHUALIS engine, required for new smoke and fire effects. This had required the programming of a new vertex and pixel shaders to be placed on top of the Delta3D model. Additionally this task has also included new models creation regarding the plant hydraulic pumps with more detail. For this it was needed to convert the geometry for the realtime applications, and insert it in the plant of benchmark. The environment lighting with new set of LightMap and Radiosity solution was implemented and applied with 3DSTUDIOMAX the new set in the Osg final file for the benchmark application. This work was carried out mainly by MW, in coordination with VRMMP for interfacing correctly to the platform. Concerning environmental setting VRMMP and MW developed a new set of dynamic environment configurations, like CLOUD/RAIN and NIGHT environment. This task required a relevant effort in modifying the texture management system and the radiosity for the new set of lights. A new set of CLOUD/RAIN lightmaps and Textures was created; currently some dedicated effort for the Night version of the new Benchmark is in progress. This last part has been carried out jointly by MW (modeling and lighting) and VRMMP (implementation). – Development Servers and Delta3D engine Releases The VR group is constantly using the development servers that VRMMP has set-up and monitored up to now. During this reporting period these services needed to be upgraded and also the apache/mysql part of the server was reconfigured to allow for bugzilla (bug reporting tool) to run properly. The subversion repository management has required also some effort aimed at regular synchronisation with the Delta3D latest releases while also minimize external dependencies, by both relying on external Subversion repository and trying to stay on the same version of libraries used by the framework that the system relies upon (for example use on the same Qt binaries provided with Delta). – Dynsim Process Simulator (driver update) The driver for the Invensys’ Dynsim (process simulator) has been redeveloped in order for it to support a native API provided by Invensys , improving the control on the simulator and allowing to run it on a different machine and specifying from within SafeVR which simulation to load, when to run it, etc. Furthermore, the interface module better uses the platform communication and only transmits useful data, avoiding redundant information and custom messages factors that would affect negatively the network utilisation - Gas Dispersion Model (now called Physical Accident Simulator) module The Gas Dispersion Model (GDM) module has been quite questioned during the project 2nd review but its inclusion was particularly encouraged by several partners and it has been decided to be included. The core routine has now been implemented by the POLIMI group and the related actors were developed for support in the platform (VRMMP’s work). A specific platform component for interfacing to this module has been developed by POLIMI, in coordination with VRPPM for interfacing it to the platform. The special effect of fire simulation and fire updating according to the GDM calculations (in real-time) has been developed, however the leakage misses a representation for the moment. – Task Tracking Module A first version of a Task Tracking module has been implemented and is working; it takes a procedure description from an XML file (which might include recursively nested sub-procedures). In later releases and when the configuration tool will be developed this module will be taking direct feedback from the IT Tools, in particular the Task Modeler; this will be part of the work of WP II.1. Investigation of this module’s requirements has taken place, regarding its automatism level and its communication with the DB tool. - CLIPS & Rules This task has involved the development of CLIPS rules & facts and also updates and maintenance of the ClipsClient and pSimProxy components of the HFLab, including debugging and bug reporting. Some code cleanup and optimization has occurred in the reporting period, so that the CLIPS module now relies of default Delta messages rather than using custom one. – Record/Playback Record & playback functionality has been tested and the first results show that it works as expected (playback of course happens on a single station only).. This means that while the simulation is running simultaneously on multiple machines, the playback is only run on a single one, though including the actions performed on all the different actors who took place in the simulation. The real verification of this feature will happen after the RA tool is completed anyway, as different complete sessions need to be recorded for proper testing. It is expected that the feature itself might require some debugging later during WP II.1; it will also be possible to extend it and to better define the user interface to use for it. - General SafeVR platform features several specific features have been developed that apply to the whole platform. They can be summarized as follows: - Better handling of data paths, also using EnvVars values - Added support for collision meshes, lightweight geometry to be used on the physics engine instead of the more detailed geometries for visual rendering - Tweaks to Networking module to correctly retrieve IP address / machine names - Added an svn patch folder to collect patches needed to external modules we depend on (mainly delta3D) – this is needed when bugs are not promptly corrected on official repository – Enhancement to ScenarioMessage, which collects all info needed to run a simulation. - Added a weather actor and visual and audio representation of wind and precipitations (rain and snow so far) – Weather – Material – Special Fx As required from the RA_tool specifications, it’s important to present the same scenario under different weather and daylight conditions. This includes changing the lighting and the appearance of surfaces, adding weather effect like rain, snow, fog, etc... The desire of modifying the environment in real-time during one exercise made us discover that a lot of underground work must be done to enable the platform to achieve that. The problems affect all the graphics pipeline, from the artist tools to the final OpenGL rendering. The first Material System written by MotherWay has some limitations on this side. We are now investigating with them the best solution to upgrade the system to: - Reuse some of the code written for the first release – Expose to the artist all the parameter needed to achieve different effects in different weather conditions – Trying not to stick too much with a single DCC tool (Studio Max used so far) It is anyway impossible to decouple completely the artist’s work from the simuscape creation, if we want to keep a satisfying graphics quality. Hence the Plant Model Builder will not focus on the graphics creation/modifications, but rather on creating the scenario file. Alternatively, the PMB can be used to create new scenes that will be considerably simpler in terms of graphics quality (which might be acceptable in several situations anyway). - At the moment we can load different scenarios for different exercises, with option of adding rain/snow effects. - Control Room Application for RA tool The control room application for the RA case study has been designed based on the requirements extracted from the HF and end-user partners of the consortium; it is an application created by ICCS. This is an application simulating the actual control room found in most of industrial sites. As it has been extracted by the relevant industrial contacts, this did not need to have the actual Control Room layout, but rather a symbolical representation of the different monitors and general capabilities that a control room can provide. Thus a simple interface has been built incorporating the requested features. These features include manipulation of plant components, observation of plant behaviour, viewing of Field Operators (avatars), camera views of plant, interactive usage of plant components/behaviour/operation, set/reset of alarms, emergency tasks executions such as ESD and EBD actions, interactive view of the plant and operators involved, etc. Several other features of the control room application were later improved following the comments of the usability tests performed inside the consortium. - Field Operator Application for RA tool This application has also been developed by ICCS having several features designed and implemented following the HF needs. A short summary of the main features is: portable gas detector implementation, portable gas detector picking/resetting/testing, portable gas detector reading indicator, gas smell indicator, text rendering for briefing/debriefing operators, ground plan view of the plant indicating where each operator is located, advanced user interaction, etc. Some other features of the field operator application were later improved following the comments of the usability tests performed inside the consortium. - Supervisor Station Application Again this application has been designed and implemented by ICCS having several supervisor features included according to the needs specified. These can be odelere as follows: monitor Field Operators, observe tasks execution, control accident parameters – start leaks – fires – etc, monitor communication between applications, load scenarios, load maps, start/stop simulation, Free/F.Op.View – navigation in plant, support messaging from other applications, etc. Although this application was mainly developed in the context of the RA tool, its relevance is quite general and it will be possible to apply it almost directly to other use cases. Through the usability tests performed towards the end of the reporting period, minor improvements of the application were suggested and implemented (as part of WP6 work). - Plant Model Builder Application This task involved the creation of a plant model builder application including the analysis of existing such components, evaluation of available 3D engines, revision of the VIRTHUALIS requirements and design guidelines as these were identified by the industrial partners. This has also included the implementation of the PMB application including interface improvements, actors’ management, triggers and alarms adding capability and also the integration of manipulators for easier object positioning. In this task mainly IFF has been involved. The produced version of the PMB was be presented in the mid-December demo held in Milano. In general the actions performed under the framework of the plant model builder application creation has included the Evaluation of existing Plant Model Tools, Analysis and evaluation of available 3d-engines with respect to their usability for the Plant Model Builder (PMB), Revision of the requirements definition and design guidelines for the PMB, and Clearance and adaptation of PMB specifications with partners. Concerning the components developments, they can be modelled as: Revision of the actor management, implementation of adding triggers and actions, interface improvements, concept and first implementation, integration of manipulators for easier, object positioning, preparations for demonstration activities, development of concepts for a cluster solution, preparative tests for the use in CAVE, ElbeDom. Also implementation of User Interface for the scenario Editor containing General Parameters, parameters for defining the rule based behaviour of the scene and parameters for defining a process simulation, export of xml-scenario file from the scenario editor. - Testing and debugging of applications Most of the VR partners in the consortium have tried testing the applications in their installations as a debugging session to prove any incompatibilities etc that should be corrected. TNO has focused on trying to stress the applications and during this it seemed that the networking communication was presenting some limitations. TNO is in charge of testing and stressing this part, and there is some positive feedback still to verify. In-depth code cleanup and optimization is an activity that will be carried out during WP II.1, however the release scheduled for M32 will already include debugging and some optimization. - VIRTHUALIS Demonstrations In the reporting period, several demonstrations have taken place, the main one being the demo during the Review meeting in Milan, at UniMi’s premises. This demonstration has shown to both the consortium and the reviews the results achieved in the first version of the HF Lab; it was a “technology demo”, i.e a demonstration of the available features, not yet a real application (which is what is expected at M32 of course). Other important demos happened after the review meeting during the restructuring period, in order to involve new partners; the most relevant one are the one give to Invensys (at VRMMP premises, in July) and at Sonatrach (at Unimi’s premises, in October). These two last demos have allowed the project to capture interest of these two partners who have then decided to join the project. Concerning the demonstration activities, it is important to note that IFF has also worked on the development of concepts for clustering solutions and also preparative tests for a CAVE implementation. Such first implementation design was carried out involving also contributions from VRMMP and TNO. Towards the end of the WP activities two further demonstrations were organised in December 2008 and January 2008 (but still under the framework of WP6). The purpose of those demonstrations was to bring all applications together and present the applications as a whole RAS tool to the HF partners inside the consortium. Out of this meeting, several directions, comments and suggestions were collected from the HF expertises inside the consortium but also other plant experienced people like Peter Kafka. The comments made were later included into usability tests and resulted into actual developments improving the RA tool as a whole (but this work covered inside WPII.1 and WPII.2. - Deliverables D6.3 and D6.4 Towards the end of this reporting period, two deliverables have to be prepared both due for M32 (end of December 2007). The two deliverables’ responsibles (ICCS & VRMMP) have started documenting and structuring the work to be included in both these deliverables from quite early stages to ensure deliverables being submitted on time. The deliverables were respectively on the VR platform and the 1st RA application applied to the benchmark plant. Both deliverables are accompanied by the related CD-ROM including all applications executable files and instructions on how to execute them. The deliverables content starts from the actual RA specifications and ranges up to the final applications and prototypes implementation methodologies, issues encountered and solutions found to keep up with not only the HF and end-user requirements but also with the huge commercial competition. For more detailed information on the above tools and modules developments please refer to deliverables D6.3 and D6.4 (applications and platform respectively). |  |  |  |  |  |  |  |
| ### WP1 Task6 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| During this reporting period the only deviations that was needed was regarding the Accident Investigation applications development. As it has been decided in executive and core group meetings, only the AI application’s specifications were to be extracted and defined in this reporting period. This is why the D6.3 will be delivering the first version of only the RA application. This has been decided firstly because of various different and not initially foreseen requirements defined for the RA application but also (and secondly) due to the general project restructuring that has decided to move the AI applications development to later stages of the project. Several features and tasks requiring great effort in WP6 developments were identified during consecutive meetings and demonstrations to the industrial partners of the consortium. To tackle with those needs and the stress of time, these features were modelled in order for the most important (based on end-user feedback) to be developed first and the teams focus firstly on these while at the same time taking into account resource and time planning. Following the rejection of NIP2 at the June 2007 ARM, the NIP was rewritten. The new NIP2 further developed the concept of the HFLab as an experimental environment, to include IT Tools that support and implement techniques used by HF experts and Safety Analysts, i.e. Task Modelling, Dynamic Event Trees, Fuzzy Probability Estimation, Fault Trees and Event Sequences. These IT Tools were integrated with the HFLab and its Tools via a Database, Log post-Processing Tool and Database Query Tool. These innovations unite human factors methods with virtual worlds, to provide a unique experimental facility, supporting observation, measurement, hypothesis testing and training. |  |  |  |  |  |  |  |
| ### WP1 Task 6 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D6.3 | 1st version of VIRTHUALIS Applications – Specification and design document | 1 | 32 | 34 | 2 | 2 | 26_ICCS |
| D6.4 | VIRTHUALIS SafeVR platform – Specification and design document | 1 | 32 | 34 | 2 | 2 | 25_VR-MMP |

| ### WP1 Task6 – List of Milestones |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| M6.7 | 1st version of 1st application – RA |  | 1 | 31 | 32 | 26_ICCS |
| M6.9 | Final version of the SafeVR platform |  | 1 | 32 | 32 | 25_VR-MMP |
| M6.8 | Functional specifications of 2nd Application – AI |  | 1 | 32 | 0 | 21_IFF |

## WP2 Task1 System Design and Detailed Specifications-

### WP2 Task1 – Task objectives and starting point of work at beginning of reporting period

This WP consists of the detailed design and development of all software tools including SafeVR completion and its integration into the HFLab and the development of all necessary functionalities for the sub product installation at the end users sites. The Work package has been organized into tasks, each task dedicated to the development of a specific software tool.

### WP2 Task1 – Progress towards objectives

See description of Tasks and subtasks below.

### WP2 Task1 – Deviation from the project program and corrective actions taken/suggested

See description of Tasks and subtasks below.

### WP2 Task1 – List of Deliverables

See subtasks below.

| ## WP2 Task1.1 – System Design and Detailed Specifications |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task1.1 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| The objectives of this task are: - Methodologies consolidation and integration into safety engineering models - Definition of the functional specs of the IT Tools - Definition of the whole architecture of the IT Tools - Definition of the collaborative development environment - Detailed design specifications of the various IS2 components |  |  |  |  |  |  |  |
| ### WP2 Task1.1 – Progress towards objectives |  |  |  |  |  |  |  |
| The results achieved are: - The functional specs for TM, FPE, DB and DBQ are defined – The whole architecture for the specified tools is well defined – The collaborative development environment is up and running (SVN/Wiki/NetBeans). |  |  |  |  |  |  |  |
| ### WP2 Task1.1 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The major deviations from the project program are: - The functional specs of TM, FPE, DB and DBQ was in late by a month. – The functional specs of ESB, FTB and DET are not yet delivered. The corrective actions taken are: - DET/DEG (now called ALBA) specs are to be delivered soon; - Development of ESB and FTB has been postponed. |  |  |  |  |  |  |  |
| ### WP2 Task1.1 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
|  | See below |  |  |  |  |  |  |

## WP2 Task1.1.1 Methodologies consolodation and integration into safety engineering models

### WP2 Task1.1.1 – Task objectives and starting point of work at beginning of reporting period

The objective of Task 1.1.1 is to integrate the Human Factors methods with safety engineering models (e.g., fault trees and dynamic event trees) and tailor them to the needs of the end-users (as specified in the workshop of 17-18 October 2007). The Integrated framework of HFs methods will be documented and provide a basis for the specification of requirements and data exchange in the IT tools. The same framework of HFs methods will be evaluated as a whole using the selected case studies in subsequent tasks.

### WP2 Task1.1.1 – Progress towards objectives

TUC has been the task leader of task 1.1.1 supported by a team of human factors and risk analysis specialists. The kick-off meeting of task 1.1.1 was in Milan on 14th December 2007, however, the actual work started early in January 2008. An action plan with responsibilities was distributed to the partners so that a draft of most reports would be ready by mid February. A progress meeting was run in Athens for 3 working days to review task progress (27-29 February 2008). During this meeting, the partners of task 1.1.1 decided to incorporate a new methodology in the framework concerning the evaluation of safety barriers. Also a decision was made to provide two versions of the framework for the average and advanced user respectively. Safety practitioners, training officers, and plant managers belong to the category of average user because of limitations in the time and resources available to invest in a safety case. On the other hand, safety analysts and risk consultants belong to the category of advanced user because they can afford a more resourceful approach to safety. The framework for the average user would be the priority for task 1.1.1 and would include: the task modeler, the safety barrier diagrams, the fuzzy probability estimator, and the fault tree analysis. For the advanced user, the framework would be expanded to include the dynamic event graph and the accident investigation tool. At present, the deliverable of task 1.1.1. comprises an executive report that explains the inter-links between the HFs methods and four appendices that provide detailed descriptions of the following methods: - Appendix 1: The Task Modeller - Appendix 2: The Fault Tree Analysis - Appendix 3: The Safety Barrier Diagrams - Appendix 4: The Fuzzy Probability Estimator Appendix 5 describes the accident investigation method (the same method used in WP5 of Phase I) and Appendix 6 describes the Dynamic Event Graph (in preparation). Finally, a functional flow sheet was prepared in the form of a short database to check the consistency of the data transfer between different methods. This short database should be further developed by the IT experts in subsequent tasks.

### WP2 Task1.1.1 – Deviation from the project program and corrective actions taken/suggested

The original task force included the following nine partners for 18 MMs, as follows: TCD (task odeler, 2MMs), TUC( task modeler and coordination, 2MMs),DEMOS (fuzzy estimator, 2MMs), POLITO (fault tree, dynamic event graph, 2 MMs), POLIMI (fault tree, dynamic event graph, 2MMs), LAAP5 (accident analysis, 2MMs), DTU/RISO (Safety management, 2MMS), DAPP (functional work sheet and case studies, 2MMs), RELCONSULT (2 MMs). The reasons for the delay were: - The incorporation of a new method (i.e., the safety barrier diagrams) for the average user - The development of the Dynamic Event Graph that relied on the modeling of a large number of system states and the response of the operators. The issue of data availability from operators and the plant simulator was a critical concern. - The starting date of task 111 was delayed until January 2008 - The introduction of new partners mainly in the group of tools that had to do with quantification. POLITO was a new partner whilst POLIMI introduced a new team to work in task 111. - The application of the framework to several case studies beyond the case studies of the project in order to ensure its general applicability. Because of these delays, an effort was made to communicate the specification of the HFs methods to the IT experts so that the adverse impact would become smaller. This risk was anticipated in the start of task 111 and all task leaders of the IT tools have been included in task 1.1.1 as partners. Hence, information on methods of task 111 was passed by the task leaders to the IT experts for the development of the IT tools. Corrective actions include: Expand task 111 until month 39 in order to achieve the following objectives: - Finalise the deliverable for the average user (end of May 1008) - Finalise the deliverable for the advanced user with the inclusion of the dynamic event graph (end of July 2008) The expansion of task 111 will result in an increase of man-power from 16 MMs (end of April 2009) up to 24 MMs (end of July 2008). Since the initial budget for task 1.1.1 were 18 MMs, the corrective action will require internal transfer of 6 MMs from existing resources of other tasks. Over the course of the task, LAAP5 withdrew and their work was allocated to INERIS (1MM) and UNIMI (1 MM). The deadline for delivering the work of task was month 34 but the individual HFs methods were delayed until month 36 and the overall deliverable until month 37 (end of May 2008). Overall 16 MMs were claimed by the partners until end of April 2008.

### WP2 Task1.1.1 – List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1.1 | An Integrated Framework to Human Factors Methods | 1 | 34 | 37 | 18 | 16 | 15_TUC |

## WP2 Task1.1.2 - System and tools functional and quality specs def

### WP2 Task1.1.2 - Task objectives and starting point of work at beginning of reporting period

- Definition of the functional specifications - Definition of the quality specifications

### WP2 Task1.1.2 - Progress towards objectives

Architectural specs are nearly ready. Functional specs are ready for TM, FPE, DB, DBQ and the specs for DET/DEG (ALBA) are coming in the period.

### WP2 Task1.1.2 - Deviation from the project program and corrective actions taken/suggested

Specs for ESB and FTB are missing and we suggest to remove them from the master plan.

### WP2 Task1.1.2 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1.2 | Wiki 1.1.2 Subtask page | 1 | 31 | 40 | 6 | 2 | 20_EXIMIA |

## WP2 Task1.2 – IT System development

### WP2 Task1.2 – Task objectives and starting point of work at beginning of reporting period

- Start with the development of the specified tools in an integrated solution.

### WP2 Task1.2 – Progress towards objectives

- Creation of the development team. – Training of the development team and definition of a common working methodology, based on periodical workshops – Setup of the working environment, based on NetBeans RCP and on a complete Enterprise Java Application environment. – Start of development of the modules

### WP2 Task1.2 – Deviation from the project program and corrective actions taken/suggested

- Due to delayed specs progress, to speed up the setup process, it was created a complete Linux OS Dev environment inside a VMWare virtual machine.

See subtasks below.

## WP2 Task1.2.1 - IT Modules development

### WP2 Task1.2.1 - Task objectives and starting point of work at beginning of reporting period

- Development of the modules

### WP2 Task1.2.1 - Progress towards objectives

- Currently in progress

### WP2 Task1.2.1 - List of Deliverables See below

## WP2 Task1.2.1.1 DB & DBQ Database Query and Analysis Tools-

### WP2 Task1.2.1.1 – Task objectives and starting point of work at beginning of reporting period

Sub-task 1.2.1: DB & DBQ Database Query and Analysis Tools, aims to design and implement a Database capable of storing the configuration and results of experiments carried out in the HFLab, and to query the data to extract information of interest to human factors and safety experts. At the start of the reporting period, the HFLab concept had not been developed and there was no database design nor database. During WP6, LBORO and KITE made progress towards a database design to test and demonstrate the concepts. This work delivered a LogPost-Processing Tool (to parse HFLab session log files), a Results database (to store HFLab experiment results) and a Database Query tool to explore the results. During sub-task 1.2.1, the PMO decided to include the development of the Log Post-Processing Tool (LogPP) with that of the Database, since the two are closely related. LBORO and KITE are currently working closely together on this.

### WP2 Task1.2.1.1 – Progress towards objectives

The database has been designed to support the storage of the configuration and extraction of the results of HFLab experiments, and to be able to query those results. The Database and Log Post-Processing Tool are documented in the Software Requirements Specification (SRS) called “VIRTHUALIS DB&LogPP SRS”, currently at v1.4. The Database Query Tool is documented in the Software Requirements Specification (SRS) called “VIRTHUALIS Database Query Tool (DBQ) Software Requirements Specification”. Release 1 (R1) of the Database has nearly been completed, and follows the Java Enterprise Edition architecture devised by Eximia. Each database entity (at least, those required in R1) has been built, along with its façade. A session façade for the Task Modeller and Database Query IT Tools is very near completion. Release 1 of the LogPP Tool is close to completion. Release 1 of the Database Query Tool, being built by UNIMI, is very close to completion and will run predefined queries. Synthetic data has been generated to test the IT Tools, based on the Risk Assessment application on the Polimi Gas Processing Plant. This will be updated for the StatoilHydro case study demonstration when the plant data becomes available. A list of ideas and changes required for R2 of the DB, DBQ and LogPP Tool has been compiled, and some analysis and design reworking has started.

### WP2 Task1.2.1.1 – Deviation from the project program and corrective actions taken/suggested

During the sub-task, development of the LogPPTool (by KITE) was merged with the DB. In the absence of detailed user requirements for the IT Tools, a document was produced (by LBORO with contributions from KITE, TCD, DEMOS, IFF, OVGU & EXIMIA) called “Notes for the VIRTHUALIS IT Tool Specifications”, currently at v1.7. This stated, in plain language wherever possible, a vision of how all the IT and HFLab Tools could work together with each other and with the Database. The document has been circulated amongst the IT Tool experts for review, corrections and comments.

| ### WP2 Task1.2.1.1 – List of Milestones |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| M1.2.1.1.a | DB and DBQ Release 1 | Deliver Release 1 (R1) of the DB & DBQ. | 1 | 35 | 38 | 24_LBORO.CO |
| M1.2.1.1.a | Spec for DB and DBQ | Provide a Software Requirements Specification (SRS) of the DB & DBQ, capable of supporting the IT Tools and HFLab Tools (2 documents) and incorporate the LogPP Tool. | 1 | 35 | 35 | 24_LBORO.CO |

| ## WP2 Task1.2.1.2 FTB+ESB- |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task1.2.1.2 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| FTB + ESB objectives consist into the detailed design and implementation of the Fault Tree Builder and Event Sequence Builder. At the beginning of the reporting period none of the methodologies were designed or implemented. |  |  |  |  |  |  |  |
| ### WP2 Task1.2.1.2 – Progress towards objectives |  |  |  |  |  |  |  |
| The FTB has been based on the logical approach of the Integrated Recursive operability analysis (IROA). This is an enhanced form of the classical ROA which drives the analyst to include explicitly human and odelerenal factors in the identification of accidental events. The new approach has absorbed from the classical ROA the logical construction that represents the links within Top Events and Initiator Events, bringing to the possibility of an automatic development of a Fault Tree. The methodology specification has been given. The detailed design is under development (90% ready). The implementation phase consists in a draft java application to be modelled. The same approach apply for the event sequence builder, that from the “tables” of the IROA is able to directly extract all the possible consequences deriving from an initiating event, in the form of a sequence of events, referring to the correct or incorrect performances of the protection systems and plant operators. The methodology is completely defined. But not still designed as an IT Tool. The final IT tool will integrate the different methodologies in order to develop an instrument able to obtain logic trees congruent with the analysis for the identification of accidental event, thus assuring the quality of the analysis. The FTB + ESB will allow reducing and quantifying the trees starting from literature failure rates, stored in the DB, up-dated with the estimation coming from the Fuzzy tool. It will return to the DB the Top event identified, their initiator events, the sequences to the TE and the probabilities associated. The decision has been taken of using an commercial software for FT solving. Its characteristics discussed. But the software has not been chosen. |  |  |  |  |  |  |  |
| ### WP2 Task1.2.1.2 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| At the moment no deviations from the project program are foreseen, but a short delay in the delivering of the documents and IT tools. |  |  |  |  |  |  |  |
| ### WP2 Task1.2.1.2 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D.3.2.1 | Detailed specifications of FTB+ESB tools | 1 | 37 | 43 | 22 | 0 | 55_POLITO |
| D.3.2.2 | Stand alone version of FTB+ESB tool | 1 | 43 | 43 | 0 | 0 | 55_POLITO |

## WP2 Task 1.2.1.3 Task Modeller

### WP2 Task 1.2.1.3 – Task objectives and starting point of work at beginning of reporting period

The Task Modeller has been modelled by the End Users as a critical component of the Final (IS)² product, as it allows covering all the aspects of task descriptions for all the applications. The task model is built as a result of a task analysis, which provides a formal and structured description of a work process to be performed by a worker or a team on a given plant, including all communications. The Task Modeller shall provide then a structured interview template for the Human Factor Practitioner so that he can reconstruct a model of an actual task execution considering also the deviation from the nominal task flow and its consequences. Furthermore the information collected should be simultaneously represented in a graphical format that should highlight the main sequence flow and the deviation flows as well (e.g., critical human errors). This module will provide the first mapping of the task (task model) that should constitute the basis of the information needed for the Task Tracker (Rule Based System) to work. The task modeler data should be organized in a software format able to be interfaced directly with the Competence Modeller and the Task Tracker.

### WP2 Task 1.2.1.3 – Progress towards objectives

In September 2007 the TM group started reviewing the state of the art in the field of task analysis and the commercially available software for performing task analysis. The review also considered software performing workflow modeler (like Microsaint). In parallel it started reviewing the state of the art in task representations notations. Following the state of the art review TCD selected a well established standard for workflow representation called the Business Process Modeling Notation (BPMN) and decided to deploy it for the task representation as a useful mean to bridge the gap between analytical representation and intuitiveness of the content. In December 2007 starting from this and from the previous field work performed in Virthualis we started to model a consistent description of the selected approach upon which a new software needed to be based (none of the task analysis software tool commercially available in fact performed the analysis in a manner consistent with the one selected to best suit the needs of the project). Following this analysis we documented a preliminary software requirement document for the tool in February 2008. In March 2008 we started the actual software development of the tool and the prototyping of the Graphical User Interfaces for the structured interview template. At the end of April the software development had already tackled part of the issue regarding the graphical formats and was moving towards the problems referring to the structured interview template and the simultaneously representation of it in a graphical format that should highlight the main sequence flow and the deviation flows as well (e.g., critical human errors). The interface of the task modeler with the competence modeler has not started yet since the development of the competence modeler is not starting till month 41. TCD is leading the subtask in charge of developing the competence odeler as well so that the integration of the two will be assured. The interface with the task tracker will be related to the possibility to deliver the information regarding the task model into a suitable XML scheme. The issue is currently under study. Up to now the task modeler approach has been tested for the representation of the Statoil preliminary case study. The results obtained have been transferred to the DET for performing some quantitative analysis. This has highlighted two strong points: - The revision of the graphical representation of the task has been considered helpful and intuitive during the field visit in Statoil in April. - The result of the task analysis derived from he task modeler can be used as an input by the DET.

### WP2 Task 1.2.1.3 – Deviation from the project program and corrective actions taken/suggested

### WP2 Task 1.2.1.3 – List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D3.3.2 | Stand alone version of TM | 1 | 42 | 42 | 33 | 11 | 09_TCD |
| D3.3.1 | Task Modeller Specifications | 1 | 34 | 34 | 0 | 0 | 09_TCD |

| ## WP2 Task 1.2.1.4 Competence Modeller |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 1.2.1.4 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| The starting point of this work is due to commence in M42. This is subject to the competence modeller receiving the go-ahead for development. - Mapping of deviations from the Task Modeller (multi-level HAZOP) into the competency framework (M42). - Eliciting Human factors issues and performance shaping factors (M42). - Developing training modes from competency framework and task modeler (M45). - Developing assessment modes from competency framework and task modeler (M45). |  |  |  |  |  |  |  |
| ### WP2 Task 1.2.1.4 - Progress towards objectives |  |  |  |  |  |  |  |
| Work on the competence modeler has not yet commenced. The decision to go ahead with the tool is due to be made in October 2008. |  |  |  |  |  |  |  |
| ### WP2 Task 1.2.1.4 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| Work on the competence modeler has not yet commenced. The decision to go ahead with the tool is due to be made in October 2008. |  |  |  |  |  |  |  |
| ### WP2 Task 1.2.1.4 - List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D.3.4.1 | Competence Modeller Specification | 1 | 44 | 44 | 6 | 0 | 09_TCD |
| D.3.4.2 | Stand alone version of the Competence Modeller | 1 | 48 | 48 | 6 | 0 | 09_TCD |

## WP2 Task 1.2.1.5 ALBA

### WP2 Task 1.2.1.5 - Task objectives and starting point of work at beginning of reporting period

Detailed design and implementation of the ALBA IT Tool. At the beginning of the reporting period none of the methodologies were designed or implemented.

### WP2 Task 1.2.1.5 - Progress towards objectives

The ALBA tool is based on the logic approach of the Integrated Dynamic Decision Analysis. It allows identifying the sequence of events bringing to an accident, taking into account the barriers posed to the accident development by automatic system and/or human intervention. It gives the results of the risk assessment as sequence of events that could be directly used in the virtual environment. The possibility to link the model to the process simulator allows to use the tool to follow the evolution of the relevant process variables, selected during the modelling stage of the dynamic trees. Therefore the tool will support the investigation of failure (technical or human) events. The ALBA has been completely designed, even if the reporting is still pending and the IT Tool is under development.

### WP2 Task1.2.1.5 - Deviation from the project program and corrective actions taken/suggested

No deviation from the project program is foreseen, but the name of the tool: formerly DET, will be called ALBA (Artificial Logic Bayesian Algorithm)

### WP2 Task1.2.1.5 - List of Deliverables

| No. | Title | WP |  | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months |  | Used indicative person-months |  | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D.3.5.1 | Specification of the ALBA | 1 |  | 42 | 42 | 0 |  | 0 |  | 55_POLITO |
| D.3.5.2 | Stand alone version of ALBA | 1 |  | 46 | 46 | 0 |  | 0 |  | 55_POLITO |

## WP2 Task 1.2.1.6 - FPE module

### WP2 Task1.2.1.6 - Task objectives and starting point of work at beginning of reporting period

Task 1.2.1.6 aims at the creation of the FPE module for the estimation of the probability of a human erroneous action in specific industrial and working contexts. This module is to be linked with the FTB the DET and the TM while its data will be stored at the DB.

### WP2 Task1.2.1.6 - Progress towards objectives

DEMOS has been the task leader of the FPE module working together with POLIMI and OVGU. To that end, a fuzzy logic system for the estimation of the probability of a human erroneous action in specific industrial and working contexts has been developed. The fuzzification process was based on the CREAM methodology. The fuzzy model developed includes nine input variables similar to the common performance conditions of this methodology and one output parameter (action failure probability of human operator). The results of the fuzzy model, which are in the form of crisp numbers, will be used directly in the fault trees and event trees calculations for the quantification of specific undesired events that include the interaction of human factors in their modeling. The source code has been jointly wrtitten in C++ by DEMOS and POLIMI staff, under the quality setting and review of OVGU. The run tests have been done in a 3 days meeting in Athens (8-10/3/2008) and the source code developed with the appropriate instructions about I/O have been forwarded to EXIMIA, which is responsible for IT integration. Together with the code a development/use manual has been produced (as internal Deliverable) under the title D3.6.1. Similar coolaboration has been held with all other IT modules developers, like the DB (KITE/LBORO), the FT, ET (POLITO) and the TM (TCD) to provide all necessary information for the smooth binding among FPE and the other modules.

### WP2 Task1.2.1.6 - Deviation from the project program and corrective actions taken/suggested

The work has unfolded on schedule. The binding of the module with the other IT tools is ongoing too.

| ### WP2 Task1.2.1.6 - List of Deliverables |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| M3.6.1 | FPE manual (1st version) | The FPE Report and manual provides both the theoretical background and the techical details for the construction and moreover the use of the FPE module, together with its links with other IT modules. | 1 | 39 | 36 | 07_DEMOS |

## WP2 Task 1.2.2 - (IS)2 Product & subproduct Integration

### WP2 Task 1.2.2 - Task objectives and starting point of work at beginning of reporting period

- Integration of the IT Tools modules inside an integrated product called (IS)2

### WP2 Task 1.2.2 - Progress towards objectives

The integration process started directly from the beginning of the development process due to: - The definition of a common server platform: Java Enterprise compatible application server - The definition of a common client platform: NetBeans Rich Client Platform - The definition of an higly integrated project and development process

### WP2 Task 1.2.2 - Deviation from the project program and corrective actions taken/suggested

No deviation to be mentioned

### WP2 Task 1.2.2 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.2.2.1 | Integrated Dev Environment | 1 | 55 | 55 | 15 | 7 | 20_EXIMIA |

## WP2 Task 1.3 HF-LAB

### WP2 Task1.3 - Task objectives and starting point of work at beginning of reporting period

Develop and deliver new versions of the HFLab. Adapt the HF Lab to specific end-user applications for (IS)2 product. This task started on M33, continuing the work done in WP I.6.

### WP2 Task1.3 - Progress towards objectives

The activity is carried out in the 4 subtasks. In the reporting period the main activity has focused on subtasks 1.3.1 and 1.3.2, plus some initial preparation work done also for 1.3.3. Subtask 1.3.4 has not started yet. See subtask description for details.

## WP2 Task1.3.1 HF LAB releases

### WP2 Task1.3.1 - Task objectives and starting point of work at beginning of reporting period

This task is dedicated to the completion of SafeVR platform and to the integration into the HF Lab of the various tools required to operate it. Task 1.3 has started its core activity in M33, right after the end of WP I.6. Compared to the previous WP, this task has a smaller number of partners, mainly focused on developing the VR platform and the related tools.

### WP2 Task1.3.1 - Progress towards objectives

Moving form the results of WP I.6 and from the internal demonstrations that, at the end of that package, have provided precious input for the next steps of the HF Lab, Task 1.3 has started working on a series of topics. The main ones and the related achievements are briefly listed below. - Performed several sessions of usability tests on the Risk Assessment tool produced in WP I.6, especially for Field-Operator UI. Several changes defined in these sessions have then been applied to the software. In particular: - Improved the User Interface for interaction with plant elements and for controlling their properties. - Changed the device controls to switch between the different application modes (navigation, operation, …). - Motion Model: added the “look around while walking in one direction” mode. o Motion model: added controls to change at runtime the motion smooth step function; this allows to fine-tune the progressive start and end of the motion. o Improved handling of the Wiimote IR pointer. This should ease the use of the Wiimote device and of its pointing features. - Started the preparation of scenario data for the StatoilHydro use case (mainly the 3D models and the sound design of the ALDS unit of Karsto plant). A visit to the plant has happened in April 2008 to collect needed data for building the simulation scenario. - Produced and circulated lots of documents about feature proposal and discussion; also collected some initial feedback on them from RTD Manager and WP1 deputy leader. - Prepared and attended Abu Dhabi demo at Invensys’ Showcase event. For this specific event some extra features have been prepared: - Added support for eMagin Head-Mounted Display, with tracker and stereo vision (via the nVidia stereo driver). - Added support for “dynamic graphs”, i.e. 3D objects (added to the 3D environment) that are updated in real-time to create a graph plotting the evolution over time of a given parameter, to show trend values for specific component variables over the time. The updated values are received from Dynsim of course. - Started the integration of the AXIM module for accident simulations; the first targeted feature is to compute the gas cloud generated by a leakage. AXIM will replace the previous module called “GDM” (GDM was preciously used but only for the pool-fire case). - Developed and applied constant updates for the SafeVRViewer, to run platform features and run tests on stereo vision (HMD and virtual theatre at Unimi premises), interaction modes, interaction devices (like trackers, wiimote), motion models. - Initiated technical discussion with Task 1.2 group to define the integration between IT tools and HF Lab. The decision is to use a common Data Abstraction Layer and only share the data, so to avoid any direct link between HF lab and IT tools. Also interacted tightly with subtask 1.2.2 to define database structure and also to detail the Log Post-Process tool and its link to the database. - Migration of the development environment to use VisualStudio 2005 and Delta3D 2.0. This migration was needed on a technical level and it has brought some clear advantages in the daily work of the dev team. - Supported the Demo Group in preparation for ARM demo.

### WP2 Task 1.3.1 - Deviation from the project program and corrective actions taken/suggested

Due to a change in planning the deployment of ther StatoilHydro use case has ben postponed by 4 months. Therefore the first release of the HFLab (tagged as Rel1 in the workplan) is delayed as well. This does not change the work management anyway, as it simply allows for more features and detailed implementation to happen in time for the first use case. The planned iterative development cycle is still maintained as planned.

## WP2 Task 1.3.2 RASVR+TRVR STATOIL development

### WP2 Task1.3.2 - Task objectives and starting point of work at beginning of reporting period

To prepare all the tools used in the HF Lab for the STATOIL application. This includes: - Integrating the process simulator used by STATOIL with the HF Lab. - Providing an interactive 3D model reproducing the specific plant. The task will require having the CAD model of the plant to simulate and all the relevant P&IDs and equipment item list available to the VR team. Photographs of the plant are also required to show exactly how the plant looks from different views. Graphical objects for all the equipment items will be created and connected together to create the plant model. All necessary technical and human factor details will be included in the model. For example, the Positioning of the items and the way displays are shown. Field trips to the plant will be required. Comments will be sort from the Plant Manager or Operators to ensure that they agree with all the important aspects of the 3D plant model. For the process simulator integration, STATOIL will provide access to the process simulator to the development team. This team will study the simulator API and determine the most appropriate communication technology to be used for integration. Finally, the VR team programs the process simulator interface using the chosen technology.

### WP2 Task 1.3.2 - Progress towards objectives

The main achievements for the reporting period have been summarised below: • Various sessions of usability tests on the RA as this was produced by WP I.6, especially for the Field-Operator UI were executed. Several changes defined in these sessions have then been developed in Software. In more detail: o Improved overall User Interface readability. o Modified User Interface to improve interaction with plant elements and their properties. o Changed the way a user may switch between the different application modes (navigation, operation etc). o Provided a more intuitive control of the Portable Gas Detector probe utilizing the Wiimote’s ability to report its position and orientation. o Modified the Portable Gas Detector to act in a more realistic way by continuously reporting measurements coupled by audio feedback. • During the reporting period, the StatoilHydro use case was prepared. At first, a detailed scenario has been drawn that reflects the needs reported by the industry. Various visits to the plant were performed to support this task and help clarify the applications’ requirements. Having this scenario as a point of reference, a new set of required features has been identified resulting in the production and finalization of the RASVR specifications. • In order to adapt the existing applications to the StatoilHydro use case, the actual working environment needs to be represented in the virtual world. Towards this goal, Statoil has provided CAD data regarding the targeted part of the plant that are being refined in order to be used by the platform. Further to this, visits to the plant have been organized and a substantial amount of images and sounds has been collected that will be used along with the CAD data to produce a realistic model of the real plant. • Further from this during the reporting period, the case study preparation of scenario data for the StatoilHydro use case (mainly the 3D models and the sound design of the ALDS unit of Karsto plant) was executed. Various visits to the plant were performed in April 2008 to collect needed data for building the simulation scenario and also to define the particular StatoilHydro requirements for the application and thus aid the specifications extraction. This task has resulted to the production and finalisation of the RASVR specifications.

### WP2 Task 1.3.2 - Deviation from the project program and corrective actions taken/suggested

Due to the early stage of the HF specifications and thus technical requirements from the HF side, at the beginning stage of the task, the application developments were frozen until the RASVR requirements reached a final state having the tasks focused on the aforementioned task. After the specifications were properly defined by the VR, HF and industrial partners the developments started again.

## WP2 Task 1.3.3 RASVR+OSM SONATRACH development

### WP2 Task 1.3.3 - Task objectives and starting point of work at beginning of reporting period

The main goal of this subtask is to prepare all the tools used in the HF Lab for the SONATRACH application. Task 1.3.3 started on M33.

### WP2 Task 1.3.3 - Progress towards objectives

In the reported period only some initial preparatory work has been carried out. This has included mainly an initial analysis of the data need to run the simulation and the work required to prepare it. Also, a first visit to the Sonatrach plant has happened in march 2008, including also people from the HF Lab team in charge of producing the 3D models of the scenario to simulate. The main corpus of the data preparation work will happen from M37 on when the CAD file will also be available.

### WP2 Task 1.3.3 - Deviation from the project program and corrective actions taken/suggested

There is a slight delayin receiving the CAD data files, which will probably delay the data prepation by 2-3 months. Anyway, at the moment this does not require any specific corrective action as this delay does not seem to impact the rest of the workplan.

## WP2 Task 1.3.4 AIS TOTAL Development

### WP2 Task1.3.4 – Task objectives and starting point of work at beginning of reporting period

According to the NIP-M25-M42 WP1.3.4 will not start before M37.

| ## WP2 Task 1.4 Product Quality Assurance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 1.4 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| The goal of this task is to assure the compliance of the product (tools and applications for risk assessment, accident investigation, operational safety management and training) with the needs and requirements of end users. Since quality assurance rgani is a continuous and dynamic process, it should accompany the development of tools and applications as well as testing and validating them in accordance with the product development roadmap. |  |  |  |  |  |  |  |
| ### WP2 Task 1.4 – Progress towards objectives |  |  |  |  |  |  |  |
| Since then VIRTHUALIS project evolved from an Human Factor centric research project, driven by industrial needs into an information system related development project, the scope of Product Quality Assurance had to be extended. Quality Assurance Group (QAG) which is responsible for ensuring and tracking quality expanded the approach with a information system related Software Quality Assurance Process (SQAP). Owing the fact that the term “quality” has an ambivalent definition, quality assurance in VIRTHUALIS at this project stage has been separated into internal “Process Quality Assurance”, including classical review of deliverables, internal documents, responsibilities as well as communication structures and “Product Quality Assurance”. The concern of this Task is therefore to keep track of external (e.g. user) and internal (e.g. rganization between tools) requirements as well as steering and supervising software tests and defining quality rules and procedures with a software development scope. To assure awareness for software development quality and therewith overall product quality is a time consuming concern within a huge rganization like VIRTHUALIS. QAG by continusly sticking to quality aspects has achieved a high awareness during the reporting period. For the upcoming period the entire rganization is supposed to live the quality rules that have been set. QAG will track and trace this learning and trainig process and will frequently report about Quality to the PM |  |  |  |  |  |  |  |
| ### WP2 Task 1.4 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| Due to major changes in project rganizati as well as involved partners after the last annual review meeting the rganization had to learn their rules and constitution entirely new. The proposed software could not be developed like it was planned in the previous Next Implementation Plan (NIP). Gathering end-user requirements worked out to be more difficult than rganiza. Moreover the project was understaffed in terms of software development skills. The project rganization had to learn how to write suitable Software Requirements Specficiations (SRS) according the templates that had been roled out during the definiton of the Software Quality Assurance Process (SQAP). The whole roadmap was under heavy discussion and had to be reassembled entirely new after and with the field work expecially for the first on-site field test. |  |  |  |  |  |  |  |
| ### WP2 Task 1.4 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D4.1 | Product implementation and test plan | 1 | 35 | 35 | 0 | 0 | 53_OVGU |
| D4.3 | Report on system quality attributes | 1 | 40 | 40 | 0 | 0 | 12_UNIMI |
| D4.2.1 | Report on test and validation results v1 | 1 | 48 | 48 | 0 | 0 | 07_DEMOS |
| D4.2.2 | Report on test and validation results v2 | 1 | 56 | 56 | 0 | 0 | 07_DEMOS |

## WP2 Task 2 Field Test and Validation

### WP2 Task 2 - Task objectives and starting point of work at beginning of reporting period

To experiment and validate the (IS)2 product, its sub products and modules with respect to the identified user need and requirements, and to identify possible improvements to consolidate the product for commercial exploitation after the end of the project. Three sites have been selected for the three involved companies: STATOIL, SONATRACH and TOTAL. Statoil field test will allow us to test and validate the sub product RAS VR for Risk assessment. It will also allow us to test TRVR for training. SONATRACH field test will allow us to validate RAS VR and OSM for operational safety management sub products. OSM application will be considered for a case study about the extension of an existing plant, still in design stage. TOTAL field test will allow us to validate AIS sub product for accident investigation.

### WP2 Task 2 - Progress towards objectives

The test case specifications with Statoil and Sonatrach are progressing well. The start of the case study with TOTAL will be delayed for a few months.

### WP2 Task 2 - Deviation from the project program and corrective actions taken/suggested

There are slight delays with each of the case studies for good reasons (see more detailsed descriptions under the sub-tasks). There is, however, sufficient time in the rest of the project to complete all the tasks.

See in subtasks 2.1-2.3.

## WP2 Task 2.1 RASVR+TRVR STATOIL

### WP2 Task 2.1 - Task objectives and starting point of work at beginning of reporting period

The overall objective of this task is to validate the risk assessment and training products for STATOIL by porting and testing them to STATOIL to carry out real-life field tests.

### WP2 Task 2.1 - Progress towards objectives

Task 2.1 has four sub-tasks. Sub-task 2.1.1 (Case study review) is completed. Sub-task 2.1.2 (IT Tools installation and experiments definition) is on going. Sub-tasks 2.1.3 (Testing and validation) and 2.1.4 (Results analysis) are due to start later.

### WP2 Task 2.1 - Deviation from the project program and corrective actions taken/suggested

See the description of each of the sub-tasks.

| ## WP2 Task 2.1.1 Case Study Review |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 2.1.1 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| To review the specified case study and check how it meets the requirements of StatoilHydro before application development begins. |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.1 – Progress towards objectives |  |  |  |  |  |  |  |
| Task completed. The first case study specification meeting was held in Paris on 3rd January 2008. The meeting was hosted by INERIS and was attended by all partners involved in this work package. An interim meeting was held in Milan to review progess on 20th March 2008. The meeting was hosted by UNIMI and was attended by DAPP and LBORO. The second case study specification meeting was held in Posgrunn, Norway on 9th April 2008. The meeting was hosted by StatoilHydro and was attended by all partners involved in this work package. In between meetings DAPP worked closely with StatoilHydro and DTU to complete the deliverable. |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.1 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The completion of the task was delayed by two months. |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.1 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.1.1 | STATOIL Case study specification | 2 | 34 | 36 | 0 | 0 | 37_STATOIL |

## WP2 Task 2.1.2 IT Tools installation

### WP2 Task 2.1.2 - Task objectives and starting point of work at beginning of reporting period

In this subtask IT tools and HFLab will be delivered and installed the first time as stand-alone modules. Risk analysis data for the reviewed case study will be stored into the DB and the IT Tools and HFLab will be also run to set up case study data.

### WP2 Task 2.1.2 - Progress towards objectives

This sub-task has one deliverable (2.1.2 Report on experiment definitions) which describes how the HF Lab should be configured to simulate different situations for the experiments. The sub-task also has one milestone, which is proper installation of the systems. Part of the experiment defintitions was described in deliverable (2.1.1 Case study specification). This is now being extended with further input from StatoilHydro to include more scenarios and human factor considerations. Meetings have been planned in May to further progress this sub-task.

### WP2 Task 2.1.2 - Deviation from the project program and corrective actions taken/suggested

This sub-task was planned to be completed in M35. However, this will be delayed till M41, due to holiday period in July and August and to the delay in the delivery of some of the IT tools. Therefore, the the report on experiment definitions (D2.1.1) will be delivered in M39 and the installation (M2.1.1) is expected to take place in M41. The delay should not have a significant impact on the completion of the whole sub-task 2.1, which is planned to be completed in M46.

### WP2 Task 2.1.2 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months |  | Used indicative person-months |  |  | Lead Partner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D2.1.2 | Report on experiments definition | 2 | 35 | 39 | 0 |  | 0 |  |  | 37_STATOIL |  |
| ### WP2 Task 2.1.2 - List of Milestones |  |  |  |  |  |  |  |  |  |  |
| No. | Title | Milestone Description |  |  | WP | Due Date (Month) |  | Actual/Forecast delivery date | Lead Partner |  |
| M2.1.1 | Systems properly installed | Installation is planned to take place in September 2008 (M41) which will be a suitable time for StatoilHydro and the rest of the consortium. |  |  | 2 | 35 |  | 41 | 37_STATOIL |  |

| ## WP2 Task 2.1.3 Testing and Validation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task2.1.3 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| To validate that the developed Modules meet the stated requirements of the STATOIL case study. To identify necessary fine adjustments where necessary. To carry out real-life experiments and perform risk assessment on site using HFLab as an experimental Human factors lab. To validate human computer interaction issues on the application case study and identify possible limitation that reduce the capability of HFLab of being used for experimenting and observing human factor safety issues |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.3 - Progress towards objectives |  |  |  |  |  |  |  |
| This sub-task is due to start after the systems have been installed in September 2008. |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.3 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| Because this sub-task is delayed in starting it is expected that it will be completed in M44. This will still leave 2 months to complete the next sub-task (2.1.4 Results analysis) so that the whole of the task 2.1 (StatoilHydro case study) will be completed on schedule as originally planned. |  |  |  |  |  |  |  |
| ### WP2 Task 2.1.3 - List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.1.3 | Report on testing and validation | 2 | 39 | 44 | 0 | 0 | 37_STATOIL |

| ### WP2 Task 2.1.3 - List of Deliverables |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| D2.1.3 | Experiments completed with data collected | Carry out experiement when the systems have been properly configured. | 2 | 38 | 43 | 37_STATOIL |
| D2.1.2 | Systems properly configured for experiments | After the installation of the systems they will be configured so that the planned experiments can be carried out. | 2 | 38 | 42 | 37_STATOIL |

## WP2 Task 2.1.4 Results Analysis

### WP2 Task 2.1.4 - Task objectives and starting point of work at beginning of reporting period

To obtain a better understanding of the human factors involved in the case study and how they affect operator performance and safety of the plant.

### WP2 Task 2.1.4 - Progress towards objectives

To be started when experiments have been completed.

### WP2 Task 2.1.4 - Deviation from the project program and corrective actions taken/suggested

N/A

### WP2 Task 2.1.4 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D2.1.4 | Final report on case study | 2 | 46 | 46 | 0 | 0 | 37_STATOIL |

## WP2 Task 2.2 RASVR+OSM SONATRACH

### WP2 Task 2.2 – Task objectives and starting point of work at beginning of reporting period

The overall objective of this task is to validate the risk assessment and OSM applications for SONATRACH by porting and testing them to SONATRACH and carry out real-life field tests.

### WP2 Task 2.2 – Progress towards objectives

Task 2.2 has four sub-tasks. Sub-task 2.2.1 (Case study specification) has started. Sub-tasks 2.2.2 (IT Tools installation and experiments definition) 2.1.3 (Testing and validation) and 2.1.4 (Results analysis) are due to start later.

### WP2 Task 2.2 – Deviation from the project program and corrective actions taken/suggested

See the description of each of the sub-tasks.

### WP2 Task 2.2 – List of Deliverables

## WP2 Task 2.2.1 Case Study Specification

### WP2 Task 2.2.1 - Task objectives and starting point of work at beginning of reporting period

To develop a detailed case study specification for the applications. The specification should provide sufficient details for the VR team to carry out development work.

### WP2 Task 2.2.1 - Progress towards objectives

A meeting was held in Paris on 4th January 2008 to begin the process of case study specification for Sonatrach. The meeting was hosted by INERIS and was attended by all partners involved in this work package. However, The initial case studies suggested by Sonatrach were thought to be inappropriate as they were either too simple or not process focused. Therefore, considerable effort was put into identifying a suitable case study that will bring significant benefits to Sonatrach and the VIRTHUALIS project. A field trip, involving the project management team, to the Sonatrach plant took place in April to explore possible case study scenarios and a particular case study scenario was identified. A subsequent meeting was held in Paris on 24th April 08 to plan to develop the case study further. Hence the actual work on developing the specification for the case study was delayed. However, after a slow start, the work on this sub-task is progressing satisfactorily. Two analysis worksops and a field trip to Sonatrach are being planned. These activities will result in sufficient material for specifying the case study in details.

### WP2 Task 2.2.1 - Deviation from the project program and corrective actions taken/suggested

The case study specification (D.2.2.1) was intended to be completed by M35. However, the plan is to have a draft of D.2.2.1 completed in M39. The final version will be released in M41.

### WP2 Task 2.2.1 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D2.2.1 | Sonatrach Case Study Specification | 2 | 35 | 41 | 0 | 0 | 02_DAPP |

| ## WP2 Task2.2.2 IT Tools installation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 2.2.2 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| In this subtask IT tools and HFLab will be delivered and installed the first time as stand-alone modules. Risk analysis data for the reviewed case study will be stored into the DB and the IT Tools and HFLab will be also run to set up case study data. |  |  |  |  |  |  |  |
| ### WP2 Task 2.2.2 - Progress towards objectives |  |  |  |  |  |  |  |
| A field trip is organised in June to gather plant information (3D images, sounds, etc) to be included in the VIRTHUALIS applications. The progress of the development of the applications is partly dependent on the development of the OTS, which is a separate but related initiative by Sonatrach. This is because the availability of a dynamic simulator and a control room interface is critical to the case study. |  |  |  |  |  |  |  |
| ### WP2 Task 2.2.2 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| To fit in the time scale of the development of the OTS, the HF Lab installation is planned to take place in M50. The is the preferred Sonatrach's preferred plan as they would like the OTS and the HF Lab to be properly integrated. However, once the case study specification (2.2.1) is completed in M41, the report on experiment definition (2.2.2) can be delivered in M42, against the original planned date of M40. |  |  |  |  |  |  |  |
| ### WP2 Task2.2.2 - List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.2.2 | Report on experiment definition | 2 | 40 | 42 | 0 | 0 | 02_DAPP |

| ### WP2 Task2.2.2 - List of Deliverables |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| D2.2.1 | System properly installed | The HF Lab and related IT tools properly installed on a Sonatrach site. | 2 | 40 | 50 | 54_SONATRACH |

## WP2 Task 2.2.3 Testing and validation

### WP2 Task 2.2.3 - Task objectives and starting point of work at beginning of reporting period

This sub-task is due to start after the systems have been installed in M50.

### WP2 Task 2.2.3 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months |  | Used indicative person-months |  |  | Lead Partner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D2.2.3 | Report on testing and validation | 2 | 46 | 51 | 0 |  | 0 |  |  | 54_SONATRACH |  |
| ### WP2 Task 2.2.3 - List of Milestones |  |  |  |  |  |  |  |  |  |  |
| No. | Title | Milestone Description |  |  | WP | Due Date (Month) |  | Actual/Forecast delivery date | Lead Partner |  |
| M2.2.3 | Experiments completed with data collected | Carry out experiements when the systems have been properly configured. |  |  | 2 | 46 |  | 52 | 54_SONATRACH |  |
| M2.2.2 | System properly configured for experiments | After the installation of the systems they will be configured so that the planned experiment can be carried out. |  |  | 2 | 46 |  | 51 | 54_SONATRACH |  |

| ## WP2 Task 2.2.4 Results Analysis |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 2.2.4 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| To obtain a better understanding of the human factors involved in the case study and how they affect operator performance and safety of the plant. |  |  |  |  |  |  |  |
| ### WP2 Task 2.2.4 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.2.4 | Sonatrach Final Report on Case Study After Analysis | 2 | 48 | 53 | 0 | 0 | 54_SONATRACH |

## WP2 Task 2.3 AIS TOTAL

### WP2 Task 2.3 - Task objectives and starting point of work at beginning of reporting period

The overall objective of this task is to validate the accident investigation application for TOTAL by porting it to TOTAL to carry out real-life field tests.

### WP2 Task 2.3 - Progress towards objectives

This subtask was scheduled to start in M36. However, it is not due to complete till M52 as there is a large gap between sub-task 2.3.1 and 2.3.2. Therefore, a decision was made to delay the beginning of this task so that resources can be used to advance the other two tasks (2.1 and 2.2) as much as possible first.

### WP2 Task 2.3 - Deviation from the project program and corrective actions taken/suggested

There is no real impact on completing this task just by delaying its start by a few months.

| ## WP2 Task 2.3.1 Case study review |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 2.3.1 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| To review the specified case study continues to meet the requirements of TOTAL before application development begins. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.1 – Progress towards objectives |  |  |  |  |  |  |  |
| The start of this sub-task is postponed till later so that effort can be focused on the StatoilHydro and Sonatrach case studies. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.1 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The postponed starting of this task has not real impact on the final completion as the whole of task 2.3 is not due to complete till M52. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.1 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.3.1 | TOTAL Case Study Specification | 2 | 37 | 47 | 0 | 0 | 05_LAA-P5 |

## WP2 Task 2.3.2 IT tools Installation

### WP2 Task 2.3.2 - Task objectives and starting point of work at beginning of reporting period

To ensure all the necessary IT tools are available and have appropriate interfaces to exchange data the DB. During the installation subtask a first version of the integrated product will be released and possibly installed before testing and validation.

### WP2 Task 2.3.2 - Progress towards objectives

The start of this sub-task is postponed till later so that effort can be focused on the StatoilHydro and Sonatrach case studies.

### WP2 Task 2.3.2 - Deviation from the project program and corrective actions taken/suggested

The postponed starting of this task has not real impact on the final completion as the whole of task 2.3 is not due to complete till M52.

### WP2 Task 2.3.2 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months |  | Used indicative person-months |  | Lead Partner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D2.3.2 | Reports on experiments definition | 2 | 47 | 49 | 0 |  | 0 |  | 34_TOTAL |  |
| ### WP2 Task 2.3.2 - List of Milestones |  |  |  |  |  |  |  |  |  |
| No. | Title | Milestone Description |  |  | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |  |
| M2.3.1 | Systems properly installed | The HF Lab and related IT tools properly installed on a TOTAL site. |  |  | 2 | 47 | 49 | 34_TOTAL |  |

| ## WP2 Task 2.3.3 Testing and validation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 2.3.3 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| To validate that the released product AISVR meet the stated requirements of the TOTAL case study. To identify fine adjustments where necessary. To carry out real-life accident investigation on site. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.3 - Progress towards objectives |  |  |  |  |  |  |  |
| The start of this sub-task is postponed till later so that effort can be focused on the StatoilHydro and Sonatrach case studies. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.3 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The postponed starting of this task has not real impact on the final completion as the whole of task 2.3 is not due to complete till M52. |  |  |  |  |  |  |  |
| ### WP2 Task 2.3.3 - List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D2.3.3 | Report on testing and validation | 2 | 49 | 51 | 0 | 0 | 34_TOTAL |

| ### WP2 Task2.3.3 - List of Milestones |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| M2.3.3 | Experiments completed with data collected | Carry out experiments when the systems have been properly configured. | 2 | 49 | 51 | 34_TOTAL |
| M2.3.2 | Systems properly configured for experiments | After the installation of the systems they will be configured so that the planned experiments can be carried out. | 2 | 49 | 51 | 34_TOTAL |
| ## WP2 Task 2.3.4 Results Analysis |  |  |  |  |  |  |
| ### WP2 Task 2.3.4 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |
| To obtain a better understanding of the human factors involved in the case study and how they affect operator performance and safety of the plant. |  |  |  |  |  |  |
| ### WP2 Task 2.3.4 - Progress towards objectives |  |  |  |  |  |  |
| The start of this sub-task is postponed till later so that effort can be focused on the StatoilHydro and Sonatrach case studies. |  |  |  |  |  |  |
| ### WP2 Task 2.3.4 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |
| The postponed starting of this task has not real impact on the final completion as the whole of task 2.3 is not due to complete till M52. |  |  |  |  |  |  |
| ### WP2 Task 2.3.4 - List of Deliverables |  |  |  |  |  |  |

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D2.3.4 | Final report on case study | 2 | 52 | 52 | 0 | 0 | 34_TOTAL |
| ## WP2 Task 3 Exploitation and Technology Transfer |  |  |  |  |  |  |  |
| ### WP2 Task 3 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| See tasks 3.1-3.5 below. |  |  |  |  |  |  |  |
| ### WP2 Task 3 – Progress towards objectives |  |  |  |  |  |  |  |
| See tasks 3.1-3.5 below. |  |  |  |  |  |  |  |
| ### WP2 Task 3 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| See tasks 3.1-3.5 below. |  |  |  |  |  |  |  |
| ### WP2 Task 3 – List of Deliverables |  |  |  |  |  |  |  |
| See tasks 3.1-3.5 below. |  |  |  |  |  |  |  |

| ## WP2 Task 3.1 Market Analysis Update |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 3.1 - Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| The starting point of this task was the initial WP11, and the market analysis that was the main deliverable report. Based on the work done so far, an update was needed given the change of strategy and the change of project focus. The main interest was emphasised on the tools that VIRTHUALIS will need to use for modelling, risk assessment and risk management. Thus the report is a compliation of what is existing in the market and what is widely used from expert Safety managers and key industries. This will be the starting point for the expert team decision process, since they will get to compare, examine and analyze the existing popular tools. |  |  |  |  |  |  |  |
| ### WP2 Task 3.1 - Progress towards objectives |  |  |  |  |  |  |  |
| Interviews with the relevant companies, internet search and literature search, were the main weapons to tackle the difficulties of producing an analytical "market" analysis. Although the industries and managers were reluctant to share information, the number of interviews (phone discussions mainly) and the internet broad search was enough to finalize the list of more than 20 tools. |  |  |  |  |  |  |  |
| ### WP2 Task 3.1 - Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The slight delay in the delivery was due to the late kick off of the task during the beginning of 2008. However the delay was easily compensated since the deliverable came right on time to coincide with the decision process making of the experts on the task modelling. The review process lasted for one week as planned, and the deliverable report was submitted officially on 25/03/2008. The results were thoroughly used during the decision making and selection of tools, from the VIRTHUALIS consortium. |  |  |  |  |  |  |  |
| ### WP2 Task 3.1 - List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D3.1 | Update of the Market Analysis | 3 | 34 | 34 | 0 | 0 | 14_CERTH/HIT |

| ### 2.38.4 WP2 Task3.1 - List of Milestones |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Title | Milestone Description | WP | Due Date (Month) | Actual/Forecast delivery date | Lead Partner |
| M3.1 | Market Analysis Survey collection | The final date for having information gathered for the completion of the market analysis. The data sourced from internet search and literature search as well as intervies from 2 industrial experts and 1 risk manager (phone discussion). | 3 | 0 | 0 | 14_CERTH/HIT |

## WP2 Task3. 4 Dissemination activity

### WP2 Task 3.4 - Task objectives and starting point of work at beginning of reporting period

Dissemination of scientific results obtained by VIRTHUALIS Project to both scientific and business community. Starting point encompasses a set of communication items, a first dissemination strategy, a dissemination procedure in place, as well as attendance of key international events and publications of papers.

### WP2 Task 3.4 - Progress towards objectives

Networking activities: • MODENA-BRENNERO: Contacted during Ambiente e Lavoro 2007, Modena Brennero joint-stock Motorway Company showed interest in VIRTHUALIS Project, especially for training purposes. Further contacts followed as well as meetings both in Modena Brennero premises (Trento, Italy, August 3, 2007) and POLIMI’s premises (September 26, 2007). • INAIL: After a preliminary contact with INAIL regional representative and INAIL headquarters in Rome, several meetings in Bologna were attended with INAIL National Risk Prevention Manager. INAIL, Italian national insurance agency, recently entrusted by the Italian state with pursuing preventive culture, has shown strong interest and is considering a form of indirect financing, i.e. the financing of a VIRTHUALIS application for one of the companies covered by their insurances. •Presentation of VIRTHUALIS Project results in the conference SDMI in Milos, Greece in June 2007. •Publication of a VIRTHUALIS Project presentation article on Modena University Journal (September 2007) Dissemination Items: Draft versions, (pending feedback and authorization) of: - (IS)2 Family Product Commercial Brochure (layout, artworks, text) - VIRTHUALIS New Project Website homepage (layout, artworks, functionalities) - VIRTHUALIS Interactive Artworks (access to VIRTHUALIS Safety Actions) - VIRTHUALIS Internal Newsletter in html form (1 page) and in Journal Form Research: Deliverable 3.4 (Dissemination Strategy reflecting the changes taking place in Phase II) currently being finalized. Research outcomes are currently being integrated in the current deliverable in order to better assess dissemination approaches to different target users, especially final users. Ongoing: UNIMORE researched the companies’ risk prevention and safety management politics, decision-making models in safety matters, safety investments, and prevention activities organization, training and training didactic methodologies with respect to prevention,cost calculation and preferred choices on safety investments and on safety culture formation processes. The expected research output will be to provide, for each prevention process mentioned above, therelative strengths and weaknesses and to compare them with those offered by Virtual Reality. Final results will be communicated in June 2008.

### WP2 Task 3.4 - Deviation from the project program and corrective actions taken/suggested

Deviations from the project program refer to two critical points already signaled by UNIMORE in the previous Interim Activity Report N°4, namely VIRTHUALIS International Conference and the block of all paper publication prior to August 7th. Unfortunately, no feedback has been given by the current WPII.3 Leader on these critical points, let alone any R&D activities in the previous months notwithstanding recurrent prompting. PMO was duly informed of the issue by UNIMORE jointly with the other Task Leaders within WPII.3. UNIMORE has however agreed with the PMO to collaborate to the proposal a common framework for scientific papers in order to overcome as soon as possible this impasse.

### WP2 Task 3.4 - List of Deliverables

| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months |  | Used indicative person-months |  |  | Lead Partner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D3.4 | Dissemination Strategy | 3 | 35 | 36 | 2 |  | 1 |  |  | 08_UNIMORE |  |
| ### WP2 Task 3.4 - List of Milestones |  |  |  |  |  |  |  |  |  |  |
| No. | Title | Milestone Description |  |  | WP | Due Date (Month) |  | Actual/Forecast delivery date | Lead Partner |  |
| M3 | VIRTHUALIS International Conference | General note on Milestones: Workshops organization depends on the actual release date of the relative System Version. VIRTHUALIS International Conference forecast date (when discussed in November 2007) was month 42. It still pending approval due to the aforementioned deviations. Therefore, for technical reason, a later date than M42 will be chosen. |  |  | 3 | 42 |  | 0 | 08_UNIMORE |  |
| M1 | Workshop System Release V2 | Workshop to be organized after WSR V2 |  |  | 3 | 40 |  | 0 | 08_UNIMORE |  |
| M2 | Workshop System Release V3 |  |  |  | 3 | 46 |  | 0 | 08_UNIMORE |  |

| ## WP2 Task 3.5 Technology training |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### WP2 Task 3.5 – Task objectives and starting point of work at beginning of reporting period |  |  |  |  |  |  |  |
| The objective of this task is to deliver a framework of training and performance support for the implementation of the (IS)2 product family. |  |  |  |  |  |  |  |
| ### WP2 Task 3.5 – Progress towards objectives |  |  |  |  |  |  |  |
| The task has defined, in collaboration with Statoil and software developers a range of target groups, training objectives and for the technology training and a preliminary list of training modules to address these needs. These preliminary training requirements relate to the RAS, OSM and TR VR tools, and the range of users that will interface with them in end-user companies. This work was carried out initially by online collaboration, and then by means of a ocused workshop on 10th April 2008, in Porsgrunn. This workshop advanced both requirements specification and the definition of the training concept. This has brought much clarity to the research tasks of training need analysis and profiling of constraints and opportunities that are currently being pursued. In particular, it became clear that it is difficult to make progress on the end-user training needs independent of detailed knowledge of the software they need to be trained to use. Thus field work to analyse training needs with end-users has been delayed to enable it to be better informed by knowledge of the different software modules. Another outcome has been the crystalisation of the need for a three-way dialogue between this task, HCI developers and software manual authors to clarify the relative roles of training, intuitive design and documentation in guiding end-users. |  |  |  |  |  |  |  |
| ### WP2 Task 3.5 – Deviation from the project program and corrective actions taken/suggested |  |  |  |  |  |  |  |
| The progress of the task, and of the deliverables, was delayed while waiting for clearer specifications of the IS2 tools and case studies. It is difficult to define training requirements before the nature of the tools the training needs to support are. Deliverables 3.5.1 “Training Requirements to support IS” Implementation (Due Month 35) and 3.5.2 “Training concept to support IS2 Implementation (Due Month 37), have not yet been completed. The task is thus delayed by four months. This delay can be accommodated since the initial training delivery for RAS VR implementation in Statoil, has been delayed by three, months and the training requirement for this initial implementation will be small. The work of the task was hampered by the inability of three partners to carry out their roles in the task, for differing reasons. This has been discussed with the parties in question. Two partners (POLIMI and TUC) will be able to contribute in the next implementation period, and the third (LAAP5) will have their resources re-allocated. |  |  |  |  |  |  |  |
| ### WP2 Task 3.5 – List of Deliverables |  |  |  |  |  |  |  |
| No. | Title | WP | Due Date (Month) | Actual/Forecast delivery date | Estimated indicative person-months | Used indicative person-months | Lead Partner |
| D3.5.1 | Specification of Training Requirements to support (IS)2 Implementation | 3 | 35 | 39 | 0 | 0 | 09_TCD |
| D3.5.2 | Training Concept to support (IS)2 | 3 | 37 | 41 | 0 | 0 | 09_TCD |

# Consortium Management

## Consortium Management Tasks

Management tasks were divided into two main blocks: tactical & operational, strategic Tactical & Operational Project Management - Change control - Work schedule performance monitoring - Information monitoring - Inter group alignment and Problem solving - Overall project performance assessment - Quality Assessment and validation of technical accomplishment Strategic • Internationalisation; • IPR management; • Start-up of MOST; • Create alliances; • Exploitation of VIRTHUALIS product(s).

### Task Achievements

Given the enormous amount of problems encountered and the relative corrective actions, management activity has been mainly focused on tactical and operational ones. About: - change control process has been setup and is operational - work monitoring has been performed actively, bringing to the major achievement: first version of (IS)2 as shown at the ARM - technical information monitoring has been implemented only partly; successfull monitoring has been obtained mainly in issues supported by web based management tools (see VDM and WIKI) allowing to follow a bottom up approach in the definition of NIP, PAR and PMR. - Inter group alignment and Problem solving has been performed - Overall project performance assessment: self auditing has not been implemented - Quality Assessment and validation of technical accomplishment has been activated For further details on tactical&operational issues please see section 1.4.

However, as far as strategic activities are concerned, actions were taken on exploitation and internationalization in terms of contact with companies operating as prominent actors in the market, allowing PMO to end up with collaboration agreements, identification of alliances (HONEYWELL and PROTOMATION) and consortium expansion. Moreover about product's exploitation strategy, in the last two months an effort has been done to contact new potential customers (e.g. SNAMPROGETTI, SCHLUMBERGER, ENI, MEIRC Training Centre), and outline a commercial stratagy to bring the product to the market.

### Problems occurred and actions taken

- WPII-1 leader withdrawal Steen Weber resigned from WPII-1 leader on 11th february due to health reasons. PMO has requested immediately to the Consortium who could have covered this role. Only Luca Vezzadini answered offering to play this role, but the PMO decided not to accept due to his critical role in task 1.3 leading. Thus the PMO activated the search for a skilled product manager to be appointed. In the meantime the RTD manger took over the WP Leader role with the support of Peter Kafka for a specific contribution based on his safety skills. The search has taken long time, until mid june, when Raffaella Folgieri started her co-operation. - WPII-3 leader defaulting and hostile actions INVENSYS organized the first kick-off meeting of WPII-3 lately at the end of january 2008, despite scheduled on early december (2 months delay). WPII-3 task leaders have been without a coordinating guidance. Even after that meeting the only action taken by INVENSYS has been to invite VIRTHUALIS consortium to present a demo of the VR subsystem at an INVENSYS internal commercial event in Abu Dhabi, on 10-12th february. INVENSYS attempted to announce the VR application as the result of their own development without recognizing it was the result of VIRTHUALIS project. PMO asked to correct the public statement, but after the meeting new unauthorized public communications have been released. As soon these malicious actions have been discovered, PMO has taken all the appropriate initiatives to protect consortium interests, image and reputation. - Replacement of INVENSYS technical competences (OTS and process simulation) The defaulting of INVENSYS has weakened the effectiveness of VIRTHUALIS project, since we lost a technical competence in OTS and process simulation issues. To solve the problem contact with Honeywell and Yokogawa has been activated by PMO. Meetings to demonstrate the product being developed and the collaboration needs have been organized. Honeywell expressed its strong interest to contribute to the success of the project and has been available to organize a technical and a commercial meeting. The technical meeting has allowed PMO to illustrate the general architecture of the product, which revealed its coherence to VIRTHUALIS new architecture. The decision has been taken to continue the technical analysis to arrive in september to start a collaboration to integrate OTS Honeywell system with VIRTHUALIS platform - SONATRACH use case selection change A first proposal of a case study has been presented by SONATRACH at the kick-off meeting of WPII-2 in Paris in january 4th 2008. The proposal has been evaluated by the PMO who unanimously decided it was too complex and inadequate to evaluate human factors issues, even if the case was of particular importance and interest. A negotiation started with SONATACH, which ended up with a meeting with PMO and SONATRACH engineers in Oran, 26-27th february, where, among three case studies proposals, one has been selected as appropriate for the project purposes. - STATOILHYDRO charged personnel change At kick-off meeting of WPII-2 in Paris, january 5th, new charged persons from STATOILHYDRO partner were present. In the meeting a complete, despite quick, presentation of VIRTHUALIS project and its outcome has been illustrated. To foster the take over of new personnel, 2 meetings have been organized: to visit Kårstø plant and Porsgrunn VR Lab and to meet local contact persons. Moreover frequent mail and phone contacts have been also organized to increase their involvement, perception and commitment. To further improve commitment and project objectives understanding two field operators have been invited to perform a usability test of the HFLab. - Defaulting or non acting partners (EB) On may 28th the Executive Board meeting has been organized in Paris. Among other issues a decision has been taken to exclude 17 partners from the consortium for defaulting, non-performing or non-relevant contribution. - Demo Group creation In mid january 2008 before the second internal review of SafeVR platform, the concept of a Demo Group has been created. The reason for this is twofold: first to have a group of partners with previous experience in organizing and performing technical demonstration of commercial software products, second to set up a preliminary organization to provide customer support for the exploitation phase of the project. The coordination of Demo group has been assigned to MW partner who has long experience in these activities. The activity of Demo group has been effective in the preparation of two public events: the INVENSYS Abu Dhabi End User Conference and the PSAM 9 conference in HongKong. The Demo group also coordinated the APM and ARM. - Definition of ARM demo script and rehearsal On May 13th PMO has started the organization of APM and ARM. To this aim a specific focus has been put on the preparation of the DEMO session for the ARM meeting. On the WIKI server a page has been created to describe the organization of the DEMO. Moreover PMO decided that a rehearsal was necessary to tune the demo presentation as well as aligning project vision with all partners. The APM has been chosen as the best moment to do the rehearsal. This was also on of the major reason to keep APM and ARM separated - End User usability test with field operators After the completion of WPI-6 end of january it was evident the necessity to plan and organize usability tests with end user. To this aim specific request has been done to STATOILHYDRO partner to check the availability of field and control room operators to come to Milano and perform the test. The purpose of this test was first to check usability and second to get useful suggestions and comments to improve the HFLab. The usability test has been run on june 5th and 6th, and was very successful. - Identification of a Knowledge Base systems expert The decision to extend the simple database approach to analysis of experiments result to develop a new Knowledge based system was taken at the previous NIP last november 2007. To this aim a search of an expert has been undertaken. The selected expert is prof. Gian Piero Zarri, who has been doing research in KB systems since ysars in different application areas, in particular, recently, in the field of terrorism and military issues. Prof. Zarri has been member of CNRS France, and is now appointed as professor at Paris Sorbonne University. - Redefinition of VIRTHUALIS (IS)2 product architecture The overall architecture of (IS)2 system as defined in previous NIP was based on a common element, the Data Base, and divided into two main subsystems: the HFLab subsystem and the ITTools subsystems. During the first months of work, it was clear that this approach was limiting the possible evolution of VIRTHUALIS platform. The adoption of an open architecture, based on Netbeans and JAVA, simplifies the implementation of a flexile system, capable of integrating internally developed tools as well as commercial ones. Thus the decision to re-design the system architecture. - Centralization of SW development server Project activities, both programming and data repository, were distributed among partners involved in SW development: VR&MMP for the VR development, EXIMIA for ITTools development and POLIMI for data repository and project management tools. Following the establishment of the IT Office at PMO, as decided in NIP M24-M42, it has been decided to centralize the IT infrastructure at POLIMI, in the perspective of rely on an externalized service to guarantee 24/7 support and backup, and to provide the maximum flexibility to manage IT infrastructure for project management and operation. - Quality assessment of SafeVr platform Given unsatisfying results achieved and shown at the internal review on december 2007 and january 2008 of SafeVR platform, PMO charged quality assurance group to perform a quality assessment of the software. Based on those results, the following three decisions were taken: 1 - to reduce to MM declared by the development group for task WPI-6 2 - to freeze development of new features of SafeVR platform and focus on improving the usability 3 - Change task leader for the Task 1.3 (continuation of task WPI-6), assigning this role to MW - Delay in EC funding The NIP M25-M42 has been officially sent over to EC offices on december 21st. Forseen payment, after amendment acceptance, was expected by mid february 2008. Fruitful and collaborative daily contacts with EC offices allowed to solve the issue by end of april, thus reducing the negative effect to further delay the recruitment of skilled programmers. - WP and task leaders did not always formally reported as planned.

## Changes in the consortium

### Changes in contractors’ responsibilities

DTU has taken over the rights and obligations of Risø as of 01 January 2007.

### Changes to the consortium itself

5 new partners are joining the Consortium: Pt53 OvGU (VR expert) Pt54 Sonatrach (Industrial partner) Pt55 POLITO (RA expert) Pt56 Relconsult (RA expert) Pt58 ISI(Industrial partner) Pt59 Solvay(Industrial partner)

2 partners withdraw: Pt10 UNITO, Pt22 TNO 17 partners were excluded from the Consortium: Pt4 LIU; Pt5 LAAP-5; Pt6 STUBA; Pt13 VTT; Pt16 KOMAG; Pt21 IFF; Pt30 BP; Pt31 CARBID-FOX; Pt33 SADACHIT; Pt42 OXONO; Pt44 CARIM-UBB; Pt45 SAUF; Pt46 DNV; Pt47 CAPSICOM; Pt48 EUROGIF; Pt49 OGP; Pt58 INVENSYS;

### Project timetable and status

# Year 4 and 5 - 01.05.2008 – 30.05.2010

Publishable Executive Summary

The VIRTHUALIS project, originally planned to last 4 years, in practice lasted 5 years. This prolongation was necessary to face the complexity of the activities but sufficient to reach the aimed goal: develop two industrial applications for two different companies and install them on their Virtual Reality Labs.

The two industrial applications produced and installed are as follows:

1.	The “gas leak management” application, installed at the Virtual Reality Lab of STATOIL (Norwegian Oil Company)

2.	The “gas turbine start-up” application, installed at the Virtual Reality Lab of SONATRACH (Algerian Oil Company)

Both applications, despite conceived for completely different purposes, were meant to be used for training operators and help trainers and HSE managers to take decision using an experimental approach.

The VIRTHUALIS project ended up with is a solution that enables to:

1.	Recreate, by means of immersive Virtual Reality, a realistic field of operations

2.	Link the immersive Virtual Environment, reproducing the field of operations, with the reproduction of a control room to allow control room operators and field operators to collaborate in a Virtual Environment to test coordination, communication and control task and prediction.

3.	Train operators by means of live experiment, manage operational safety, and perform live risk assessment and realistic accident investigation

4.	Record experiments

5.	Review experiments for decision-making purposes

All in all, the VIRTHUALIS consortium gathered something around 50 partners from 17 European and pan-European countries and had a budget of 15M€.

The spectrum of competencies needed to achieve the VIRTHUALIS solution was pretty large, namely (a) IT, (b) Virtual Reality, (c) Safety Engineering, (d) Human Factors. The competencies have been brought in the consortium by different type of partners such as academia, industry (large and SME), consultants and research centres.

Despite the many difficulties encountered during the project due to the inherent difficulty in achieving the goals (interdisciplinary of the activities, consortium structure, immaturity of VR technologies) the project closed successfully and with something concrete to exploit for the future, thus giving value to the 9M€ of “seed capital” for RTD given to the consortium by EC.

# Project Objectives and major achievements during the reporting period

## Overview of general project objectives and relation to state-of-the-art

The objectives of this last period were as follows:

- Complete of the VIRTHUALIS software and applications development

- Install the applications in the 2 identified industrial sites, i.e., STATOIL and SONATRACH

- Perform technology training to the 2 companies

- Perform a market analysis

- Create a business plan to assess the feasibility of setting-up a company after the project

All the aforementioned objectives were achieved successfully by the end of the project.

## Summary of the recommendations from pervious review

Recommendations from the review were as follows:

The project sees the risks as a) lack of commitment from the project partners and b) inadequate technology.

These risks are judged to be realistic and likely to come about, jeopardising a successful conclusion to the project unless:

- A clear view of the expected outcomes and their application is developed and ‘involvement’ and ‘buy-in’ to a shared view of the outcomes is achieved

- The work is driven by support of the user scenarios and feedback of the findings rather than by IT research interests

- Coherent teams with strong project management are formed, focussed on, and taking ownership for, project sub

- Mitigation plans are drawn up to address the possibility that certain parts of the complete platform won’t be present – which should not be allowed to prevent the validation of the methodology in a less integrated manner

All the recommendations were properly listened to and corrective actions put in place.

## Objectives for the reporting period, work performed, contractors involved and main achievements in the period

Summary of the objectives for the reporting period, work performed, contractors involved and the main achievement in the period.

### Objectives for the reporting period

The objective subdivided by WP and Task were as follows:

WPII.1

The overall objectives of this WP were to complete the development of the IT Tools and the HF Lab. The Quality Assurance Task guaranteed the production of a standard quality product and its coherence to human interface good practices.

Task 1.1

This Task consisted of four main activities:

- Methodologies consolidation and integration into safety engineering models

- Definition of the Functional attributes of (IS)² system and tools in relation to specific industrial needs

- Definition of the system and tools quality attributes

- Detailed design specifications of the various IS2 components (IT Tools)

Task 1.1.1

The goals of Task 1.1.1 was that of creating two frameworks of work, namely:

- For the average user

- For the advance user

Both goals have been achieved.

Task 1.1.2

This goals of Task 1.1.2 consists of the following activities:

- Definition of the Functional attributes of (IS)² system and tools in relation to specific industrial needs

- Definition of the system and tools quality specification definitions

- Detailed design specifications of the various IS2 components (IT Tools)

Task 1.2

The goals of this Task are as follows:

- Creation of a highly integrated software platform that represents the foundation of all the IT Tools

- Managing the quality process of development needed to obtain a high professional product, based on two major versions

- Produce and integrate the related documentation

The goals of this task have been achieved.

Task 1.2.1

The main objective of this task is to build the IT-sub modules needed for the integrated applications.

Task 1.2.1.1

The goals of this task are as follows:

- Design and implement a Database capable to

  - Store the configuration and the results of experiments carried out in the HFLab

  - Query the data to extract information of interest to human factors and safety experts

- Development of the Log Post-Processing Tool (LogPP) with that of the Database (since the two are closely related)

Task 1.2.1.2

The goals of this task were as follows:

- Detailed design and implementation of the

  - Fault Tree Builder

  - Event Sequence Builder

The FTB and the ESB where never developed as eventually conceived not so innovative compared to the other tools developed.

Task 1.2.1.3

The goal of this task was as follows:

- Develop a software tool for guiding the collection data to be analysed and then represented using the Virtual Reality.

Its scope is to provide a structure for the interviews and for the graphical representation of the Task so that it can be a common means of communication between the technical personnel involved in the interviews, the human factors expert and the VR expert to reach a common understanding of a Task, its main objective, challenges and criticalities.

Task 1.2.1.5

The goals of this task were to as follows:

- Clarify the specifications to link the ALBA for VIRTHUALIS tool to the VIRTHUALIS infrastructure

- Develop the link with the ALBA for VIRTHUALIS tool

- Develop an application of the ALBA for VIRTHUALIS tool both for the STATOIL case study and for the SONATRACH one

It has been capitalised the experience gained on the logic approach of the Integrated Dynamic Decision Analysis.

Task 1.2.1.6

The goal of this task was to develop the FPE module.

Task 1.3

This task is achieved by means of 4 subtasks.

Task 1.3.1

The goals of this task were as follows:

- Perform several sessions of usability tests on the Risk Assessment tool produced in WP I.6

- Prepared and supported the Abu Dhabi demo at Invensys’ Showcase event

- Integrate the AXIM module for accident simulations

- Develop and apply constant updates for the SafeVRViewer

- Initiate technical discussion with Task 1.2 group to define the integration between IT tools and HF Lab

- Migrate the development environment to use VisualStudio 2005 and Delta3D 2.0

- Support the Demo Group in preparation for ARM demo

The task concluded successfully.

Task 1.3.2

The goals of this task were as follows:

- Various sessions of usability tests on the RA as this was produced by WP I.6

- Preparation of the Statoil use case

Eventually, this task closed successfully.

Task 1.3.3

The goals of this task were as follows:

- Preparation of the SONATRACH use case

Eventually, this task closed successfully.

Task 1.4

The goal of this task was that of Product Quality Assurance.

WPII.2

The objective of this WP was the Field Test and Validation of the two case studies, i.e., STATOIL and SONATRACH.

All in all the two use cases completed successfully accomplishing the planned tasks. The only activity that was not possible to achieve was the installation of the SONATRACH application to the SONATRACH VR Lab. This for a twofold reason: the ash cloud that impeded partners to travelling and the not-readiness of the VR Lab at SONATRACH premises. The SONATRACH application was the installed at showed at the final review meeting in the Milan VR Lab.

Task 2.1

The work of this task, specifically devoted to the STATOIL use case, has been split in four sub-Tasks:

- Sub-Task 2.1.1 (Case study review)

- Sub-Task 2.1.2 (IT Tools installation and experiments definition)

- Sub-Task 2.1.3 (Testing and validation)

- Sub-Task 2.1.4 (Results analysis)

Task 2.1.1

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.1.2

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.1.3

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.1.4

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.2

The work of this task, specifically devoted to the STATOIL use case, has been split in four sub-Tasks:

- Sub-Task 2.1.1 (Case study review)

- Sub-Task 2.1.2 (IT Tools installation and experiments definition)

- Sub-Task 2.1.3 (Testing and validation)

- Sub-Task 2.1.4 (Results analysis)

Task 2.2.1

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.2.2

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.2.3

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

Task 2.2.4

The goals of this task were as follows:

- Review the STATOIL use case and detail the development specs and needs

- Review the SONATRACH use case and detail the development specs and needs

WPII.3

The objectives of this WP were as follows:

- Updating market analysis;

- Identifying the exploitation routes for VIRTHUALIS results, to be reflected in a realistic exploitation plan;

- Using of practical results for dissemination/exploitation strategy;

- Establishing key-contacts with End Users;

- Establishing strategic alliances with vendors of complementary solutions (CAD/PLM solutions, process simulation solutions etc) engineering companies; market influencers (insurance companies);

- Creating cost benefit and cost effectiveness models for the thorough market analysis;

- Developing and validating training and performance support for key user groups such as trainers, safety analysts and managers;

- Delivering introductory workshops on the (IS)2 and its use

### Work performed

Task 1.1.1

The framework created for the average user includes:

- The Task modeller

- The safety barrier diagrams

- The fuzzy probability estimator

- The fault tree analysis

The framework created for the advanced user includes

- The dynamic event graph

- The accident investigation tool

The deliverable of Task 1.1.1 comprises an executive report that explains the inter-links between the HFs methods and four appendices that provide detailed descriptions of the following methods:

- Appendix 1: The Task Modeller

- Appendix 2: The Fault Tree Analysis

- Appendix 3: The Safety Barrier Diagrams

- Appendix 4: The Fuzzy Probability Estimator

- Appendix 5 describes the accident investigation method (the same method used in WP5 of Phase I)

- Appendix 6 describes ALBA (prev. DET) (in preparation).

Task 1.1.2

The specifications in detail are as follows:

- Db and DbQ: specs are completed and specified in the document "VIRTHUALIS DB & LogPP SRS v1.4"

- Task modeller: the Software Requirements Specifications are completed “VIRTHUALIS Task Modeller SRS v1.1”

- Alba (Det/Deg): actually there is a software prototype but no documents with specs were needed as already existing prior to the project

- LogPP: specs are available in the document "VIRTHUALIS DB & LogPP SRS v1.4”

- FPE specs available

- FTB-ESB: specs are available in the document "VIRTHUALIS-FTB-ESB-WPII.1-SRS.doc"

The activities planned are completed.

Task 1.2.1

The work achieved in this task is

- A highly integrated software platform that represents the foundation of all the IT Tools

- A set of integrated IT Tools to perform analyses

Task 1.2.1.1

The picture to follow depict the work done in this task and the functioning of the tools.

The Database and Log Post-Processing Tool are documented in the Software Requirements Specification (SRS) called "VIRTHUALIS DB&LogPP SRS".

The Database Query Tool is documented in the Software Requirements Specification (SRS) called "VIRTHUALIS Database Query Tool (DBQ) Software Requirements Specification".

- Release 1 (R1) of the Database is completed and conforms to the Java Enterprise Edition architecture devised by Eximia. Each database entity (at least, those required in R1) has been built, along with its facade. Session facades for the Task Modeller and Database Query IT Tools is also provided

- Release 1 of the LogPP Tool, being built by KITE, is completed

- Release 1 of the Database Query Tool, built by UNIMI, is completed and runs predefined queries

Synthetic data has been generated to test the IT Tools, based on the Risk Assessment application on the Polimi Gas Processing Plant.

Task 1.2.1.2

The detailed specification of the tool has been completed for the FTB part, while the ESB was not concluded.

A first raw version of the FTB tool, subsequently frozen for lack of resources, was developed in java in order to show

- The main features of the tool

- The user-interface for the input phase of the analysis

The choice of using an external solver has been made and its characteristics clarified. Deliverables produced are as follows:

- Detailed specifications of FTB+ESB tools

- Stand alone version of FTB+ESB tool October 2008

Task 1.2.1.3

The work performed in this task can be summarised as follows:

- Review of the state of the art in the field of Task analysis, commercially available Task analysis software and workflow modelling software (like Microsaint)

- A review of state of the art in Task representations notations; selection of appropriate notation

- The methodology used for Task analysis and modelling was formalised and reviewed for building up the bases of the software requirements

- The Task modeller approach has been tested for the representation of the Statoil preliminary case study and the results obtained have been transferred to another the ALBA for performing quantitative analysis

- Software requirement document for the tool was produced and reviewed by partners

- Software development of the tool and the prototyping of the Graphical User Interfaces (GUI) for the structured interview template started and are currently under development

- The interface with the Task tracker to allow delivery of Task model information into a suitable XML scheme under development

The achievements are as follows:

- Business Process Modelling Notation (BPMN) selected.

- Workflow modelling software selected - The development has been performed using a common platform for all the IT Tools within the VIRTHUALIS consortium. The implementation has been based on an Enterprise application System called NETBEANs, the language used for coding is JAVA.

- Task modelling methodology finalised and tested on Statoil case study

- Software requirements specified

Task 1.2.1.5

The work done in this task was to:

- Clarify the specifications to link the ALBA for VIRTHUALIS tool to the VIRTHUALIS infrastructure

- Develop the link with the ALBA for VIRTHUALIS tool

- Develop an application of the ALBA for VIRTHUALIS tool both for the STATOIL case study and for the SONATRACH one

The use of the ALBA for VIRTHUALIS tool has been successfully applied for

- The development of the STATOIL use case

- The development of the SONATRACH use case

In particular, for the development of the SONATRACH use case, the application of the ALBA for VIRTHUALIS tool was essential for the completion of the use case.

Task 1.2.1.6

The work done and the achievements are as follows:

- The development in C++ of the FPE code

- The fuzzification procedure based on the CREAM methodology

- The testing of the FPE

- Production of the user manual

The fuzzy model developed includes nine input variables similar to the common performance conditions of this methodology and one output parameter (action failure probability of human operator).

The results of the fuzzy model, which are in the form of crisp numbers, is to be used directly in the fault trees and event trees calculations for the quantification of specific undesired events that include the interaction of human factors in their modelling.

The source code has been jointly written in C++ by DEMOS and POLIMI staff, under the quality setting and review of OVGU.

The run tests have been done in a 3 days meeting in Athens. Together with the code a development/use manual has been produced (as internal Deliverable-Milestone) under the title M3.6.1.

Task 1.3.1

The work done and the achievements are as follows:

- Performed several sessions of usability tests on the Risk Assessment tool produced in WP I.6, especially for Field-Operator UI. Several changes defined in these sessions have then been applied to the software.

- Prepared and supported the Abu Dhabi demo at Invensys’ Showcase event.

- Started the integration of the AXIM module for accident simulations; the first targeted feature is to compute the gas cloud generated by a leakage. AXIM will replace the previous module called “GDM” (GDM was preciously used but only for the pool-fire case).

- Developed and applied constant updates for the SafeVRViewer, to run platform features and run tests on stereo vision (HMD and virtual theatre at Unimi premises), interaction modes, interaction devices (like trackers, wiimote), motion models.

- Initiated technical discussion with Task 1.2 group to define the integration between IT tools and HF Lab. The decision is to use a common Data Abstraction Layer and only share the data, so to avoid any direct link between HF lab and IT tools. Also interacted tightly with subtask 1.2.2 to define database structure and also to detail the Log Post-Process tool and its link to the database.

- Migration of the development environment to use VisualStudio 2005 and Delta3D 2.0. This migration was needed on a technical level and it has brought some clear advantages in the daily work of the dev team.

- Supported the Demo Group in preparation for ARM demo.

The task completed successfully.

Task 1.3.2

The work done and the achievements are as follows:

- Various sessions of usability tests on the RA as this was produced by WP I.6, especially for the Field-Operator UI were executed. Several changes defined in these sessions have then been developed in Software. This has regarded improving overall User Interface readability, modifying user interface to improve interaction with plant elements and their properties, changing the way a user may switch between the different application modes (navigation, operation etc), providing a more intuitive control of the Portable Gas Detector probe utilizing the Wiimote’s ability to report its position and orientation, modifying the Portable Gas Detector to act in a more realistic way by continuously reporting measurements coupled by audio feedback

- The Statoil use case was prepared. At first, a detailed scenario has been drawn that reflects the needs reported by the industry. Various visits to the plant were performed to support this Task and help clarify the applications’ requirements. Having this scenario as a point of reference, a new set of required features has been identified resulting in the production and finalization of the tool for risk assessment specifications.

- In order to adapt the existing applications to the Statoil use case, the actual working environment needed to be represented in the virtual world. Towards this goal, Statoil provided CAD data regarding the targeted part of the plant that are being refined in order to be used by the platform. Further to this, visits to the plant were organized and a substantial amount of images and sounds were collected and used along with the CAD data to produce a realistic model of the real plant.

Further from this during the reporting period, the case study preparation of scenario data for the Statoil use case (mainly the 3D models and the sound design of the ALDS unit of Karsto plant) was executed. Various visits to the plant were performed in April 2008 to collect needed data for building the simulation scenario and also to define the particular Statoil requirements for the application and thus aid the specifications extraction. This Task has resulted to the production and finalisation of the RASVR specifications.

Task 1.3.3

The work done and the achievements are as follows:

- Analysis of the data needed to run the simulation and the work required to prepare it.

- Visit to the Sonatrach plant has happened in march 2008, including also people from the HF Lab team in charge of producing the 3D models of the scenario to simulate.

- Creation of the SONATRACH use case

Task 1.4

The objective of this task has been to validate the added value of “VIRTHUALIS IT Tools” for improving safety, without any consideration of Virtual Reality aspects..

It has achieved the preparation of the working concept and procedure for the IT tool validation process, based on the review the End Users and methodological needs collected during the project and on the review functionality that IT Tools should provide, as designed in  Task 1.2. A specific evaluation table has been completely developed on the example of Risk Assessment, while preliminary work has been undertaken to evaluate the added value of specific IT tools with respect to the tools available at the market place (e.g. TM, FPE, Alba, Axim). Identification has been also made of some industrial companies interested by the test of the IT Tools.

Task 1.5

The work done and the achievements are as follows:

To cope with the project needs and challenges that have been defined in phase 2, the goal of the Product Quality Assurance has been fixed to assuring the quality of the developed IT tools by fulfilling predefined industrial requirements.

A special attention has been paid to the aspect of user-friendly interfaces to facilitate the process of integrating these tools in an industrial infrastructure.

Based on that, the Quality Assurance Group introduced the Software Quality Assurance Process (SQAP) so that the developers who contribute to software development align their efforts through a well defined process of specifying, developing, documenting and testing their own code. This SQAP has been adopted by the developers group drawing the first system specifications and starting development work on the IT-tools.

The QAG also delivered the Product Implementation and Test Plan (PITP) that details the work that shall be carried out in order to perform the quality test of the individual IT tools and the overall resulting product. The QAG assisted also various Task leaders while defining system specifications for each IT module.

Task 2.1.1

The work done and the achievements are as follows:

- First case study specification meeting was held in Paris on 3rd January 2008. The meeting was hosted by INERIS and was attended by all partners involved in this work package. An interim meeting was held in Milan to review progress on 20th March 2008. The meeting was hosted by UNIMI and was attended by DAPP and LBORO

- Second case study specification meeting was held in Posgrunn, Norway on 9th April 2008. The meeting was hosted by Statoil and was attended by all partners involved in this work package. In between meetings DAPP worked closely with Statoil and DTU to complete the deliverable.

This Task was completed.

Task 2.1.2

The work done and the achievements are as follows:

- This sub-Task has achieved its goal of describing how the HF Lab should be configured to simulate different situations for the experiments

- The milestone on the proper installation of the systems was achieved

- Part of the experiment definitions was described in deliverable

Task 2.2.1

The work done and the achievements are as follows:

- A meeting was held in Paris on 4th January 2008 to begin the process of case study specification for Sonatrach, attended by all partners involved in this work package. However, The initial case studies suggested by Sonatrach were thought to be inappropriate as they were either too simple or not process focused. Therefore, considerable effort was put into identifying a suitable case study that will bring significant benefits to Sonatrach and the VIRTHUALIS project.

- A field trip, involving the project management team, to the Sonatrach plant took place in April 2008 to explore possible case study scenarios and a particular case study scenario was identified. A subsequent meeting was held in Paris on 24th April 08 to plan to develop the case study further. Hence the actual work on developing the specification for the case study was delayed. However, after a slow start, the work on this sub-Task is progressing satisfactorily. A field trip to Sonatrach took place in June 2008.

This Task was completed.

Task 2.2.2

The work done and the achievements are as follows:

- This sub-Task has achieved its goal of describing how the HF Lab should be configured to simulate different situations for the experiments

- The milestone on the proper installation of the systems was achieved

- Part of the experiment definitions was described in deliverable

Task 2.3

Task 2.3 has four sub-Tasks:

- sub-Task 2.3.1 (Case study review),

- sub-Task 2.3.2 (IT Tools installation and experiments definition),

- sub-Task 2.3.3 (Testing and validation) and

- Sub-Task 2.3.4 (Results analysis).

This Task was scheduled to start in M36. However, it was not due to complete till M52 as there was a large gap between sub-Task 2.3.1 and 2.3.2. Therefore, a decision was made to delay the beginning of this Task so that resources could be used to advance the other two Tasks (2.1 and 2.2) as much as possible.

Task 3.1

The objectives of this task can be summarised as follows:

- identify the industry final end-users needs in terms of safety and in terms of the 4 safety actions;

- identify the market of reference given the IS2 developed from November 2007 onwards;

- perform a market analysis given the 2 points above, aiming at developing an analytical tool required to perform task 3.2 hereunder.

The objectives have been met and the whole market analysis (deliverable 3.1) was finalised by the end of September 2009 and revised and updated by the end of March 2010.

Task 3.2

The main objective of the task was to define the business area of VIRTHUALIS IS2.

The starting point was the identification of a three dimensional Abell diagram.

Abell identifies on a three axes diagram the following three functions/groups:

- Customer Groups, referring to “who needs to be served”

- Use Functions referring to “what do customers want, what need has to be satisfied” i.e. identification of customer needs.

- Technologies Utilized refer to “what means should be used to carry out the use function” that is the way that the needs are being satisfied.

The advantage of this approach is to analyse business not only in terms of products and market but also in terms of technologies to be utilized and identification of customers’ needs.

The scientific method used in WP II 3.1 and 3.2 was not a strictly deductive one but it required a certain amount of reiteration between the assumptions and analyses of WP II 3.1 and 3.2 (and vice-versa), thus reaching a sufficient basis required to develop the most important achievement of WP II 3 which is the Business Plan i.e. deliverable under WP II 3.3 below.

Task 3.3

The objective of this task was the preparation of a full document along guidelines prevailing in the business community, describing the business and market strategy envisaged for the future of IS2, i.e. a business plan and information memorandum.

Work started in July 2009 and the first decision in preparing the Business Plan was to include all or most of the work done in WP 3.1. and 3.2 but in inverted order, i.e. a definition of the Business area of IS2 first and a market analysis afterwards.

The outcome of the task is a document that not only deals with the main objective of the task, i.e. the development of a market strategy, but goes beyond that by outlining and implementing concrete facts towards the constitution of the future small independent company and the structure and mission of the network envisaged for VIRTHUALIS after the end of the actual project.

Task 3.4

This task deals with the dissemination of project results and has achieve its mission by several publications, road shows presentations of VIRTHUALIS, brokerage events and the constant interconnection with the industry that applied this technology.

Task 3.5

The objective of this task has been to deliver a framework of training and performance support for the implementation of the Virthualis tools.

It was originally envisaged that this task would deliver face-to-face workshops to the end users. However, deviation from the planned task was necessary because - delays in software development and deployment meant resources had to be re-directed to ensure delivery of the VR lab - Statoil were not prepared to commit additional resources to accommodate the training need analysis and training delivery until they had installed and piloted the software - the target group was narrowed - the methodology expertise is widely distributed in the consortium so a methodology needed to be found to effectively bring that expertise to the end-user - web-tutorials were chosen as the most effective means of bringing expertise from across the consortium to the Statoil end-users - Delivery of training in Sonatrach to the same extent as Statoil since the end-user resources were focussed on ensuring installation and piloting of the VR lab.

### Contractors involved

POLIMI, DAPP, DEMOS, UNIMORE, TCD, DTU, UNIMI, CERTH/HIT, TUC, KITE, INERIS, STR, EXIMIA, MW, LBORO.CO, VR&MMP, ICCS, IFF, TECNATOM, TOTAL, STATOIL, S-VURUP, PFI, OVGU, SONATRACH, POLITO, RELCONSULT, SIS, EIMM.

### Main achievements

The building of the HF lab has been completed together with a “bouquet” of additional Risk Analysis tools that have been implemented in two real case studies, namely in the STATOIL and SONATRACH companies.

## Problems encountered and corrective actions

Task 1.1.1

Problems encountered

The deadline for delivering the work of Task was month 34 but the individual HFs methods were delayed until month 36 and the overall deliverable until month 37 (end of May 2008).

The reasons for the delay were:

  - The incorporation of a new method (i.e., the safety barrier diagrams) for the average user

  - The development of ALBA (prev. DET) that relied on the modelling of a large number of system states and the response of the operators. The issue of data availability from operators and the plant simulator was a critical concern.

  - The starting date of Task 1.1.1 was delayed until January 2008

  - The introduction of new partners mainly in the group of tools that had to do with quantification. POLITO was a new partner whilst POLIMI introduced a new team to work in Task 1.1.1.

  - The application of the framework to several case studies beyond the case studies of the project in order to ensure its general applicability.

Because of these delays, an effort was made to communicate the specification of the HFs methods to the IT experts so that the adverse impact would become smaller. This risk was anticipated in the start of Task 111 and all Task leaders of the IT tools have been included in Task 1.1.1 as partners. Hence, information on methods of Task 111 was passed by the Task leaders to the IT experts for the development of the IT tools.

Corrective actions

Given the inherent difficulty linked to the methodological framework being created, the only include: Expand Task 1.1.1 until month 39 in order to achieve the following objectives:

- Finalise the deliverable for the average user (end of May 2008)

- Finalise the deliverable for the advanced user with the inclusion of the dynamic event graph (end of July 2008).

The expansion of Task 1.1.1 resulted in an increase of man-power from 16 MMs (end of April 2009) up to 24 MMs (end of July 2008). Since the initial budget for Task 1.1.1 was 18 MMs, the corrective action required internal transfer of 6 MMs from existing resources of other Tasks.

The corrective action allowed to reach the goal.

Task 1.2

Problems encountered

- Delay in producing system specifications (related to the Task 1.1.2)

- Lack of global product vision

- Not uniform programming skill level across the team

Corrective actions

- Encouraging the use of the Wiki environment to facilitate the production of the specs and the documentation

- Workshop based methodology and training performed by Eximia to all the team involved partners

The corrective actions allowed reducing the problems and reaching the goals.

Task 1.2.1

Problems encountered

- Lack of well defined and completed specifications, related to the Task 1.1.2

- Not uniform skill level across the team

Corrective actions

- Encouraging the use of the Wiki environment to facilitate the production of the specs and the documentation

- Workshop based methodology and training performed by Eximia to all the team involved partners

Task 1.2.1.1

Problems encountered

- Absence of detailed user requirements for the IT Tools

Corrective actions

- A document was produced (by LBORO with contributions from KITE, TCD, DEMOS, IFF, OVGU & EXIMIA) called "Notes for the VIRTHUALIS IT Tool Specifications". This stated, in plain language wherever possible, a vision of how all the IT and HFLab Tools could work together with each other and with the Database.

The corrective actions allowed to unlocked the situation and reach the goals.

Task 1.2.1.2

Problems encountered

No deviations from the project program were recorded apart from a little delay in the delivering the documents and IT tools.

Task 1.2.1.2

Problems encountered

The main problems encountered were the selection of an established standard notification for graphically representing a Task and the integration of the Task Modeller (TM) specification with that of other IT tools. These have led to a delay in TM development; this was not a critical problem as it was less than the delays in the development of other tools and the implementation schedule for the case studies.

Task 1.2.2

Problems encountered

Some problems arose due to integration with all the legacy code developed in Phase I. The problem was overcome with the re-writing of the code.

Some other problems were related to the integration with products "windows-based" that were not multiplatform by architecture constrains.

Task 1.3

Problems encountered

After the review at the end of WP I.6, it has been decided by PMO and RTD Manager to focus the attention mainly to improve usability, especially for the 3D navigation and interaction modes. This has consequently reduced the effort to be put on specific new features. For this reason, the development of new functionality (like the configuration editor) has been delayed and started only in M39, so to give time to the various stakeholders to better define the needed features and their priorities.

Task 1.3.1

Problems encountered

Due to a change in planning and in receiving input data, the deployment of the Statoil use case has been postponed by 4 months. Therefore the first release of the HFLab (tagged as Rel1 in the work plan) was delayed as well. This did not change the work management anyway, as it simply allowed for more features and detailed implementation to happen in time for the first use case. The planned iterative development cycle was maintained as planned. Also, because of an increased effort on usability issues, not a lot of new features have been developed in the 4 months of Task 1.3.1. The work on new features eventually was fully operational after M39.

Task 1.3.2

Problems encountered

Due to the early stage of the HF specifications and thus technical requirements from the HF side, at the beginning stage of the Task, the application developments were frozen until the requirements for risk assessment reached a final state having the Tasks focused on the aforementioned Task. After the specifications were properly defined by the VR, HF and industrial partners the developments started again.

There has been a slight delay in receiving the CAD data files, which has delayed the data preparation by 2-3 months.

Corrective actions

No corrective actions were needed as the delay did not seem to impact the rest of the work plan.

Task 1.4

Problems encountered

The major problem that was encountered was the lack of skilled developers for some project partners who are in charge of implementing the IT software tools.

Corrective actions

This lack led to development delays. The demand on skilled personnel has started to be tackled by hiring new developers as well as several joint group development meetings.

Task 1.5

Problems encountered

The major problem that was encountered was the major changes in the project organization so that the entire organization had to learn its rules and constitution entirely anew.

Corrective actions

Despite various delays at least developers could leverage the information system architecture employed to timely develop and deploy there work efforts and to share their ideas and solutions.

Task 2.1.1

Problems encountered

The completion of the Task was delayed by two months.

Task 2.1.2

Problems encountered

This sub-Task was planned to complete in M35. However, this was delayed till M41, due to holiday period in July and August and to the delay in the delivery of some of the IT tools. Therefore, the report on experiment definitions (D2.1.1) was delivered in M39 and the installation (M2.1.1) was done in M41.

The delay did not have a significant impact on the completion of the whole sub-Task 2.1, which was planned to be completed in M46.

Task 2.1.3

Problems encountered

Because this sub-Task was delayed its completion ended in M44. This left 2 months to complete the sub-Task (2.1.4 Results analysis) so that the whole of the Task 2.1 (Statoil case study) was completed but not on schedule as originally planned (M56).

Task 2.2.1

Problems encountered

The case study specification (D.2.2.1) was intended to complete by M35. However, the first draft of D.2.2.1 completed in M39. The final version was released in M41.

Task 2.2.1

Problems encountered

To fit in the time scale of the development of the OTS, the HF Lab installation was planned to take place in M50. This was the Sonatrach's preferred plan was to have the OTS and the HF Lab to be properly integrated. However, once the case study specification (2.2.1) was completed in M41, the report on experiment definition (D2.2.2) was delivered in M42, against the original planned date of M40.

Task 2.3

Problems encountered

The start of sub-Task 2.3.1 was later then originally planned. However, there was sufficient time to complete the whole Task. There was no real impact on completing this Task just by delaying its start by a few months.

Task 2.3.1

Problems encountered

The postponed starting of this Task had not real impact on the final completion as the whole of Task 2.3 was not due till M52.

Task 2.3.3

Problems encountered

The postponed starting of this Task had not real impact on the final completion as the whole of Task 2.3 was not due till M52.

Task 3.1

Problems encountered

The problem encountered sourced from a relatively late kick-off of the Task (since it was contained in a broader strategy package that needed to launch a bit later), thus the deliverable report was delayed for nearly 15 days. Another practical problem that was encountered was that the industry is quite secretive about its activities, thus the interviewing part of the market analysis did not provide the results expected. The research was focused on Internet surveys and Literature searching.

Task 3.4

Problems encountered

Paper Publications block due to IP rights protection, negatively affecting academic Partners. A three-tiered (Public, Confidential, and Project Members Only) dissemination level, applying to all external communications, operationally proved to be the most viable solution.

Corrective actions

A common framework for dissemination is currently being discussed with PMO in order to address the problem and at the same time protect VIRTHUALIS IP rights.

Task 3.5

Problems encountered

The progress of the Task, and of the deliverables, was delayed while waiting for clearer specifications of the IS2 tools and case studies. It would have been difficult to define training requirements before the nature of the tools the training needs to support are. Deliverables 3.5.1 "Training Requirements to support IS" was not yet completed. The Task was thus delayed by four months. This delay was accommodated since the initial training delivery for the risk assessment implementation in Statoil, has been delayed by three, months and the training requirement for this initial implementation will be small.

The work of the Task was hampered by the inability of three partners to carry out their roles in the Task, for differing reasons. This has been discussed with the parties in question. Two partners (POLIMI and TUC) were able to contribute in the next implementation period.

# Workpackage progress of the period

Provide an overview of the actions carried out in the reporting period, based on the workpackages (with exclusion of the Management workpackage) which were active or planned to be active during the reporting period. A section as 2.1 or 2.2 is needed for each active work package.

## WP II.0  – Task 0.1 – Steering of the project

### Objectives and starting point of work at beginning of reporting period

This Task has started since the beginning of the project, so as to manage the work performed in the project with the aim to meet the goals set in the TA agreed with the European Commission.

### Progress towards objectives

POLIMI has been in charge of this mission representing the Consortium in front of the European Commission. To that end all necessary both administrative and substantial actions have been undertaken.

## WP II.0  – Task 0.2 – Administration of the project

### Objectives and starting point of work at beginning of reporting period

This Task has started since the beginning of the project, with the objectives of: - ensure the monitoring and control of resources spent by project partners; - manage the financial reporting towards the European Commission.

### Progress towards objectives

This task has been led by D'Appolonia during the period May 2008 - December 2009 (Month 37-Month 56). During the considered period the following activities have been undertaken: - Collection and transmission to the EC of financial reporting (Form C and audit certificates) related to the third reporting period; - Collection of additional financial documents and information related to the third reporting period, following the remarks received by the EC; - Preparation of reporting for the Consortium concerning the resources spent during the third reporting period; - Preparation of budget allocation for the period Month 37- Month 54; - Revision of the budget and resources allocation for the whole duration of the project, following several modifications to the consortium and review of tasks allocated to Consortium members; - Calculation of distribution of advanced payments related to the second and third reporting periods; - Calculation of re-payment to be requested to partners who left the Consortium and received a total payment exceeding the EC contribution requested; - Analysis of resources consumed during the first three reporting year of project, as baseline for the definition of budget for the last reporting period - Preparation of requests for amending the contract with the EC, following modifications to Consortium composition and the request for project prolongation, including the modification of contractual documents (Technical Annex).

## WP II.0  – Task 0.3 – Quality management

### Objectives and starting point of work at beginning of reporting period

Quality Assurance has been subdivided into 2 major concerns. First concern is the assurance of the Process Quality and second assurance of the Product Quality. Both quality activities also comprise management activities. This results from the fact that the role of the “Quality Manager” was not part of the Management Board but a had reporting function to the Top Management only. The “Quality Manager” thus built the link between quality related research topics conducted in Task 1.5 and the actual management of the project. One can say that the operative and tactical management activities have been carried out by partners DEMOS and OVGU together comprising the Quality Assurance Group in Task 1.5, while presenting an strategically inform the Top Management was linked to Task 0.3.

### Progress towards objectives

Within the reporting period all mayor communication systems have been set up or consolidated according to decisions taken by the PMO in collaboration with the “Quality Manager”. All major quality concerns have as well as regular quality reports have been issued by the QAG and presented through the “Quality Manager” in various management meetings. Overall quality procedures have been set upon suggestion of the QAG. The QAG always tried to make as much as possible quality related information transparent to the consortium in order to adapt their work to the overall quality goal. Furthermore the “Quality Manager” and his team always carried out quality inspections and non-routine quality task upon request of the PMO or on certain trigger events (e.g. remote quality assessment in the OVGU lab while conducting management meetings abroad). Nevertheless strategic decisions have been organizationally limited to the management board only.

### Deviation from the project programme and corrective actions taken\suggested

Not all decisions taken by the Top Management, such as redevelopment of the VR part, also comprising a major switch concerning the underlying technology (from Delta3d to Ogre) and this drawing additional risk on the consortium have been taken following suggestions made by the QAG. Moreover rules to measure timely contribution as well as activity and efficiency level of partners have not been taken into account by the PMO. Furthermore following a strictly quality oriented development procedure has not been substantially reinforced by the PMO. Uncovered and fluctuating position in the line management body, such as partly uncovered WP 1 and the WP2 positions or leaving developers resulted in a relatively low acceptance and reinforcement of quality concerns throughout the consortium over time. Leaving out or circumvent test procedures, while quite common to research project, clearly signalize deviations from the initially claimed quality goals.

## WP II.1 – Task 1.1 – Design & Detailed Specification

### Objectives and starting point of work at beginning of reporting period

The objective of this Task was to deliver a document with all the IT Tools specifications and a document about the HF Methodology consolidation and integration into safety engineering models. An extension of HF Methodology consolidation was proposed in the NIP for a period of 3 calendar months. The objective of this extension is to complete the Task 1.1.1 report of the HFs Framework for the Average User, incorporate the Dynamic Event Graphs method for the Advanced User, and prepare a more comprehensive case study to illustrate the human factors methods.

### Progress towards objectives

The objective was fully accomplished with the production of the planned deliverables.

### Deviation from the project programme and corrective actions taken\ suggested

The first approach was to produce a monolithic set of devliverables and after the first release, to start with the implementation.

During the first months it was clear that a fast prototiping methodology approach was suitable, due to a not clear vision of the specs at the beginning.

On this basis, the specs implementation was due using an interactive software platform, based on a wiki server, on wich the team was able to contribute day by day in a cooperative way.

The wiki server represented the container who provided the detailed specs to the developer team. From the knowledge base produced on the wiki, was built the deliverable

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D1.1.1 | Methodologies Consolidation and Integration into Safety Engineering Models | 1.1.1 | 51 | 53 |  |  | TUC |
| D1.1.2 | User Requirements and System Specifications | 1.1.2 | 51 | 60 |  |  | EXIMIA |
| (*) if available |  |  |  |  |  |  |  |

WP II.1 – Deliverables List

## WP II.1 – Task 1.2 – IS2 System Development

### Objectives and starting point of work at beginning of reporting period

The task can be splitted into three subtasks: 1) Complete re-engineering and developement of the Virthualis 3D real time experiment environment: The previous system implementation called SafeVR and based on Delta was not satisfying in terms of performances, features and stability. So it was decided to perform a complete re-engineering and brand new implementation of the system that was called HFLab. 2) Statoil Hydro case study: Developement of the 3D scenario, logic and user interactions 3) Sonatrach case study: Developement of the 3D scenario, logic and user interactions.

### Progress towards objectives

We complete satisfied all our tasks objectives. 1) Complete re-engineering and developement of the Virthualis 3D real time experiment environment We have redesigned the real time experiment environment basing it on a messaging bus technology. The developed HFLab suite is made up by: - VRClient - SupervisorStation - ControlRoom - DebugTool - SceneHandler - MessageServer - Messaging library - OPC gateway 2) Statoil Hydro case study - 3D scenario modelling - 3D scenario interaction scripting - ControlRoom custom developement - SupervisorStation custom developement - SceneHandler custom experiment logic 3) Sonatrach case study - 3D scenario modelling - 3D scenario interaction scripting - ControlRoom custom developement - SupervisorStation custom development

### Deviation from the project programme and corrective actions taken\ suggested

For the Sonatrach case study was implemented from scratch the Turbine Symulator, because not provided from the producer ManTurbo. The activities conduced to design and develop a software module, integrated with the Virthualis Symulation Engine, able to simulate all the status of the turbine, describing the startup, the running phase and the shutdown. The variables simulated was connected to the Sonatrach Virthualis (IS)2 product.

The 3D scenario of Sonatrach case study was designed from scratch because the partner did not provide CAD files. This took more resources and time as planned.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | HFLab platform | 1 | 45 | 45 | 18 | 18 | 23_MW |
| 3 | Sonatrach distro | 1 | 59 | 59 | 13 | 13 | 23_MW |
| 2 | StatoilHydro distro | 1 | 45 | 45 | 15 | 15 | 23_MW |
| *) if available |  |  |  |  |  |  |  |

WP II.1 – Deliverables List

## WP II.1 – Task 1.3 – Case study on Statoil Hydro and Sonatrach

### Objectives and starting point of work at beginning of reporting period

Using the reenginered Virthualis (IS)2 platform, the two case studies Statoil Hydro and Sonatrach, were redesigned according the new technology. For each case study was implemented the developement of the 3D scenario, the scene logic, the experiments logic and the user interactions.

### Progress towards objectives

We complete satisfied all our tasks objectives. 1) Complete re-engineering and developement of the Virthualis 3D real time experiment environment We have redesigned the real time experiment environment basing it on a messaging bus technology. The developed HFLab suite is made up by: - VRClient - SupervisorStation - ControlRoom - DebugTool - SceneHandler - MessageServer - Messaging library - OPC gateway 2) Statoil Hydro case study - 3D scenario modelling - 3D scenario interaction scripting - ControlRoom custom developement - SupervisorStation custom developement - SceneHandler custom experiment logic 3) Sonatrach case study - 3D scenario modelling - 3D scenario interaction scripting - ControlRoom custom developement - SupervisorStation custom developement

### Deviation from the project programme and corrective actions taken\ suggested

For the Sonatrach case study was implemented from scratch the Turbine Symulator, because not provided from the producer ManTurbo. The activities conduced to design and develop a software module, integrated with the Virthualis Symulation Engine, able to simulate all the status of the turbine, describing the startup, the running phase and the shutdown. The variables simulated was connected to the Sonatrach Virthualis (IS)2 product.

The 3D scenario of Sonatrach case study was designed from scratch because the partner did not provide CAD files. This took more resources and time as planned.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | HFLab platform | 1 | 45 | 45 | 18 | 18 | 23_MW |
| 2 | Sonatrach distro | 1 | 59 | 59 | 13 | 13 | 23_MW |
| 3 | StatoilHydro distro | 1 | 45 | 45 | 15 | 15 | 23_MW |
| *) if available |  |  |  |  |  |  |  |

WP II.1 – Deliverables List

## WP II.1 – Task 1.4 – IT-Tools validation

### Objectives and starting point of work at beginning of reporting period

The overall objective of this task is to validate the added value of “VIRTHUALIS IT Tools” for improving safety, without any consideration of Virtual Reality aspects. It is planed that this task is managed by three engineering companies (INERIS, TECNATOM and RELCONSULT), in close relation with industries from the VIRTHUALIS consortium and from outside of it. One main question: how much is the added value of IT Tools for improving safety? Five sub-questions: • Added value for doing risk analysis? New results? • Added value for designing, auditing and improving safety management systems? New results? • Added value for doing accident investigations? New results? • Added value for training? New results? • Added value for an integrated approach of risk analysis, safety management, accident investigation and training? IT Tools have to be installed and tested in different industries and engineering companies. One of the aim issues of this task is to give feedbacks and proposal of improvement in a timely manner in order to improve the IT Tools design and implementation … as far as it is possible. This task is also linked to the WPII.3 Exploitation and technology training (especially to the task “3.5 VIRTHUALIS Technology training”).

### Progress towards objectives

Preparation of the working concept and procedure for the IT tool validation process, based on the review the End Users and methodological needs collected during the project (WP1, WP3, WP4, WP5, task 1.1), and on the review functionality that IT Tools should provide, tasks 1.2. ; Discussion and harmonisation of this concept with the ideas of involved partners; -> a specific evaluation table has been completely developed on the example of Risk Assessment. - Preliminary work to evaluate the added value if specific IT tools related to the tools available at the market place (e.g. TM, FPE, Alba, Axim) - Identification of some industrial companies interested by the test of the IT Tools.; final report (VIRTHUALIS-ITToolValidation1.4FinalV04.doc).

### Deviation from the project programme and corrective actions taken\ suggested

Deviation from the project program: - a delay in the development of the IT Tools, - a delay in the production of a document describing the IT Tools functionalities from an end user point of view, on which the evaluation could have started (i.e, with a list of IT Tools inputs and outputs). Without IT Tools duly developed, installation on the industrial sites cannot take place and the experiments cannot be carried out. Corrective actions was suggested: in agreement with the PMO and other partners of the task, in order not to spend the money of the project unnecessarily, it was considered more judicious to wait a satisfactory stage of development of the IT Tools (and their documentation) before starting work fully.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | IT Tool Validation of Added Value, Task 1.4 | 1 | 0 | 0 | 0 | 0 | 56_RELCONSULT |
| *) if available |  |  |  |  |  |  |  |

WP II.1 – Deliverables List

## WP II.1 – Task 1.5 – Product Quality Assurance

### Objectives and starting point of work at beginning of reporting period

The goal of this task is to assure the compliance of the product (tools and applications for risk assessment, accident investigation, operational safety management and training) with the needs and requirements of potential end users (i.e. industry). Since quality assurance is intended to be a continuous and dynamic process, it should accompany the development of tools and applications as well as testing and validating them in accordance with the product development road map. Furthermore and due to the distributed set-up of the consortium a major concern and necessary precondition of Product Quality Assurance is the assurance of the consortium's entire communication process and quality capabilities. This has been determined as project's most obvious weakness in proceeding quality during the ARM of year 3. In the previous phase and as a direct consequence of the aforementioned difficulties, it had become obvious that industries standards (especially in terms of Software Quality Assurance) were not applicable. This has even been amplified by the significant shortcoming of development personnel as well as only weak organizational team experience (due to the late beginning of the development process) and only limited time period until projects ends.

### Progress towards objectives

Since then VIRTHUALIS project evolved from a human factors centric research project, driven by industrial needs into an information system related development project, the scope of Product Quality Assurance had to be extended and partly transformed. Quality Assurance Group (QAG) which is responsible for ensuring and tracking quality expanded the approach with an information system related Software Quality Assurance Process (SQAP). Owing to the fact that the term “quality” has an ambivalent definition, quality assurance in VIRTHUALIS has been separated into internal “Process Quality Assurance”, including review of deliverables, internal documents, responsibilities as well as consortium wide communication infrastructures (i.e. consolidation of the entire supportive information system incl. Website, Bug Tracker, SVN, Wiki, SSH, FTP etc.) and “Product Quality Assurance” (actual testing of the Product). The concern of this task has been therefore to keep track of external (i.e. end-users) and internal (i.e. organizational) requirements as well as planning, steering and supervising software tests and defining quality rules and procedures with a software development scope. To assure a full awareness to software development quality in day to day development and therewith an optimal overall product quality, time consuming procedures and guidelines would have been the best solution, which is unfortunately not possible within a huge organization such as VIRTHUALIS. The QAG has increased the partners' awareness to quality by continuously sticking to quality aspects (i.e. playing the advocatus diabolus). Unfortunately the majority of the organizational body still does not fully anticipate the importance of quality but only accept the basic need for its pursuing. Partners have been continuously requested to internalize the quality rules that have been set and even learning to anticipate them. QAG tracked and traced this learning and training process and frequently reported quality status to the PMO. QAG took several major actions to improve both process and product quality (e.g.: Consolidating the entire IT-System infrastructure Taking over First and Second Level Support for the information system infrastructure Setting up VDM system for management reporting Various improvements to the collaborative knowledge platform (Wiki) Setting up new project website Introducing an maintaining a bug and issue-tracking system and help developers to proceed quality Continuous quality review using the bug and issue-tracker Reviewing specifications and preparing management report Preparing various internal as well as external quality reports Installation guidance for training an validation teams.

### Deviation from the project programme and corrective actions taken\ suggested

Due to major changes in the project organization as well as to the involved partners (discussions to exclude VRMMP, ICCS and IFF) after the last annual review meeting and even previous happenings, the entire organization had to learn its rules and constitution entirely new. Furthermore there were huge uncertainties about partners' responsibilities and the future project road map. The proposed software could not be developed as originally planned in the TA. One of the reasons behind that was the refactoring of the entire VR environment (based on a PMO decision partner MOTHERWAY took over the task leadership role of task 1.3). A further reason was the process of restructuring the gathered end-user requirements which turned out to be more difficult than anticipated due to methodological uncertainties and unclear value added among projects experts. Due to the technically new methodological approach towards industrial safety the organization still does not have full-featured could not leverage a full-featured version of functional software specification at a early stage of development but rather adopted a ad-hoc development and test cycle. The software development was thus following a significantly more agile approach. Even if the software requirement specification became finally ready during April 2010 and a early version of it has been used starting from 11/2009 this does not reflect the planned requirements engineering and Software Quality Assurance Process as it has been planned. The illustrated difficulties and deviations thus made traditional state-of-the-art software testing (planning and running) almost impossible, since the question of what has to be tested against which measures has been poorly answered during the course of the time. Some but not all grounds can be found in the fact that research projects always suffer from a high level of uncertainty during the entire project phase. Despite various delays at least developers could leverage the information system architecture employed to timely develop and deploy there work efforts and to share their ideas and solutions.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D 1.5 | System Release Quality Report | 1 | 56 | 60 | 2 | 2 | 53_OVGU |
| *) if available |  |  |  |  |  |  |  |

WP II.1 – Deliverables List

## WP II.2  – Task 2.1 – RASVR+TRVR STATOIL

### Objectives and starting point of work at beginning of reporting period

The overall objective of this task is to validate the Risk Assessment and Training (IS)2 products (HFLab+IT_Tools) for STATOIL, by porting and testing them to STATOIL to carry out real-life field tests, with respect to the developed methodology and to identified user needs and requirements, and to identify possible improvements to consolidate the product for commercial exploitation after the end of the project. The activity is to be developed through these five steps: 1. Review of the Statoil Case Study Specifications (deliverable D.2.1.1) after internal peer reviews; 2. Design of Experiments (DoE) to be tested by Statoil operators and HSE/Training specialists; 3. Delivery and installation of (IS)2 product at Statoil Training Centre (Porsgrunn); 4. Perform Methodology and Technology Training to Statoil HSE/HF experts and Operators; 5. (IS)2 Testing, Validation and Fine Tuning by Statoil operators and HSE/Training specialists, assisted by a team of experts in VR, Safety and Human Factors; 6. Carry out real-life experiments with Statoil personnel (operators and engineers) and validate the (IS)2 solution, demonstrating its usefulness to perform Training and Risk Assessment on site using (IS)2 as an experimental Safety and Human Factors lab.

### Progress towards objectives

1. Review of the Statoil Case Study Specifications (deliverable D.2.1.1) after internal peer reviews was completed in June 2008; 2. Design of Experiments criteria have been defined during a meeting hosted by DTU in Copenhagen (March 2009). The DoE was finalized at DEMOS (Athens) in October 2009; 3. Delivery and installation activity of the ready-for-experiments (IS)2 solution was delayed to November 2009 due to lack of founds for VR developers; 4. Methodology and Technology Training to Statoil HSE/HF experts and Operators was performed immediately after installation of the ready-for-experiments (IS)2 solution; 5. (IS)2 Testing, Validation and Fine Tuning by Statoil operators and HSE/Training specialists, assisted by a team of experts in VR, started immediately after installation completion. A release nr. 2 of the (IS)2, following Statoil operators and HSE/Training specialists suggestions, was not possible to be delivered; 6. The experimental campaign was held in December 2009 at Statoil Research Centre in Porsgrunn (NO), and involved Statoil HSE and HF Experts, as well as Operators. Finalization of the Deliverable D.2.1 “Final report on Statoil (IS)² Validation” was completed in April 2010.

### Deviation from the project programme and corrective actions taken\suggested

3. Delivery and installation activity of the ready-for-experiments (IS)2 solution was delayed to November 2009 due to lack of founds for VR developers. This factor had an impact on the D.2.1 issue date, postponed to M60. 6. Limited time available for experimental campaign that Statoil was able to offer (2.5 days) did not allow the Virthualis team to complete the planned sequence of Experiments. Thus it was not possible to: - compare the tested Operators Response Time with the one assumed in the Statoil QRA; - do a sensitivity analysis on the 9 Common Performance Conditions families in order to verify and to rank their influence on the operator response time. However, it was demonstrated that both activities can be performed with the use of the (IS)2 solution, which can be therefore used to perform Training and Risk Assessment on site using (IS)2 as an experimental Safety and Human Factors lab.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| D 2.1 | Final report on Statoil (IS)2 Validation | 2 | 59 | 60 | 12 | 0 | 02_DAPP |
| *) if available |  |  |  |  |  |  |  |

WP II.2 – Deliverables List

## WP II.2  – Task 2.2 – RASVR+OSM SONATRACH

### Objectives and starting point of work at beginning of reporting period

The case study is concerned with the start-up of a Gas Turbine which is used to drive the compressor of the propane chilling section of GP1Z complex in one of the SONATRACH installations at Arzew, Algeria. The overall objective of this Task was to validate two safety actions, the Risk Assessment and the Operational Safety Management. The work was divided into three activities: - Case study specification - Experiments definition - Testing and validation & fine tuning.

### Progress towards objectives

Review of the Sonatrach Case Study Specifications (Annex_1_D.2.2.1.Final_V9.doc); Design of a simple model of human performance that includes execution and control & command functions, for the experiments definition and the debriefing (Sonatrach - Parameters and Markers.doc). Definition of the DOE (design of experiments) methodology (SONATRACH_Case_Study_DoE_ver3.doc); From April 12th to 16th 2010, Testing, Validation and Fine Tuning by Sonatrach operators and HSE specialists, assisted by one expert in VR. The deliverable D222 Final report on Sonatrach (IS)2 Validation is under process.

### Deviation from the project programme and corrective actions taken\suggested

1. The Sonatrach case study suffers from the delay in the all IT Tools development, excepted the FPE. Data management was made difficult by the absence of the Task Modeller and by the technical and methodological difficulty of access to Alba. It is demonstrate that Virthualis methodology, although very innovating and full with promise for the improvement of safety, is too much heavy if it is not shouldered by IT tools. 2. The Virthualis methodology had to be improved/modified during the field work process (see differences between D111 and D221). Sonatrach case study is the occasion to call into question assumptions formulated since the beginning of the project: - scenario of uses (wp1), - dated model needed (wp4), - shape of RA, OSM, Tr, AI and the tool to be developed (wp5.3), - exact uses of (IS)2 components. Progression of research is chaotic, not linear. One can say that we meet the classical difficulties when demonstrators are developed at the end of the project: theory vs. practical issues, dreams vs. reality.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | D2.2.1 SONATRACH Case study specifications | 2 | 0 | 0 | 0 | 0 | 18_INERIS |
| 2 | D2.2.1 SONATRACH Case study specifications | 2 | 0 | 0 | 0 | 0 | 18_INERIS |
| *) if available |  |  |  |  |  |  |  |

WP II.2 – Deliverables List

## WP II.3  – Task 3.1 – Market analysis update

### Objectives and starting point of work at beginning of reporting period

WP II.3 activities started at the beginning of 2009 when STR Solutions (Giuseppe Sannazzaro) was appointed responsible of the work package. Previous activities done under WP I, included a general market overview of the 3D technology available but limited to the simple 3D visualization process.

The objectives of the present task can be summarised as follows:

- identify the industry final end-users needs in terms of safety and in terms of the 4 safety actions;

- identify the market of reference given the IS2 developed from November 2007 onwards;

- given the 2 points above, perform a market analysis, aiming at developing an analytical tool required to perform task 3.2 hereunder.

At the beginning of the working period, it was envisaged to discuss with industrial partners within the Consortium needs and requirements as a starting point to accomplish objectives 1 in point 1 above.

However due to difficulties in obtaining directly from the industry information on sensitive data on one hand and in obtaining data that represent the overall industry market, this approach had soon to be changed.

### Progress towards objectives

In the same period (first 5 months of 2009), thanks to PMO efforts it was possible to sign an important MOU with Honeywell which helped WPII.3 leader and contributors to obtain a clearer picture of the market of reference and in the long run to develop all the required market analysis and its objectives.

Following this approach it has been assumed that industry automation identifies inside its global market, VIRTHUALIS absolute potential market. This concept mainly derives from the belief that IS2 is strictly intertwined with the industry automation application due to the large amount of engineering work shared by both.

With the help of Honeywell the group started working along these directions and prepared a complete market analysis.

While preparing the above, during a reunion of LM (June 2009) it was however noticed that VIRTHUALIS IS2 does not end in the Automation industry. For this reason a parallel line of market analysis has been developed based on the “safety consultancy” streamline and applied to the so-called Seveso plants (process industry).

The first part of the analysis was done by POLIMI between June and September 2009 under the leadership and contribution of STR. The second part of the analysis was developed jointly by Relconsult and STR, based on data and information provided mainly by Relconsult.

Given these two parts the whole market analysis (deliverable 3.1) was finalised by the end of September 2009 and revised and updated by the end of March 2010.

### Deviation from the project programme and corrective actions taken\suggested

As already stated in paragraph 2.11.1 above the first programme included the possibilities to discuss and interview industry partners. This original plan has not been performed for reasons already expressed in paragraph 2.11.1 above.

Corrective actions with the help of Honeywell have made possible the realization of a thorough market analysis in relation to the automation industry sectors, while the help of Relconsult has made possible the development of another portion of the market analysis referring to consultancy report in relation to the Seveso plants sectors.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 3.1 | Market Analysis | 3 | 56 | 54 (rev. 59) |  |  | 19-STR |

WP II.3 – Deliverables List

## WP II.3  – Task 3.2 – Definition of the IS2 product

### Objectives and starting point of work at beginning of reporting period

The main objective of the task was to define the business area of VIRTHUALIS IS2. As already anticipated in the previous article 2.11, the difficulties in defining the business area of a “product” like IS2 is linked to the innovation component which makes it difficult to be defined in clear business, market and economics terms. In fact a new “invention” to be successful creates its own new market (as already conceived in theoretical terms by the liberal thought more than 100 years ago) but until the market is in place, it is difficult to define it with proven scientific method.

Our method of work started from the points already indicated in point 2.11.2 above, i.e. from the identification of the market of reference for IS2 in the automation industry and in the safety consultancy report (in relation to the SEVESO plants). Two main considerations have led us to this conclusion: (1) the close link between process industry and industry automation and (2) the large amount of engineering work required in the industry in reference to obtain proper results. Similar principles apply to the consultancy report in relation to SEVESO plants. In this way the safety market for process industry has been broadly covered.

### Progress towards objectives

This part of the work has been performed by POLIMI and STR jointly with the help of the PMO. The starting point was the identification of a three dimensional Abell diagram.

Abell identifies on a three axes diagram the following three functions/groups:

- Customer Groups, referring to “who needs to be served”

- Use Functions referring to “what do customers want, what need has to be satisfied” i.e. identification of customer needs.

- Technologies Utilized refer to “what means should be used to carry out the use function” that is the way that the needs are being satisfied.

The advantage of this approach is to analyse business not only in terms of products and market but also in terms of technologies to be utilized and identification of customers’ needs.

In this way customers have been identified as belonging to the various subcomponents of the process industry (mainly oil and gas, refineries and chemical/petrochemical), use functions have been identified in the four safety actions (Training, Operations Safety Management, Risk Assessment, Accident Investigation), while technologies to be utilized have been identified within the technological framework prepared by the Consortium in the last years but with an important distinction between customised and standardised solutions.

It has to be clearly stated that the scientific method used in WP II 3.1 and 3.2 is not a strictly deductive one (i.e. moving from assumptions to results through a straightforward analysis) but it requires a certain amount of reiteration between the assumptions and analyses of WP II 3.1 and 3.2 (and vice-versa), thus reaching a sufficient basis required to develop the most important achievement of WP II 3 which is the Business Plan i.e. deliverable under WP II 3.3.

### Deviation from the project programme and corrective actions taken\suggested

Once assumptions have been clearly stated and analysis performed, no major deviation from programme has occurred and therefore no major corrective actions have been required.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | Definition of IS2 product (Business area definition) | 3.2 | 56 | 54 (rev. 59) |  |  | 19-STR |

WP II.3 – Deliverables List

## WP II.3  – Task 3.3 – Developing a market strategy

### Objectives and starting point of work at beginning of reporting period

Once defined the business area of IS2 (deliverable 3.2) and performed a thorough market analysis (deliverable 3.1), the objective of this task was the preparation of a full document along guidelines prevailing in the business community, describing the business and market strategy envisaged for the future of IS2, i.e. a business plan and information memorandum.

Work started in July 2009 and the first decision in preparing the Business Plan was to include all or most of the work done in WP 3.1. and 3.2 but in inverted order, i.e. a definition of the Business area of IS2 first and a market analysis afterwards.

### Progress towards objectives

Once the first part of the document was outlined, the rest of the document had to define and discuss possible strategic options of the business model.

The following are the main issues discussed and analysed in the business plan:

- the IS2 is not a real product but a solution and as such requires technical skills that includes the following areas of business: IT, process engineering, risk and safety consultancy, 3D visualization skills. The conclusion was that a solution of this nature has to be flexible in terms of products definition and identification.

- Given the large world-wide market, a concentration of the future market activity in a well-defined geographical area was required. IN our case EMEA geographical area was chosen.

- The main alternative discussed was between the development of a small independent company and the setting up of a division of a large corporation. The first choice was preferred for flexibility reasons but also in view of a greater economic sustainability.

- IN order to obtain a complete range of the technical and managerial requirements a network of VIRTHUALIS partners was conceived. Different legal options of such a network have been analysed leading to the belief that final legal form will be agreed at a later stage, depending on the future business development of the project.

- The IPR issue has been discussed inside the document in light of the high level of methodological work done and the high level of IT software work developed.

- A business price model has been conceived and discussed in the document. Prices have been identified on the basis of the case studies done in VIRTHUALIS (STATOIL and SONATRACH) and on comparison with tools existing in the automation industry (like the OTS).

- Finally a financial model has been implemented on the basis of the assumptions and issues here above outlined. Our choice has opted for a simple financial model with a high level of economic and development sustainability rather than a financially complex structure with a lot of uncertainties.

In our view the outcome of the task is a document that not only deals with the main objective of the task, i.e. the development of a market strategy, but goes beyond that by outlining and implementing concrete facts towards the constitution of the future small independent company (point 3 above) and the structure and mission of the network envisaged for VIRTHUALIS (point 4 above).

This task has been performed by STR with contributions by:

POLIMI for the first part,

UNIMORE for the financial model described in point 7 above and for general lay out and revision/improvement.

### Deviation from the project programme and corrective actions taken\suggested

During the first part of the work done on this task (months 52-54) a complex financial model was developed. The main problem arising from this approach was the need to make important assumptions on the growth rate of the business in reference. For such reason it has been decided to prepare a simpler financial model (as already described in point 7 of the previous paragraph) more in line with the small business model approach.

The business plan was uploaded on the Wiki at months 56. After a review by reviewers it has been modified in order to include a list of abbreviations, an executive summary, some methodological changes (source of data and information more clearly defined) and an overall lay-out and graphical improvements.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | Business plan (market strategy development) | 3 | 60 | 56 (rev. 59) |  |  | 19-STR |

WP II.3 – Deliverables List

## WP II.3  – Task 3.4 – Dissemination activity

### Objectives and starting point of work at beginning of reporting period

The objective of Task 3.4. is the coordination and support of VIRTHUALIS Dissemination Activities.

### Progress towards objectives

- Creation and coordination VIRTHUALIS Academic Publication Panel (VAPP) and relative guidelines to manage the confidentiality problems in publications).

- Review process applied to all external scientific publications of VIRTHUALIS, abstract submission included.

- New website layout and contents developed.

- Field research finalized on potential applications of VIRTHUALIS technology.

- Updated plan for Using and Disseminating the Knowledge.

- Updated Dissemination Material, including press releases and printed leaftlets.

- Support for Dissemination Events

- Contributed to legal framework for VIRTHUALIS NewCo

### Deviation from the project programme and corrective actions taken\suggested

The main deviation from initial project programme is the cancellation of the final VIRTHUALIS Conference as agreed with Project Management.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 1 | Dissemination Report | II.3 | 52 | 52 |  |  | 8-UNIMORE |

WP II.3 – Deliverables List

## WP II.3  – Task 3.5 – Technology Training

### Objectives and starting point of work at beginning of reporting period

The objective of this task is to deliver a framework of training and performance support for the implementation of the Virthualis tools.

### Progress towards objectives

Building on the training needs and training concept defined in the previous reporting period, the task proceeded to elaborate the specific training requirements related to each software tool. These training requirements were translated into a set of four training solutions: - Virthualis Methodology Training; Methodologies: face-to-face and web tutorial - Software tools training; methodologies: face-to-face and web tutorials - VR lab configuration and management: presentations and videos - VR interaction for e-learning or face-to-face training; Methodology: interactive e-learning training tool These training solutions were delivered to Statoil in support of their implementation, and their deployment evaluated. Training solutions were also evaluated by the task partners.

### Deviation from the project programme and corrective actions taken\suggested

It was originally envisaged that this task would deliver face-to-face workshops in the to the end users. However, deviation from the planned task was necessary because - delays in software development and deployment meant resources had to be re-directed to ensure delivery of the VR lab - Statoil were not prepared to commit additional resources to accommodate the training need analysis and training delivery until they had installed and piloted the software - the target group was narrowed - the methodology expertise is widely distributed in the consortium so a methodology needed to be found to effectively bring that expertise to the end-user - web-tutorials were chosen as the most effective means of bringing expertise from across the consortium to the Statoil end-users - Delivery of training in Sonatrach to the same extent as Statoil since the end-user resources were focussed on ensuring installation and piloting of the VR lab.

### List of deliverables

| Deliverable |  | WP | Due Date (Month) | Actual/ Forecast delivery date | Estimated indicative person-months* | Used indicative person-months*) | Lead Contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N. | Title |  |  |  |  |  |  |
| 3.5.1 | Training to support Virthualis implementation | 3 | 0 | 0 | 0 | 0 | 09_TCD |

WP II.3 – Deliverables List

# Consortium management

Most of the scientific efforts of the period were devoted to guarantee:

- Integration (linking components together);

- Innovation (creating added value);

- Usability (making product usable and stable enough to be industrialised);

- Coherence to scientific results, in particular selected methodologies.

Strategic Management tasks were focused on:

- Internationalisation;

- IPR management

- Create alliances;

- Exploitation of VIRTHUALIS product.

## Consortium management tasks

In addition to the aforementioned strategic tasks, the activities of this WP were focused on:

- Ensure an updated managerial structure in place capable to promptly respond to the evolving development activities and ensuring that project objectives were reached by the deadlines set out, within the financial budget, and high level of technical content produced;

- Guarantee the total and effective quality of all product-related components being produced, together with the associated documentation, by setting up a formal and structured Quality Deployment process;

- Control and consolidate project planning, progress reports, budgetary overview with the partners and in accordance with EC's requirements;

- Focus the effort of contractors both on contractual commitments and on mid-term business goals related to a positive and effective industrial exploitation of the results;

### Put in place appropriate and effective corrective actions needed to ensure that project objectives were met. Tasks achievements

Tasks accomplished during this last period of project activity are as follows:

- Manage WPs both technically and organizationally in order to get the 2 industrial applications done and installed at the 2 industrial sites;

- Sign a Memorandum of Understanding (MoU) with Honeywell in order to get both feedbacks on the VIRTHUALIS solution from the one of the largest automation companies producing OTS and prepare the ground for a future commercial exploitation of the VIRTHUALIS solution;

- Develop a viable Business Plan for the VIRTHUALIS company to create after project conclusion to bring the solution on the market;

- Produce and share Intellectual Property framework in order to clarify the IP rights of different partners;

### Problems occurred and actions taken

In addition to the many technical and managerial issues tackled at task level, the following project issues were faced:

- The delay in the OTS delivery for the SONATRACH application;

- Shortfall of resources to cope with the technology training.

Actually, the OTS was necessary to guarantee that the SONATRACH application would have not been a useless videogame. The bad news that the OTS would have not been delivered in time for the completion of the project came 6 months before delivery. This would have implied a failure of the second application. Fortunately, having an experienced person like Remo Galvagni (project safety expert) enabled STR to develop a fast running simulator that saved the situation, i.e., the SONATRACH application eventually was up and running.

As for the technology training, fortunately the proposal and experience of TCD staff enabled to perform a remote technology training that allowed to save time and resources, without compromising the training efficacy. Podcasts were produced for the STATOIL application and STATOIL personnel trained remotely.

## Changes in the consortium

Some changes have occurred during the project time, as follows.

### Changes in contractors’ responsibilities

The elimination of sub-tasks and the assignment of higher responsibility and flexibility to task leaders enabled to have the necessary adjustments needed during the development without significantly impinging on contractors’ responsibilities.

### Changes to consortium itself

The substantial change in the consortium composition took place from Phase I to Phase II were 19 people were voted off the consortium and 4 other new partners were included.

Within Phase II no changes in the consortium composition took place.

## Project timetable and status

In the picture to follow the Pert and Gantt charts of the last period is reported.

## Partners’ communication and meetings

Extaordinary General Assembly, Milan , February 4 & 5 ,  2009

Project Final Review Meeting, Milan, May 17-19 2010.

## Co-operation with other projects/programmes

Links with INTUITION and TRENDS have been assured, for the former by its co-ordinator participation in VIRTHUALIS (ICCS), and for the latter by POLIMI.

# Final Review Meeting & Conclusions

Thanks to the ash cloud of the Icelander’s volcano the Final Review Meeting had to be moved and set-up in Milan.

Actually, the original planning was that of organizing the FRM at SONATRACH premises to see and “touch” the application developed for SONATRACH, i.e., the “Gas Turbine Start-Up”, jointly with that of STATOIL, i.e., the “Gas Leak Management”. This even due to the fact that SONATRACH bought an innovative VR Lab with 2 immersive screens to experiment the multiplayer feature, just developed to suit that type of needs.

The FRM concluded positively with the following agenda:

Sixth Framework Programme

PRIORITY 3-NMP

New Production Processes and Devices

VIRTHUALIS

Virtual Reality and Human Factors Applications for Improving Safety

NMP-515831-2

Agenda of Final Review Meeting

| Document No.: | VIRTHUALIS FRM Agenda – 18./19.05.2010 |
| --- | --- |
| Authors | Frederik Kramer (OVGU) |
| Status (F: final; D: draft; RD: revised draft): | RD |
| File Name: | Agenda FRM Final |
| Distribution: | FRM - All |
| Date: | 13.05.2010 |

Table of Content

1	Venue and date	1

2	Preparation	Error! Bookmark not defined.

3	Agenda	2

4	Other issues	Error! Bookmark not defined.

Revision Chart and History Log

| Version | Date | Responsible | Reason |
| --- | --- | --- | --- |
| V01 | 13.05.2010 | Frederik Kramer | Preparation FRM |

Venue and date

Venue

Politecnico di Milano (POLIMI) & University of Milan (UNIMI)

- Morning of Tuesday @ POLIMI

Aula Magna – Rectorate

- From Tuesday afternoon till Wednesday noon @ UNIMI

VR Lab

- Afternoon of Wednesday @ POLIMI

Aula Magna – Rectorate

Date

Tuesday 18th May & Wednesday 19th May 2010

Agenda

| 18.05.2010 |  |  |
| --- | --- | --- |
| time | topic | presenter |
| Strategic View |  |  |
| 9.00 – 9.30 | Project Summary | S. Colombo, S. Vanuzzi |
| 9.30 – 10.00 | Best Practice in VR versus Project Achievements | D. Marini |
| 10.00 – 10.30 | Best Practice in IS2s versus Project Achievements | P. Kafka |
|  | Coffee Break |  |
| 11.00 – 11.30 | Project Exploitation | G. Sanazzaro |
| 11.30 – 12.00 | Status & List of Deliverables and Quality Assurance | Z.Nivolianitou, F.Kramer |
|  | Lunch |  |
| methodology & system improvements m37-m60 |  |  |
| 13.30 – 14.00 | Methodology Improvements | T.Kontogiannis |
| 14.00 – 14.30 | Technology Improvements | M. Locatelli |
| 14.30 – 15.00 | System and Tools Functional Requirements | D. Marini |
| 15.00 – 15.15 | The Task Modeller Tool | S. Cromie |
| 14.15 – 15.30 | The ALBA for VIRTHUALIS Tool | M. Demichela |
|  | Coffee Break |  |
| 15.30 – 17.30 | The STATOIL Use Case & the STATOIL Application (180’, Andrea et al.) - The Use Case - The STATOIL application - Technology Training - The experiments and the results - Q&A session | A.Monferini, S.Cromie |
|  | End of Meeting |  |

| 19.05.2010 |  |  |
| --- | --- | --- |
| time | topic | presenter |
| 9.00 – 12.00 | The SONATRACH Use Case & SONATRACH Application (180’, Emmanuel et al.) - The Use Case - The SONATRACH Application - The Bow-Tie Analysis - The experiments and the results - Q&A session | E.Plot et. al. |
|  | Coffee Break |  |
| 12.00 – 12.15 | Voice of the Customer – STATOIL | B. Moltu |
| 12.15 – 12.30 | Voice of the Customer – SONATRACH | M. Naar |
|  | Lunch |  |
| 14.00 – 14.30 | The Business Plan | G. Sanazzaro |
| 14.30 – 15.00 | Wrap-up | S.Colombo et. al. |
|  | End of Meeting |  |

## Presentation of the 2 applications developed

Apart from the aforementioned force majeure, the FRM concluded with the presentation of the two applications developed for STATOIL and SONATRACH.

Both STATOIL and SONATRACH representative highlighted the usefulness of the VIRTHUALIS approach and its potential. Both companies expressed their wish to have a proper product developed in the project. The project officer, Mr. Søren Bowadt explained that the result achieved by the VIRTHUALIS Project is the maximum a European Project can aim at, i.e., a precompetitive product. Actually, EC does not finance the development of products but, instead, the creation of precompetitive applications that enable industry to touch the feasibility and viability of a certain root, thus reducing the risk of investment, i.e., seed capital part, to build a proper product after the project findings and outcomes.

Both companies expressly manifested the intention to find internally the best way to continue working with the VIRTHUALIS Company.

## Business plan

As anticipated at the 3rd Annual Review Meeting at STATOIL premises, the future exploitation of VIRTHUALIS would have been that of setting up a company to bring on the market the project findings.

To that aim, a business plan was prepared and presented.

The Business Area has been defined analysing:

- The VIRTHUALIS Safety Actions;

- The Customer Group;

- The technology used (standard vs. customised);

The Abel diagram has then been drawn up to graphically highlight the different options:

The Market Analysis is the fundamental activity that gives to the Business Plan the essential ground to:

- Understand the sustainability of the business;

- Perform the strategic analysis

This activity has been performed in tight cooperation with HONEYWELL.

The Absolute Market by Region is as follows:

The results of the Market Analysis are as follows:

- 18 major companies operating in the automation industry for a total market share of 78,5%;

- Approx. 100 SMEs oprerating in the automation industry for a total market share of 22,5%;

Options to bring the VIRTHUALIS solution on the market are as follows:

- Creation of a division of a large company

- Creation of an SME specialized in software and engineering services

In the definition of the business model the latter has been chosen.

The reason of this choice is threefold:

- Greater flexibility in terms of work to perform

- Greater flexibility of solutions to propose (customers’ needs)

- Greater flexibility in terms of sales channel

## Intellectual Property

In order to foster the creation of the VIRTHUALIS Company and avoid hampering the use of the IP generated by the consortium, an Intellectual Property plan has been discussed internally at Line Management level and presented at the FRM.

After revision of all activities done in the consortium, it has been identified 3 main streams of IP reflecting the different expertise made available by partners, namely:

- IP associated with the creation of the methodology;

- IP associated with the creation of the use cases;

- IP associated with the creation of the software.

According to the Consortium Agreement and the EC Contract in place, each partner owns the IP related to the part developed during project activities.

The IPR Shares have been assigned to partners on the basis of the undeniable fact that the skills deployed in the project, i.e., paid, are of three kind, namely: research skills, safety analysis skills, and software development skills.

Some partners deployed research skills, others deployed safety analysis skills (including H&OF and training ones), and others deployed software development skills. Some partners deployed more than one expertise. And some other simply did not contribute to the development of the VIRTHUALIS Solution.

The IPR Shares have been assigned as follows:

- those partners who paid and deployed research skills and took part to the development of the methodology will have access to the VIRTHUALIS methodology and have the rights to use it;

- those partners who paid and deployed safety analysis skills (including H&OF and training ones) and took part to the development of the use cases will have access to the VIRTHUALIS Use Cases and thus have the rights to use them;

- those partners who paid and deployed software development skills will have access to the source code of the entire version to which they have contributed to develop and have the rights to use it.

Those partners who did not pay and deploy software development skills but contributed to the development of the IT solution, will have access to the executable version of the software and have the rights to use it for internal purposes at no charges (royalty free).

In the section to follow are indicated the IPR Shares subdivided in the aforementioned 3 parts, i.e., IPR Metodology, IPR Use Cases, IPR Software.

IPR Shares for the Methodology

IPR Shares for the Use Cases

IPR Shares for the Software

Conclusions

All in all, and despite the many difficulties the project has gone through, it can be concluded that the project closed successfully as it has been able to produce practical industrial applications that proved the original idea of VIRTHUALIS is not just viable but desirable by industry.